## Projects
Project Number | Project Type | WBS | Division | Duration | Start Date | Finish Date | Budget | Cost per Day | Contract | Revenue per Day | Project Number | Project Type | Start | Finish | Budget | Contract | Project Number | Date | Day Number | Cost Per Day | Revenue Per Day | Cumulative Cost | Cumulative Revenue
106 | Multifamily | 1.1 | General Conditions | 208 | 2024-01-04 | 2024-10-21 | 88392.48 | 424.9638 | 98999.5776 | 475.9595 | 106 | Multifamily | 2024-01-04 | 2024-10-21 | 824996.48 | 989699.0176 | 106 | 2024-01-04 | 1 | 424.9638 | 475.9595 | 424.9638 | 475.9595
106 | Multifamily | 1.2 | Existing Conditions | 38 | 2024-01-09 | 2024-02-29 | 141044 | 3711.6842 | 155148.4 | 4082.8526 | 107 | Condominium | 2024-02-18 | 2025-01-09 | 636049.98 | 752381.6766 | 106 | 2024-01-05 | 2 | 424.9638 | 475.9595 | 849.9277 | 951.919
106 | Multifamily | 1.4 | Woods, Plastics, Composites | 69 | 2024-02-29 | 2024-06-04 | 119476 | 1731.5362 | 137397.4 | 1991.2667 | 109 | Condominium | 2024-04-12 | 2024-11-07 | 387820.16 | 445760.336 | 106 | 2024-01-06 | 3 | 0 | 0 | 849.9277 | 951.919
106 | Multifamily | 1.5 | Thermal & Moisture | 29 | 2024-05-15 | 2024-06-24 | 107884 | 3720.1379 | 130539.64 | 4501.3669 | 110 | Commercial | 2024-02-27 | 2024-10-18 | 887718.96 | 1057522.3312 | 106 | 2024-01-07 | 4 | 0 | 0 | 849.9277 | 951.919
106 | Multifamily | 1.6 | Finishes | 100 | 2024-05-25 | 2024-10-11 | 368200 | 3682 | 467614 | 4676.14 | 111 | Multifamily | 2024-04-11 | 2025-04-06 | 1123704.06 | 1316252.5272 | 106 | 2024-01-08 | 5 | 424.9638 | 475.9595 | 1274.8915 | 1427.8785
107 | Condominium | 1.1 | General Conditions | 234 | 2024-02-18 | 2025-01-09 | 63031.98 | 269.3674 | 73747.4166 | 315.1599 | 112 | Commercial | 2024-05-01 | 2024-12-13 | 879255.3 | 1056729.681 | 106 | 2024-01-09 | 6 | 4136.6481 | 4558.8121 | 5411.5396 | 5986.6907
107 | Condominium | 1.2 | Existing Conditions | 37 | 2024-02-23 | 2024-04-15 | 50364 | 1361.1892 | 55904.04 | 1510.92 | 113 | Commercial | 2024-04-16 | 2024-11-01 | 699377.8 | 867131.448 | 106 | 2024-01-10 | 7 | 4136.6481 | 4558.8121 | 9548.1877 | 10545.5028
107 | Condominium | 1.4 | Woods, Plastics, Composites | 67 | 2024-04-15 | 2024-07-16 | 140580 | 2098.209 | 157449.6 | 2349.994 | 114 | Condominium | 2024-05-30 | 2025-04-06 | 623136.8 | 718659.76 | 106 | 2024-01-11 | 8 | 4136.6481 | 4558.8121 | 13684.8357 | 15104.3149
107 | Condominium | 1.5 | Thermal & Moisture | 35 | 2024-06-26 | 2024-08-13 | 84966 | 2427.6 | 102808.86 | 2937.396 | 115 | Multifamily | 2024-06-05 | 2025-03-22 | 732735.42 | 868188.8466 | 106 | 2024-01-12 | 9 | 4136.6481 | 4558.8121 | 17821.4838 | 19663.1271
107 | Condominium | 1.6 | Finishes | 126 | 2024-07-06 | 2024-12-30 | 297108 | 2358 | 362471.76 | 2876.76 | 116 | Multifamily | 2024-06-10 | 2025-06-29 | 1111050.06 | 1262688.6272 | 106 | 2024-01-13 | 10 | 0 | 0 | 17821.4838 | 19663.1271
109 | Condominium | 1.1 | General Conditions | 150 | 2024-04-12 | 2024-11-07 | 41552.16 | 277.0144 | 45707.376 | 304.7158 | 117 | Multifamily | 2024-06-18 | 2025-04-27 | 774416.66 | 937602.8254 | 106 | 2024-01-14 | 11 | 0 | 0 | 17821.4838 | 19663.1271
109 | Condominium | 1.2 | Existing Conditions | 14 | 2024-04-17 | 2024-05-06 | 19552 | 1396.5714 | 22875.84 | 1633.9886 | 118 | Condominium | 2024-07-30 | 2025-06-14 | 571019.52 | 687343.2892 | 106 | 2024-01-15 | 12 | 4136.6481 | 4558.8121 | 21958.1318 | 24221.9392
109 | Condominium | 1.4 | Woods, Plastics, Composites | 57 | 2024-05-06 | 2024-07-23 | 91392 | 1603.3684 | 105100.8 | 1843.8737 | 119 | Commercial | 2024-08-05 | 2025-04-13 | 1083561.92 | 1338449.0584 | 106 | 2024-01-16 | 13 | 4136.6481 | 4558.8121 | 26094.7799 | 28780.7514
109 | Condominium | 1.5 | Thermal & Moisture | 29 | 2024-07-03 | 2024-08-12 | 73444 | 2532.5517 | 94008.32 | 3241.6662 | 120 | Condominium | 2024-08-20 | 2025-08-16 | 753613.2 | 913030.408 | 106 | 2024-01-17 | 14 | 4136.6481 | 4558.8121 | 30231.4279 | 33339.5635
109 | Condominium | 1.6 | Finishes | 76 | 2024-07-13 | 2024-10-28 | 161880 | 2130 | 178068 | 2343 | 121 | Condominium | 2024-09-05 | 2025-05-18 | 938310.84 | 1137656.7668 | 106 | 2024-01-18 | 15 | 4136.6481 | 4558.8121 | 34368.076 | 37898.3756
110 | Commercial | 1.1 | General Conditions | 169 | 2024-02-27 | 2024-10-18 | 65756.96 | 389.0944 | 80223.4912 | 474.6952 | 122 | Multifamily | 2024-10-24 | 2025-08-22 | 805724.58 | 993993.4986 | 106 | 2024-01-19 | 16 | 4136.6481 | 4558.8121 | 38504.724 | 42457.1878
110 | Commercial | 1.2 | Existing Conditions | 14 | 2024-03-03 | 2024-03-21 | 48454 | 3461 | 58144.8 | 4153.2 | 123 | Multifamily | 2024-11-05 | 2025-10-02 | 1028007.68 | 1283393.4948 | 106 | 2024-01-20 | 17 | 0 | 0 | 38504.724 | 42457.1878
110 | Commercial | 1.4 | Woods, Plastics, Composites | 86 | 2024-03-21 | 2024-07-18 | 340680 | 3961.3953 | 419036.4 | 4872.5163 | 124 | Commercial | 2024-12-18 | 2025-10-12 | 1143549.12 | 1355866.7424 | 106 | 2024-01-21 | 18 | 0 | 0 | 38504.724 | 42457.1878
110 | Commercial | 1.5 | Thermal & Moisture | 25 | 2024-06-28 | 2024-08-01 | 118272 | 4730.88 | 138378.24 | 5535.1296 | [6 empty] | 106 | 2024-01-22 | 19 | 4136.6481 | 4558.8121 | 42641.3721 | 47015.9999
110 | Commercial | 1.6 | Finishes | 67 | 2024-07-08 | 2024-10-08 | 314556 | 4694.8657 | 361739.4 | 5399.0955 | [6 empty] | 106 | 2024-01-23 | 20 | 4136.6481 | 4558.8121 | 46778.0202 | 51574.8121
111 | Multifamily | 1.1 | General Conditions | 257 | 2024-04-11 | 2025-04-06 | 111358.06 | 433.2998 | 124721.0272 | 485.2958 | [6 empty] | 106 | 2024-01-24 | 21 | 4136.6481 | 4558.8121 | 50914.6682 | 56133.6242
111 | Multifamily | 1.2 | Existing Conditions | 23 | 2024-04-16 | 2024-05-16 | 43802 | 1904.4348 | 54314.48 | 2361.4991 | [6 empty] | 106 | 2024-01-25 | 22 | 4136.6481 | 4558.8121 | 55051.3163 | 60692.4363
111 | Multifamily | 1.4 | Woods, Plastics, Composites | 74 | 2024-05-16 | 2024-08-27 | 200823 | 2713.8243 | 251028.75 | 3392.2804 | [6 empty] | 106 | 2024-01-26 | 23 | 4136.6481 | 4558.8121 | 59187.9643 | 65251.2485
111 | Multifamily | 1.5 | Thermal & Moisture | 38 | 2024-08-07 | 2024-09-27 | 133311 | 3508.1842 | 169304.97 | 4455.3939 | [6 empty] | 106 | 2024-01-27 | 24 | 0 | 0 | 59187.9643 | 65251.2485
111 | Multifamily | 1.6 | Finishes | 159 | 2024-08-17 | 2025-03-27 | 634410 | 3990 | 716883.3 | 4508.7 | [6 empty] | 106 | 2024-01-28 | 25 | 0 | 0 | 59187.9643 | 65251.2485
112 | Commercial | 1.1 | General Conditions | 163 | 2024-05-01 | 2024-12-13 | 79932.3 | 490.3822 | 101514.021 | 622.7854 | [6 empty] | 106 | 2024-01-29 | 26 | 4136.6481 | 4558.8121 | 63324.6124 | 69810.0606
112 | Commercial | 1.2 | Existing Conditions | 18 | 2024-05-06 | 2024-05-29 | 82178 | 4565.4444 | 101900.72 | 5661.1511 | [6 empty] | 106 | 2024-01-30 | 27 | 4136.6481 | 4558.8121 | 67461.2604 | 74368.8728
112 | Commercial | 1.4 | Woods, Plastics, Composites | 44 | 2024-05-29 | 2024-07-29 | 113391 | 2577.0682 | 126997.92 | 2886.3164 | [6 empty] | 106 | 2024-01-31 | 28 | 4136.6481 | 4558.8121 | 71597.9085 | 78927.6849
112 | Commercial | 1.5 | Thermal & Moisture | 39 | 2024-07-09 | 2024-08-30 | 181222 | 4646.7179 | 219278.62 | 5622.5287 | [6 empty] | 106 | 2024-02-01 | 29 | 4136.6481 | 4558.8121 | 75734.5566 | 83486.497
112 | Commercial | 1.6 | Finishes | 98 | 2024-07-19 | 2024-12-03 | 422532 | 4311.551 | 507038.4 | 5173.8612 | [6 empty] | 106 | 2024-02-02 | 30 | 4136.6481 | 4558.8121 | 79871.2046 | 88045.3092
113 | Commercial | 1.1 | General Conditions | 144 | 2024-04-16 | 2024-11-01 | 63579.8 | 441.5264 | 80110.548 | 556.3233 | [6 empty] | 106 | 2024-02-03 | 31 | 0 | 0 | 79871.2046 | 88045.3092
113 | Commercial | 1.2 | Existing Conditions | 14 | 2024-04-21 | 2024-05-09 | 44240 | 3160 | 53088 | 3792 | [6 empty] | 106 | 2024-02-04 | 32 | 0 | 0 | 79871.2046 | 88045.3092
113 | Commercial | 1.4 | Woods, Plastics, Composites | 67 | 2024-05-09 | 2024-08-09 | 205854 | 3072.4478 | 253200.42 | 3779.1107 | [6 empty] | 106 | 2024-02-05 | 33 | 4136.6481 | 4558.8121 | 84007.8527 | 92604.1213
113 | Commercial | 1.5 | Thermal & Moisture | 21 | 2024-07-20 | 2024-08-19 | 81984 | 3904 | 104119.68 | 4958.08 | [6 empty] | 106 | 2024-02-06 | 34 | 4136.6481 | 4558.8121 | 88144.5007 | 97162.9334
113 | Commercial | 1.6 | Finishes | 61 | 2024-07-30 | 2024-10-22 | 303720 | 4979.0164 | 376612.8 | 6173.9803 | [6 empty] | 106 | 2024-02-07 | 35 | 4136.6481 | 4558.8121 | 92281.1488 | 101721.7456
114 | Condominium | 1.1 | General Conditions | 222 | 2024-05-30 | 2025-04-06 | 56648.8 | 255.1748 | 67978.56 | 306.2097 | [6 empty] | 106 | 2024-02-08 | 36 | 4136.6481 | 4558.8121 | 96417.7968 | 106280.5577
114 | Condominium | 1.2 | Existing Conditions | 11 | 2024-06-04 | 2024-06-18 | 15780 | 1434.5455 | 19093.8 | 1735.8 | [6 empty] | 106 | 2024-02-09 | 37 | 4136.6481 | 4558.8121 | 100554.4449 | 110839.3699
114 | Condominium | 1.4 | Woods, Plastics, Composites | 93 | 2024-06-18 | 2024-10-24 | 218224 | 2346.4946 | 244410.88 | 2628.074 | [6 empty] | 106 | 2024-02-10 | 38 | 0 | 0 | 100554.4449 | 110839.3699
114 | Condominium | 1.5 | Thermal & Moisture | 34 | 2024-10-04 | 2024-11-20 | 103092 | 3032.1176 | 116493.96 | 3426.2929 | [6 empty] | 106 | 2024-02-11 | 39 | 0 | 0 | 100554.4449 | 110839.3699
114 | Condominium | 1.6 | Finishes | 119 | 2024-10-14 | 2025-03-27 | 229392 | 1927.6639 | 270682.56 | 2274.6434 | [6 empty] | 106 | 2024-02-12 | 40 | 4136.6481 | 4558.8121 | 104691.093 | 115398.182
115 | Multifamily | 1.1 | General Conditions | 208 | 2024-06-05 | 2025-03-22 | 72613.42 | 349.103 | 89314.5066 | 429.3967 | [6 empty] | 106 | 2024-02-13 | 41 | 4136.6481 | 4558.8121 | 108827.741 | 119956.9941
115 | Multifamily | 1.2 | Existing Conditions | 22 | 2024-06-10 | 2024-07-09 | 67977 | 3089.8636 | 85651.02 | 3893.2282 | [6 empty] | 106 | 2024-02-14 | 42 | 4136.6481 | 4558.8121 | 112964.3891 | 124515.8063
115 | Multifamily | 1.4 | Woods, Plastics, Composites | 79 | 2024-07-09 | 2024-10-25 | 176436 | 2233.3671 | 224073.72 | 2836.3762 | [6 empty] | 106 | 2024-02-15 | 43 | 4136.6481 | 4558.8121 | 117101.0371 | 129074.6184
115 | Multifamily | 1.5 | Thermal & Moisture | 29 | 2024-10-05 | 2024-11-14 | 118697 | 4093 | 142436.4 | 4911.6 | [6 empty] | 106 | 2024-02-16 | 44 | 4136.6481 | 4558.8121 | 121237.6852 | 133633.4306
115 | Multifamily | 1.6 | Finishes | 107 | 2024-10-15 | 2025-03-12 | 297012 | 2775.8131 | 326713.2 | 3053.3944 | [6 empty] | 106 | 2024-02-17 | 45 | 0 | 0 | 121237.6852 | 133633.4306
116 | Multifamily | 1.1 | General Conditions | 275 | 2024-06-10 | 2025-06-29 | 110104.06 | 400.3784 | 123316.5472 | 448.4238 | [6 empty] | 106 | 2024-02-18 | 46 | 0 | 0 | 121237.6852 | 133633.4306
116 | Multifamily | 1.2 | Existing Conditions | 19 | 2024-06-15 | 2024-07-11 | 71934 | 3786 | 90636.84 | 4770.36 | [6 empty] | 106 | 2024-02-19 | 47 | 4136.6481 | 4558.8121 | 125374.3332 | 138192.2427
116 | Multifamily | 1.4 | Woods, Plastics, Composites | 99 | 2024-07-11 | 2024-11-26 | 339570 | 3430 | 380318.4 | 3841.6 | [6 empty] | 106 | 2024-02-20 | 48 | 4136.6481 | 4558.8121 | 129510.9813 | 142751.0548
116 | Multifamily | 1.5 | Thermal & Moisture | 30 | 2024-11-06 | 2024-12-17 | 117740 | 3924.6667 | 140110.6 | 4670.3533 | [6 empty] | 106 | 2024-02-21 | 49 | 4136.6481 | 4558.8121 | 133647.6294 | 147309.867
116 | Multifamily | 1.6 | Finishes | 154 | 2024-11-16 | 2025-06-19 | 471702 | 3063 | 528306.24 | 3430.56 | [6 empty] | 106 | 2024-02-22 | 50 | 4136.6481 | 4558.8121 | 137784.2774 | 151868.6791
117 | Multifamily | 1.1 | General Conditions | 224 | 2024-06-18 | 2025-04-27 | 63942.66 | 285.4583 | 76091.7654 | 339.6954 | [6 empty] | 106 | 2024-02-23 | 51 | 4136.6481 | 4558.8121 | 141920.9255 | 156427.4913
117 | Multifamily | 1.2 | Existing Conditions | 30 | 2024-06-23 | 2024-08-02 | 63120 | 2104 | 74481.6 | 2482.72 | [6 empty] | 106 | 2024-02-24 | 52 | 0 | 0 | 141920.9255 | 156427.4913
117 | Multifamily | 1.4 | Woods, Plastics, Composites | 99 | 2024-08-02 | 2024-12-18 | 158858 | 1604.6263 | 179509.54 | 1813.2277 | [6 empty] | 106 | 2024-02-25 | 53 | 0 | 0 | 141920.9255 | 156427.4913
117 | Multifamily | 1.5 | Thermal & Moisture | 21 | 2024-11-28 | 2024-12-26 | 85800 | 4085.7143 | 96096 | 4576 | [6 empty] | 106 | 2024-02-26 | 54 | 4136.6481 | 4558.8121 | 146057.5735 | 160986.3034
117 | Multifamily | 1.6 | Finishes | 94 | 2024-12-08 | 2025-04-17 | 402696 | 4284 | 511423.92 | 5440.68 | [6 empty] | 106 | 2024-02-27 | 55 | 4136.6481 | 4558.8121 | 150194.2216 | 165545.1155
118 | Condominium | 1.1 | General Conditions | 229 | 2024-07-30 | 2025-06-14 | 56587.52 | 247.1071 | 68470.8992 | 298.9996 | [6 empty] | 106 | 2024-02-28 | 56 | 4136.6481 | 4558.8121 | 154330.8696 | 170103.9277
118 | Condominium | 1.2 | Existing Conditions | 39 | 2024-08-04 | 2024-09-26 | 38571 | 989 | 48985.17 | 1256.03 | [6 empty] | 106 | 2024-02-29 | 57 | 5868.1843 | 6550.0788 | 160199.0539 | 176654.0065
118 | Condominium | 1.4 | Woods, Plastics, Composites | 60 | 2024-09-26 | 2024-12-18 | 123487 | 2058.1167 | 158063.36 | 2634.3893 | [6 empty] | 106 | 2024-03-01 | 58 | 2156.5001 | 2467.2262 | 162355.554 | 179121.2327
118 | Condominium | 1.5 | Thermal & Moisture | 39 | 2024-11-28 | 2025-01-21 | 82422 | 2113.3846 | 101379.06 | 2599.4631 | [6 empty] | 106 | 2024-03-02 | 59 | 0 | 0 | 162355.554 | 179121.2327
118 | Condominium | 1.6 | Finishes | 128 | 2024-12-08 | 2025-06-04 | 269952 | 2109 | 310444.8 | 2425.35 | [6 empty] | 106 | 2024-03-03 | 60 | 0 | 0 | 162355.554 | 179121.2327
119 | Commercial | 1.1 | General Conditions | 180 | 2024-08-05 | 2025-04-13 | 116095.92 | 644.9773 | 147441.8184 | 819.1212 | [6 empty] | 106 | 2024-03-04 | 61 | 2156.5001 | 2467.2262 | 164512.0541 | 181588.4588
119 | Commercial | 1.2 | Existing Conditions | 24 | 2024-08-10 | 2024-09-12 | 121128 | 5047 | 147776.16 | 6157.34 | [6 empty] | 106 | 2024-03-05 | 62 | 2156.5001 | 2467.2262 | 166668.5542 | 184055.685
119 | Commercial | 1.4 | Woods, Plastics, Composites | 43 | 2024-09-12 | 2024-11-11 | 126714 | 2946.8372 | 144453.96 | 3359.3944 | [6 empty] | 106 | 2024-03-06 | 63 | 2156.5001 | 2467.2262 | 168825.0542 | 186522.9112
119 | Commercial | 1.5 | Thermal & Moisture | 30 | 2024-10-22 | 2024-12-02 | 139635 | 4654.5 | 156391.2 | 5213.04 | [6 empty] | 106 | 2024-03-07 | 64 | 2156.5001 | 2467.2262 | 170981.5543 | 188990.1374
119 | Commercial | 1.6 | Finishes | 110 | 2024-11-01 | 2025-04-03 | 579989 | 5272.6273 | 742385.92 | 6748.9629 | [6 empty] | 106 | 2024-03-08 | 65 | 2156.5001 | 2467.2262 | 173138.0544 | 191457.3635
120 | Condominium | 1.1 | General Conditions | 259 | 2024-08-20 | 2025-08-16 | 55823.2 | 215.5336 | 66429.608 | 256.485 | [6 empty] | 106 | 2024-03-09 | 66 | 0 | 0 | 173138.0544 | 191457.3635
120 | Condominium | 1.2 | Existing Conditions | 15 | 2024-08-25 | 2024-09-13 | 25485 | 1699 | 28543.2 | 1902.88 | [6 empty] | 106 | 2024-03-10 | 67 | 0 | 0 | 173138.0544 | 191457.3635
120 | Condominium | 1.4 | Woods, Plastics, Composites | 116 | 2024-09-13 | 2025-02-21 | 284395 | 2451.681 | 324210.3 | 2794.9164 | [6 empty] | 106 | 2024-03-11 | 68 | 2156.5001 | 2467.2262 | 175294.5545 | 193924.5897
120 | Condominium | 1.5 | Thermal & Moisture | 40 | 2025-02-01 | 2025-03-28 | 120160 | 3004 | 153804.8 | 3845.12 | [6 empty] | 106 | 2024-03-12 | 69 | 2156.5001 | 2467.2262 | 177451.0545 | 196391.8159
120 | Condominium | 1.6 | Finishes | 127 | 2025-02-11 | 2025-08-06 | 267750 | 2108.2677 | 340042.5 | 2677.5 | [6 empty] | 106 | 2024-03-13 | 70 | 2156.5001 | 2467.2262 | 179607.5546 | 198859.0421
121 | Condominium | 1.1 | General Conditions | 158 | 2024-09-05 | 2025-04-14 | 34839.84 | 220.5053 | 44246.5968 | 280.0418 | [6 empty] | 106 | 2024-03-14 | 71 | 2156.5001 | 2467.2262 | 181764.0547 | 201326.2682
121 | Condominium | 1.2 | Existing Conditions | 11 | 2024-09-10 | 2024-09-24 | 14200 | 1290.9091 | 16898 | 1536.1818 | [6 empty] | 106 | 2024-03-15 | 72 | 2156.5001 | 2467.2262 | 183920.5548 | 203793.4944
121 | Condominium | 1.4 | Woods, Plastics, Composites | 69 | 2024-09-24 | 2024-12-27 | 164356 | 2381.971 | 192296.52 | 2786.9061 | [6 empty] | 106 | 2024-03-16 | 73 | 0 | 0 | 183920.5548 | 203793.4944
121 | Condominium | 1.5 | Thermal & Moisture | 38 | 2024-12-07 | 2025-01-29 | 119662 | 3149 | 132824.82 | 3495.39 | [6 empty] | 106 | 2024-03-17 | 74 | 0 | 0 | 183920.5548 | 203793.4944
121 | Condominium | 1.6 | Finishes | 79 | 2024-12-17 | 2025-04-04 | 137280 | 1737.7215 | 172972.8 | 2189.5291 | [6 empty] | 106 | 2024-03-18 | 75 | 2156.5001 | 2467.2262 | 186077.0549 | 206260.7206
121 | Condominium | 1.1 | General Conditions | 175 | 2024-09-15 | 2025-05-18 | 42543 | 243.1029 | 51477.03 | 294.1545 | [6 empty] | 106 | 2024-03-19 | 76 | 2156.5001 | 2467.2262 | 188233.5549 | 208727.9467
121 | Condominium | 1.2 | Existing Conditions | 41 | 2024-09-20 | 2024-11-15 | 63720 | 1554.1463 | 80287.2 | 1958.2244 | [6 empty] | 106 | 2024-03-20 | 77 | 2156.5001 | 2467.2262 | 190390.055 | 211195.1729
121 | Condominium | 1.4 | Woods, Plastics, Composites | 46 | 2024-11-15 | 2025-01-17 | 97830 | 2126.7391 | 111526.2 | 2424.4826 | [6 empty] | 106 | 2024-03-21 | 78 | 2156.5001 | 2467.2262 | 192546.5551 | 213662.3991
121 | Condominium | 1.5 | Thermal & Moisture | 25 | 2024-12-28 | 2025-01-31 | 55950 | 2238 | 71056.5 | 2842.26 | [6 empty] | 106 | 2024-03-22 | 79 | 2156.5001 | 2467.2262 | 194703.0552 | 216129.6253
121 | Condominium | 1.6 | Finishes | 88 | 2025-01-07 | 2025-05-08 | 207930 | 2362.8409 | 264071.1 | 3000.808 | [6 empty] | 106 | 2024-03-23 | 80 | 0 | 0 | 194703.0552 | 216129.6253
122 | Multifamily | 1.1 | General Conditions | 217 | 2024-10-24 | 2025-08-22 | 79846.58 | 367.9566 | 93420.4986 | 430.5092 | [6 empty] | 106 | 2024-03-24 | 81 | 0 | 0 | 194703.0552 | 216129.6253
122 | Multifamily | 1.2 | Existing Conditions | 35 | 2024-10-29 | 2024-12-16 | 73712 | 2106.0571 | 94351.36 | 2695.7531 | [6 empty] | 106 | 2024-03-25 | 82 | 2156.5001 | 2467.2262 | 196859.5553 | 218596.8514
122 | Multifamily | 1.4 | Woods, Plastics, Composites | 72 | 2024-12-16 | 2025-03-25 | 120487 | 1673.4306 | 150608.75 | 2091.7882 | [6 empty] | 106 | 2024-03-26 | 83 | 2156.5001 | 2467.2262 | 199016.0553 | 221064.0776
122 | Multifamily | 1.5 | Thermal & Moisture | 24 | 2025-03-05 | 2025-04-07 | 82386 | 3432.75 | 102982.5 | 4290.9375 | [6 empty] | 106 | 2024-03-27 | 84 | 2156.5001 | 2467.2262 | 201172.5554 | 223531.3038
122 | Multifamily | 1.6 | Finishes | 107 | 2025-03-15 | 2025-08-12 | 449293 | 4199 | 552630.39 | 5164.77 | [6 empty] | 106 | 2024-03-28 | 85 | 2156.5001 | 2467.2262 | 203329.0555 | 225998.53
123 | Multifamily | 1.1 | General Conditions | 238 | 2024-11-05 | 2025-10-02 | 110143.68 | 462.7886 | 122259.4848 | 513.6953 | [6 empty] | 106 | 2024-03-29 | 86 | 2156.5001 | 2467.2262 | 205485.5556 | 228465.7561
123 | Multifamily | 1.2 | Existing Conditions | 24 | 2024-11-10 | 2024-12-12 | 74952 | 3123 | 83196.72 | 3466.53 | [6 empty] | 106 | 2024-03-30 | 87 | 0 | 0 | 205485.5556 | 228465.7561
123 | Multifamily | 1.4 | Woods, Plastics, Composites | 89 | 2024-12-12 | 2025-04-15 | 162536 | 1826.2472 | 195043.2 | 2191.4966 | [6 empty] | 106 | 2024-03-31 | 88 | 0 | 0 | 205485.5556 | 228465.7561
123 | Multifamily | 1.5 | Thermal & Moisture | 40 | 2025-03-26 | 2025-05-20 | 159471 | 3986.775 | 205717.59 | 5142.9397 | [6 empty] | 106 | 2024-04-01 | 89 | 2156.5001 | 2467.2262 | 207642.0556 | 230932.9823
123 | Multifamily | 1.6 | Finishes | 121 | 2025-04-05 | 2025-09-22 | 520905 | 4305 | 677176.5 | 5596.5 | [6 empty] | 106 | 2024-04-02 | 90 | 2156.5001 | 2467.2262 | 209798.5557 | 233400.2085
124 | Commercial | 1.1 | General Conditions | 213 | 2024-12-18 | 2025-10-12 | 122523.12 | 575.2259 | 155604.3624 | 730.5369 | [6 empty] | 106 | 2024-04-03 | 91 | 2156.5001 | 2467.2262 | 211955.0558 | 235867.4347
124 | Commercial | 1.2 | Existing Conditions | 25 | 2024-12-23 | 2025-01-24 | 70656 | 2826.24 | 88320 | 3532.8 | [6 empty] | 106 | 2024-04-04 | 92 | 2156.5001 | 2467.2262 | 214111.5559 | 238334.6608
124 | Commercial | 1.4 | Woods, Plastics, Composites | 57 | 2025-01-24 | 2025-04-14 | 146664 | 2573.0526 | 186263.28 | 3267.7768 | [6 empty] | 106 | 2024-04-05 | 93 | 2156.5001 | 2467.2262 | 216268.056 | 240801.887
124 | Commercial | 1.5 | Thermal & Moisture | 24 | 2025-03-25 | 2025-04-25 | 110331 | 4597.125 | 121364.1 | 5056.8375 | [6 empty] | 106 | 2024-04-06 | 94 | 0 | 0 | 216268.056 | 240801.887
124 | Commercial | 1.6 | Finishes | 130 | 2025-04-04 | 2025-10-02 | 693375 | 5333.6538 | 804315 | 6187.0385 | [6 empty] | 106 | 2024-04-07 | 95 | 0 | 0 | 216268.056 | 240801.887
[17 empty] | 106 | 2024-04-08 | 96 | 2156.5001 | 2467.2262 | 218424.556 | 243269.1132
[17 empty] | 106 | 2024-04-09 | 97 | 2156.5001 | 2467.2262 | 220581.0561 | 245736.3394
[17 empty] | 106 | 2024-04-10 | 98 | 2156.5001 | 2467.2262 | 222737.5562 | 248203.5655
[17 empty] | 106 | 2024-04-11 | 99 | 2156.5001 | 2467.2262 | 224894.0563 | 250670.7917
[17 empty] | 106 | 2024-04-12 | 100 | 2156.5001 | 2467.2262 | 227050.5563 | 253138.0179
[17 empty] | 106 | 2024-04-13 | 101 | 0 | 0 | 227050.5563 | 253138.0179
[17 empty] | 106 | 2024-04-14 | 102 | 0 | 0 | 227050.5563 | 253138.0179
[17 empty] | 106 | 2024-04-15 | 103 | 2156.5001 | 2467.2262 | 229207.0564 | 255605.2441
[17 empty] | 106 | 2024-04-16 | 104 | 2156.5001 | 2467.2262 | 231363.5565 | 258072.4702
[17 empty] | 106 | 2024-04-17 | 105 | 2156.5001 | 2467.2262 | 233520.0566 | 260539.6964
[17 empty] | 106 | 2024-04-18 | 106 | 2156.5001 | 2467.2262 | 235676.5567 | 263006.9226
[17 empty] | 106 | 2024-04-19 | 107 | 2156.5001 | 2467.2262 | 237833.0567 | 265474.1488
[17 empty] | 106 | 2024-04-20 | 108 | 0 | 0 | 237833.0567 | 265474.1488
[17 empty] | 106 | 2024-04-21 | 109 | 0 | 0 | 237833.0567 | 265474.1488
[17 empty] | 106 | 2024-04-22 | 110 | 2156.5001 | 2467.2262 | 239989.5568 | 267941.3749
[17 empty] | 106 | 2024-04-23 | 111 | 2156.5001 | 2467.2262 | 242146.0569 | 270408.6011
[17 empty] | 106 | 2024-04-24 | 112 | 2156.5001 | 2467.2262 | 244302.557 | 272875.8273
[17 empty] | 106 | 2024-04-25 | 113 | 2156.5001 | 2467.2262 | 246459.057 | 275343.0535
[17 empty] | 106 | 2024-04-26 | 114 | 2156.5001 | 2467.2262 | 248615.5571 | 277810.2796
[17 empty] | 106 | 2024-04-27 | 115 | 0 | 0 | 248615.5571 | 277810.2796
[17 empty] | 106 | 2024-04-28 | 116 | 0 | 0 | 248615.5571 | 277810.2796
[17 empty] | 106 | 2024-04-29 | 117 | 2156.5001 | 2467.2262 | 250772.0572 | 280277.5058
[17 empty] | 106 | 2024-04-30 | 118 | 2156.5001 | 2467.2262 | 252928.5573 | 282744.732
[17 empty] | 106 | 2024-05-01 | 119 | 2156.5001 | 2467.2262 | 255085.0574 | 285211.9582
[17 empty] | 106 | 2024-05-02 | 120 | 2156.5001 | 2467.2262 | 257241.5574 | 287679.1843
[17 empty] | 106 | 2024-05-03 | 121 | 2156.5001 | 2467.2262 | 259398.0575 | 290146.4105
[17 empty] | 106 | 2024-05-04 | 122 | 0 | 0 | 259398.0575 | 290146.4105
[17 empty] | 106 | 2024-05-05 | 123 | 0 | 0 | 259398.0575 | 290146.4105
[17 empty] | 106 | 2024-05-06 | 124 | 2156.5001 | 2467.2262 | 261554.5576 | 292613.6367
[17 empty] | 106 | 2024-05-07 | 125 | 2156.5001 | 2467.2262 | 263711.0577 | 295080.8629
[17 empty] | 106 | 2024-05-08 | 126 | 2156.5001 | 2467.2262 | 265867.5577 | 297548.089
[17 empty] | 106 | 2024-05-09 | 127 | 2156.5001 | 2467.2262 | 268024.0578 | 300015.3152
[17 empty] | 106 | 2024-05-10 | 128 | 2156.5001 | 2467.2262 | 270180.5579 | 302482.5414
[17 empty] | 106 | 2024-05-11 | 129 | 0 | 0 | 270180.5579 | 302482.5414
[17 empty] | 106 | 2024-05-12 | 130 | 0 | 0 | 270180.5579 | 302482.5414
[17 empty] | 106 | 2024-05-13 | 131 | 2156.5001 | 2467.2262 | 272337.058 | 304949.7675
[17 empty] | 106 | 2024-05-14 | 132 | 2156.5001 | 2467.2262 | 274493.5581 | 307416.9937
[17 empty] | 106 | 2024-05-15 | 133 | 5876.638 | 6968.5931 | 280370.1961 | 314385.5868
[17 empty] | 106 | 2024-05-16 | 134 | 5876.638 | 6968.5931 | 286246.8341 | 321354.1799
[17 empty] | 106 | 2024-05-17 | 135 | 5876.638 | 6968.5931 | 292123.4721 | 328322.7729
[17 empty] | 106 | 2024-05-18 | 136 | 0 | 0 | 292123.4721 | 328322.7729
[17 empty] | 106 | 2024-05-19 | 137 | 0 | 0 | 292123.4721 | 328322.7729
[17 empty] | 106 | 2024-05-20 | 138 | 5876.638 | 6968.5931 | 298000.1101 | 335291.366
[17 empty] | 106 | 2024-05-21 | 139 | 5876.638 | 6968.5931 | 303876.7481 | 342259.9591
[17 empty] | 106 | 2024-05-22 | 140 | 5876.638 | 6968.5931 | 309753.3861 | 349228.5521
[17 empty] | 106 | 2024-05-23 | 141 | 5876.638 | 6968.5931 | 315630.0241 | 356197.1452
[17 empty] | 106 | 2024-05-24 | 142 | 5876.638 | 6968.5931 | 321506.6621 | 363165.7383
[17 empty] | 106 | 2024-05-25 | 143 | 0 | 0 | 321506.6621 | 363165.7383
[17 empty] | 106 | 2024-05-26 | 144 | 0 | 0 | 321506.6621 | 363165.7383
[17 empty] | 106 | 2024-05-27 | 145 | 9558.638 | 11644.7331 | 331065.3001 | 374810.4714
[17 empty] | 106 | 2024-05-28 | 146 | 9558.638 | 11644.7331 | 340623.9382 | 386455.2044
[17 empty] | 106 | 2024-05-29 | 147 | 9558.638 | 11644.7331 | 350182.5762 | 398099.9375
[17 empty] | 106 | 2024-05-30 | 148 | 9558.638 | 11644.7331 | 359741.2142 | 409744.6706
[17 empty] | 106 | 2024-05-31 | 149 | 9558.638 | 11644.7331 | 369299.8522 | 421389.4036
[17 empty] | 106 | 2024-06-01 | 150 | 0 | 0 | 369299.8522 | 421389.4036
[17 empty] | 106 | 2024-06-02 | 151 | 0 | 0 | 369299.8522 | 421389.4036
[17 empty] | 106 | 2024-06-03 | 152 | 9558.638 | 11644.7331 | 378858.4902 | 433034.1367
[17 empty] | 106 | 2024-06-04 | 153 | 9558.638 | 11644.7331 | 388417.1282 | 444678.8698
[17 empty] | 106 | 2024-06-05 | 154 | 7827.1018 | 9653.4664 | 396244.23 | 454332.3362
[17 empty] | 106 | 2024-06-06 | 155 | 7827.1018 | 9653.4664 | 404071.3318 | 463985.8026
[17 empty] | 106 | 2024-06-07 | 156 | 7827.1018 | 9653.4664 | 411898.4335 | 473639.269
[17 empty] | 106 | 2024-06-08 | 157 | 0 | 0 | 411898.4335 | 473639.269
[17 empty] | 106 | 2024-06-09 | 158 | 0 | 0 | 411898.4335 | 473639.269
[17 empty] | 106 | 2024-06-10 | 159 | 7827.1018 | 9653.4664 | 419725.5353 | 483292.7354
[17 empty] | 106 | 2024-06-11 | 160 | 7827.1018 | 9653.4664 | 427552.6371 | 492946.2018
[17 empty] | 106 | 2024-06-12 | 161 | 7827.1018 | 9653.4664 | 435379.7389 | 502599.6682
[17 empty] | 106 | 2024-06-13 | 162 | 7827.1018 | 9653.4664 | 443206.8406 | 512253.1346
[17 empty] | 106 | 2024-06-14 | 163 | 7827.1018 | 9653.4664 | 451033.9424 | 521906.601
[17 empty] | 106 | 2024-06-15 | 164 | 0 | 0 | 451033.9424 | 521906.601
[17 empty] | 106 | 2024-06-16 | 165 | 0 | 0 | 451033.9424 | 521906.601
[17 empty] | 106 | 2024-06-17 | 166 | 7827.1018 | 9653.4664 | 458861.0442 | 531560.0674
[17 empty] | 106 | 2024-06-18 | 167 | 7827.1018 | 9653.4664 | 466688.146 | 541213.5338
[17 empty] | 106 | 2024-06-19 | 168 | 7827.1018 | 9653.4664 | 474515.2477 | 550867.0002
[17 empty] | 106 | 2024-06-20 | 169 | 7827.1018 | 9653.4664 | 482342.3495 | 560520.4666
[17 empty] | 106 | 2024-06-21 | 170 | 7827.1018 | 9653.4664 | 490169.4513 | 570173.933
[17 empty] | 106 | 2024-06-22 | 171 | 0 | 0 | 490169.4513 | 570173.933
[17 empty] | 106 | 2024-06-23 | 172 | 0 | 0 | 490169.4513 | 570173.933
[17 empty] | 106 | 2024-06-24 | 173 | 7827.1018 | 9653.4664 | 497996.5531 | 579827.3994
[17 empty] | 106 | 2024-06-25 | 174 | 4106.9638 | 5152.0995 | 502103.5169 | 584979.499
[17 empty] | 106 | 2024-06-26 | 175 | 4106.9638 | 5152.0995 | 506210.4808 | 590131.5985
[17 empty] | 106 | 2024-06-27 | 176 | 4106.9638 | 5152.0995 | 510317.4446 | 595283.698
[17 empty] | 106 | 2024-06-28 | 177 | 4106.9638 | 5152.0995 | 514424.4085 | 600435.7975
[17 empty] | 106 | 2024-06-29 | 178 | 0 | 0 | 514424.4085 | 600435.7975
[17 empty] | 106 | 2024-06-30 | 179 | 0 | 0 | 514424.4085 | 600435.7975
[17 empty] | 106 | 2024-07-01 | 180 | 4106.9638 | 5152.0995 | 518531.3723 | 605587.897
[17 empty] | 106 | 2024-07-02 | 181 | 4106.9638 | 5152.0995 | 522638.3362 | 610739.9965
[17 empty] | 106 | 2024-07-03 | 182 | 4106.9638 | 5152.0995 | 526745.3 | 615892.096
[17 empty] | 106 | 2024-07-04 | 183 | 4106.9638 | 5152.0995 | 530852.2638 | 621044.1955
[17 empty] | 106 | 2024-07-05 | 184 | 4106.9638 | 5152.0995 | 534959.2277 | 626196.295
[17 empty] | 106 | 2024-07-06 | 185 | 0 | 0 | 534959.2277 | 626196.295
[17 empty] | 106 | 2024-07-07 | 186 | 0 | 0 | 534959.2277 | 626196.295
[17 empty] | 106 | 2024-07-08 | 187 | 4106.9638 | 5152.0995 | 539066.1915 | 631348.3945
[17 empty] | 106 | 2024-07-09 | 188 | 4106.9638 | 5152.0995 | 543173.1554 | 636500.494
[17 empty] | 106 | 2024-07-10 | 189 | 4106.9638 | 5152.0995 | 547280.1192 | 641652.5935
[17 empty] | 106 | 2024-07-11 | 190 | 4106.9638 | 5152.0995 | 551387.0831 | 646804.693
[17 empty] | 106 | 2024-07-12 | 191 | 4106.9638 | 5152.0995 | 555494.0469 | 651956.7926
[17 empty] | 106 | 2024-07-13 | 192 | 0 | 0 | 555494.0469 | 651956.7926
[17 empty] | 106 | 2024-07-14 | 193 | 0 | 0 | 555494.0469 | 651956.7926
[17 empty] | 106 | 2024-07-15 | 194 | 4106.9638 | 5152.0995 | 559601.0108 | 657108.8921
[17 empty] | 106 | 2024-07-16 | 195 | 4106.9638 | 5152.0995 | 563707.9746 | 662260.9916
[17 empty] | 106 | 2024-07-17 | 196 | 4106.9638 | 5152.0995 | 567814.9385 | 667413.0911
[17 empty] | 106 | 2024-07-18 | 197 | 4106.9638 | 5152.0995 | 571921.9023 | 672565.1906
[17 empty] | 106 | 2024-07-19 | 198 | 4106.9638 | 5152.0995 | 576028.8662 | 677717.2901
[17 empty] | 106 | 2024-07-20 | 199 | 0 | 0 | 576028.8662 | 677717.2901
[17 empty] | 106 | 2024-07-21 | 200 | 0 | 0 | 576028.8662 | 677717.2901
[17 empty] | 106 | 2024-07-22 | 201 | 4106.9638 | 5152.0995 | 580135.83 | 682869.3896
[17 empty] | 106 | 2024-07-23 | 202 | 4106.9638 | 5152.0995 | 584242.7938 | 688021.4891
[17 empty] | 106 | 2024-07-24 | 203 | 4106.9638 | 5152.0995 | 588349.7577 | 693173.5886
[17 empty] | 106 | 2024-07-25 | 204 | 4106.9638 | 5152.0995 | 592456.7215 | 698325.6881
[17 empty] | 106 | 2024-07-26 | 205 | 4106.9638 | 5152.0995 | 596563.6854 | 703477.7876
[17 empty] | 106 | 2024-07-27 | 206 | 0 | 0 | 596563.6854 | 703477.7876
[17 empty] | 106 | 2024-07-28 | 207 | 0 | 0 | 596563.6854 | 703477.7876
[17 empty] | 106 | 2024-07-29 | 208 | 4106.9638 | 5152.0995 | 600670.6492 | 708629.8871
[17 empty] | 106 | 2024-07-30 | 209 | 4106.9638 | 5152.0995 | 604777.6131 | 713781.9866
[17 empty] | 106 | 2024-07-31 | 210 | 4106.9638 | 5152.0995 | 608884.5769 | 718934.0862
[17 empty] | 106 | 2024-08-01 | 211 | 4106.9638 | 5152.0995 | 612991.5408 | 724086.1857
[17 empty] | 106 | 2024-08-02 | 212 | 4106.9638 | 5152.0995 | 617098.5046 | 729238.2852
[17 empty] | 106 | 2024-08-03 | 213 | 0 | 0 | 617098.5046 | 729238.2852
[17 empty] | 106 | 2024-08-04 | 214 | 0 | 0 | 617098.5046 | 729238.2852
[17 empty] | 106 | 2024-08-05 | 215 | 4106.9638 | 5152.0995 | 621205.4685 | 734390.3847
[17 empty] | 106 | 2024-08-06 | 216 | 4106.9638 | 5152.0995 | 625312.4323 | 739542.4842
[17 empty] | 106 | 2024-08-07 | 217 | 4106.9638 | 5152.0995 | 629419.3962 | 744694.5837
[17 empty] | 106 | 2024-08-08 | 218 | 4106.9638 | 5152.0995 | 633526.36 | 749846.6832
[17 empty] | 106 | 2024-08-09 | 219 | 4106.9638 | 5152.0995 | 637633.3238 | 754998.7827
[17 empty] | 106 | 2024-08-10 | 220 | 0 | 0 | 637633.3238 | 754998.7827
[17 empty] | 106 | 2024-08-11 | 221 | 0 | 0 | 637633.3238 | 754998.7827
[17 empty] | 106 | 2024-08-12 | 222 | 4106.9638 | 5152.0995 | 641740.2877 | 760150.8822
[17 empty] | 106 | 2024-08-13 | 223 | 4106.9638 | 5152.0995 | 645847.2515 | 765302.9817
[17 empty] | 106 | 2024-08-14 | 224 | 4106.9638 | 5152.0995 | 649954.2154 | 770455.0812
[17 empty] | 106 | 2024-08-15 | 225 | 4106.9638 | 5152.0995 | 654061.1792 | 775607.1807
[17 empty] | 106 | 2024-08-16 | 226 | 4106.9638 | 5152.0995 | 658168.1431 | 780759.2802
[17 empty] | 106 | 2024-08-17 | 227 | 0 | 0 | 658168.1431 | 780759.2802
[17 empty] | 106 | 2024-08-18 | 228 | 0 | 0 | 658168.1431 | 780759.2802
[17 empty] | 106 | 2024-08-19 | 229 | 4106.9638 | 5152.0995 | 662275.1069 | 785911.3798
[17 empty] | 106 | 2024-08-20 | 230 | 4106.9638 | 5152.0995 | 666382.0708 | 791063.4793
[17 empty] | 106 | 2024-08-21 | 231 | 4106.9638 | 5152.0995 | 670489.0346 | 796215.5788
[17 empty] | 106 | 2024-08-22 | 232 | 4106.9638 | 5152.0995 | 674595.9985 | 801367.6783
[17 empty] | 106 | 2024-08-23 | 233 | 4106.9638 | 5152.0995 | 678702.9623 | 806519.7778
[17 empty] | 106 | 2024-08-24 | 234 | 0 | 0 | 678702.9623 | 806519.7778
[17 empty] | 106 | 2024-08-25 | 235 | 0 | 0 | 678702.9623 | 806519.7778
[17 empty] | 106 | 2024-08-26 | 236 | 4106.9638 | 5152.0995 | 682809.9262 | 811671.8773
[17 empty] | 106 | 2024-08-27 | 237 | 4106.9638 | 5152.0995 | 686916.89 | 816823.9768
[17 empty] | 106 | 2024-08-28 | 238 | 4106.9638 | 5152.0995 | 691023.8538 | 821976.0763
[17 empty] | 106 | 2024-08-29 | 239 | 4106.9638 | 5152.0995 | 695130.8177 | 827128.1758
[17 empty] | 106 | 2024-08-30 | 240 | 4106.9638 | 5152.0995 | 699237.7815 | 832280.2753
[17 empty] | 106 | 2024-08-31 | 241 | 0 | 0 | 699237.7815 | 832280.2753
[17 empty] | 106 | 2024-09-01 | 242 | 0 | 0 | 699237.7815 | 832280.2753
[17 empty] | 106 | 2024-09-02 | 243 | 4106.9638 | 5152.0995 | 703344.7454 | 837432.3748
[17 empty] | 106 | 2024-09-03 | 244 | 4106.9638 | 5152.0995 | 707451.7092 | 842584.4743
[17 empty] | 106 | 2024-09-04 | 245 | 4106.9638 | 5152.0995 | 711558.6731 | 847736.5738
[17 empty] | 106 | 2024-09-05 | 246 | 4106.9638 | 5152.0995 | 715665.6369 | 852888.6734
[17 empty] | 106 | 2024-09-06 | 247 | 4106.9638 | 5152.0995 | 719772.6008 | 858040.7729
[17 empty] | 106 | 2024-09-07 | 248 | 0 | 0 | 719772.6008 | 858040.7729
[17 empty] | 106 | 2024-09-08 | 249 | 0 | 0 | 719772.6008 | 858040.7729
[17 empty] | 106 | 2024-09-09 | 250 | 4106.9638 | 5152.0995 | 723879.5646 | 863192.8724
[17 empty] | 106 | 2024-09-10 | 251 | 4106.9638 | 5152.0995 | 727986.5285 | 868344.9719
[17 empty] | 106 | 2024-09-11 | 252 | 4106.9638 | 5152.0995 | 732093.4923 | 873497.0714
[17 empty] | 106 | 2024-09-12 | 253 | 4106.9638 | 5152.0995 | 736200.4562 | 878649.1709
[17 empty] | 106 | 2024-09-13 | 254 | 4106.9638 | 5152.0995 | 740307.42 | 883801.2704
[17 empty] | 106 | 2024-09-14 | 255 | 0 | 0 | 740307.42 | 883801.2704
[17 empty] | 106 | 2024-09-15 | 256 | 0 | 0 | 740307.42 | 883801.2704
[17 empty] | 106 | 2024-09-16 | 257 | 4106.9638 | 5152.0995 | 744414.3838 | 888953.3699
[17 empty] | 106 | 2024-09-17 | 258 | 4106.9638 | 5152.0995 | 748521.3477 | 894105.4694
[17 empty] | 106 | 2024-09-18 | 259 | 4106.9638 | 5152.0995 | 752628.3115 | 899257.5689
[17 empty] | 106 | 2024-09-19 | 260 | 4106.9638 | 5152.0995 | 756735.2754 | 904409.6684
[17 empty] | 106 | 2024-09-20 | 261 | 4106.9638 | 5152.0995 | 760842.2392 | 909561.7679
[17 empty] | 106 | 2024-09-21 | 262 | 0 | 0 | 760842.2392 | 909561.7679
[17 empty] | 106 | 2024-09-22 | 263 | 0 | 0 | 760842.2392 | 909561.7679
[17 empty] | 106 | 2024-09-23 | 264 | 4106.9638 | 5152.0995 | 764949.2031 | 914713.8674
[17 empty] | 106 | 2024-09-24 | 265 | 4106.9638 | 5152.0995 | 769056.1669 | 919865.967
[17 empty] | 106 | 2024-09-25 | 266 | 4106.9638 | 5152.0995 | 773163.1308 | 925018.0665
[17 empty] | 106 | 2024-09-26 | 267 | 4106.9638 | 5152.0995 | 777270.0946 | 930170.166
[17 empty] | 106 | 2024-09-27 | 268 | 4106.9638 | 5152.0995 | 781377.0585 | 935322.2655
[17 empty] | 106 | 2024-09-28 | 269 | 0 | 0 | 781377.0585 | 935322.2655
[17 empty] | 106 | 2024-09-29 | 270 | 0 | 0 | 781377.0585 | 935322.2655
[17 empty] | 106 | 2024-09-30 | 271 | 4106.9638 | 5152.0995 | 785484.0223 | 940474.365
[17 empty] | 106 | 2024-10-01 | 272 | 4106.9638 | 5152.0995 | 789590.9862 | 945626.4645
[17 empty] | 106 | 2024-10-02 | 273 | 4106.9638 | 5152.0995 | 793697.95 | 950778.564
[17 empty] | 106 | 2024-10-03 | 274 | 4106.9638 | 5152.0995 | 797804.9138 | 955930.6635
[17 empty] | 106 | 2024-10-04 | 275 | 4106.9638 | 5152.0995 | 801911.8777 | 961082.763
[17 empty] | 106 | 2024-10-05 | 276 | 0 | 0 | 801911.8777 | 961082.763
[17 empty] | 106 | 2024-10-06 | 277 | 0 | 0 | 801911.8777 | 961082.763
[17 empty] | 106 | 2024-10-07 | 278 | 4106.9638 | 5152.0995 | 806018.8415 | 966234.8625
[17 empty] | 106 | 2024-10-08 | 279 | 4106.9638 | 5152.0995 | 810125.8054 | 971386.962
[17 empty] | 106 | 2024-10-09 | 280 | 4106.9638 | 5152.0995 | 814232.7692 | 976539.0615
[17 empty] | 106 | 2024-10-10 | 281 | 4106.9638 | 5152.0995 | 818339.7331 | 981691.161
[17 empty] | 106 | 2024-10-11 | 282 | 4106.9638 | 5152.0995 | 822446.6969 | 986843.2606
[17 empty] | 106 | 2024-10-12 | 283 | 0 | 0 | 822446.6969 | 986843.2606
[17 empty] | 106 | 2024-10-13 | 284 | 0 | 0 | 822446.6969 | 986843.2606
[17 empty] | 106 | 2024-10-14 | 285 | 424.9638 | 475.9595 | 822871.6608 | 987319.2201
[17 empty] | 106 | 2024-10-15 | 286 | 424.9638 | 475.9595 | 823296.6246 | 987795.1796
[17 empty] | 106 | 2024-10-16 | 287 | 424.9638 | 475.9595 | 823721.5885 | 988271.1391
[17 empty] | 106 | 2024-10-17 | 288 | 424.9638 | 475.9595 | 824146.5523 | 988747.0986
[17 empty] | 106 | 2024-10-18 | 289 | 424.9638 | 475.9595 | 824571.5162 | 989223.0581
[17 empty] | 106 | 2024-10-19 | 290 | 0 | 0 | 824571.5162 | 989223.0581
[17 empty] | 106 | 2024-10-20 | 291 | 0 | 0 | 824571.5162 | 989223.0581
[17 empty] | 106 | 2024-10-21 | 292 | 424.9638 | 475.9595 | 824996.48 | 989699.0176
[17 empty] | 107 | 2024-02-18 | 1 | 0 | 0 | 0 | 0
[17 empty] | 107 | 2024-02-19 | 2 | 269.3674 | 315.1599 | 269.3674 | 315.1599
[17 empty] | 107 | 2024-02-20 | 3 | 269.3674 | 315.1599 | 538.7349 | 630.3198
[17 empty] | 107 | 2024-02-21 | 4 | 269.3674 | 315.1599 | 808.1023 | 945.4797
[17 empty] | 107 | 2024-02-22 | 5 | 269.3674 | 315.1599 | 1077.4697 | 1260.6396
[17 empty] | 107 | 2024-02-23 | 6 | 1630.5566 | 1826.0799 | 2708.0264 | 3086.7195
[17 empty] | 107 | 2024-02-24 | 7 | 0 | 0 | 2708.0264 | 3086.7195
[17 empty] | 107 | 2024-02-25 | 8 | 0 | 0 | 2708.0264 | 3086.7195
[17 empty] | 107 | 2024-02-26 | 9 | 1630.5566 | 1826.0799 | 4338.583 | 4912.7994
[17 empty] | 107 | 2024-02-27 | 10 | 1630.5566 | 1826.0799 | 5969.1396 | 6738.8793
[17 empty] | 107 | 2024-02-28 | 11 | 1630.5566 | 1826.0799 | 7599.6962 | 8564.9592
[17 empty] | 107 | 2024-02-29 | 12 | 1630.5566 | 1826.0799 | 9230.2529 | 10391.0391
[17 empty] | 107 | 2024-03-01 | 13 | 1630.5566 | 1826.0799 | 10860.8095 | 12217.119
[17 empty] | 107 | 2024-03-02 | 14 | 0 | 0 | 10860.8095 | 12217.119
[17 empty] | 107 | 2024-03-03 | 15 | 0 | 0 | 10860.8095 | 12217.119
[17 empty] | 107 | 2024-03-04 | 16 | 1630.5566 | 1826.0799 | 12491.3661 | 14043.1989
[17 empty] | 107 | 2024-03-05 | 17 | 1630.5566 | 1826.0799 | 14121.9227 | 15869.2788
[17 empty] | 107 | 2024-03-06 | 18 | 1630.5566 | 1826.0799 | 15752.4794 | 17695.3587
[17 empty] | 107 | 2024-03-07 | 19 | 1630.5566 | 1826.0799 | 17383.036 | 19521.4386
[17 empty] | 107 | 2024-03-08 | 20 | 1630.5566 | 1826.0799 | 19013.5926 | 21347.5185
[17 empty] | 107 | 2024-03-09 | 21 | 0 | 0 | 19013.5926 | 21347.5185
[17 empty] | 107 | 2024-03-10 | 22 | 0 | 0 | 19013.5926 | 21347.5185
[17 empty] | 107 | 2024-03-11 | 23 | 1630.5566 | 1826.0799 | 20644.1492 | 23173.5984
[17 empty] | 107 | 2024-03-12 | 24 | 1630.5566 | 1826.0799 | 22274.7059 | 24999.6783
[17 empty] | 107 | 2024-03-13 | 25 | 1630.5566 | 1826.0799 | 23905.2625 | 26825.7582
[17 empty] | 107 | 2024-03-14 | 26 | 1630.5566 | 1826.0799 | 25535.8191 | 28651.8381
[17 empty] | 107 | 2024-03-15 | 27 | 1630.5566 | 1826.0799 | 27166.3757 | 30477.918
[17 empty] | 107 | 2024-03-16 | 28 | 0 | 0 | 27166.3757 | 30477.918
[17 empty] | 107 | 2024-03-17 | 29 | 0 | 0 | 27166.3757 | 30477.918
[17 empty] | 107 | 2024-03-18 | 30 | 1630.5566 | 1826.0799 | 28796.9324 | 32303.9979
[17 empty] | 107 | 2024-03-19 | 31 | 1630.5566 | 1826.0799 | 30427.489 | 34130.0778
[17 empty] | 107 | 2024-03-20 | 32 | 1630.5566 | 1826.0799 | 32058.0456 | 35956.1577
[17 empty] | 107 | 2024-03-21 | 33 | 1630.5566 | 1826.0799 | 33688.6022 | 37782.2376
[17 empty] | 107 | 2024-03-22 | 34 | 1630.5566 | 1826.0799 | 35319.1589 | 39608.3175
[17 empty] | 107 | 2024-03-23 | 35 | 0 | 0 | 35319.1589 | 39608.3175
[17 empty] | 107 | 2024-03-24 | 36 | 0 | 0 | 35319.1589 | 39608.3175
[17 empty] | 107 | 2024-03-25 | 37 | 1630.5566 | 1826.0799 | 36949.7155 | 41434.3974
[17 empty] | 107 | 2024-03-26 | 38 | 1630.5566 | 1826.0799 | 38580.2721 | 43260.4773
[17 empty] | 107 | 2024-03-27 | 39 | 1630.5566 | 1826.0799 | 40210.8287 | 45086.5572
[17 empty] | 107 | 2024-03-28 | 40 | 1630.5566 | 1826.0799 | 41841.3854 | 46912.6371
[17 empty] | 107 | 2024-03-29 | 41 | 1630.5566 | 1826.0799 | 43471.942 | 48738.717
[17 empty] | 107 | 2024-03-30 | 42 | 0 | 0 | 43471.942 | 48738.717
[17 empty] | 107 | 2024-03-31 | 43 | 0 | 0 | 43471.942 | 48738.717
[17 empty] | 107 | 2024-04-01 | 44 | 1630.5566 | 1826.0799 | 45102.4986 | 50564.7969
[17 empty] | 107 | 2024-04-02 | 45 | 1630.5566 | 1826.0799 | 46733.0552 | 52390.8768
[17 empty] | 107 | 2024-04-03 | 46 | 1630.5566 | 1826.0799 | 48363.6119 | 54216.9567
[17 empty] | 107 | 2024-04-04 | 47 | 1630.5566 | 1826.0799 | 49994.1685 | 56043.0366
[17 empty] | 107 | 2024-04-05 | 48 | 1630.5566 | 1826.0799 | 51624.7251 | 57869.1165
[17 empty] | 107 | 2024-04-06 | 49 | 0 | 0 | 51624.7251 | 57869.1165
[17 empty] | 107 | 2024-04-07 | 50 | 0 | 0 | 51624.7251 | 57869.1165
[17 empty] | 107 | 2024-04-08 | 51 | 1630.5566 | 1826.0799 | 53255.2817 | 59695.1964
[17 empty] | 107 | 2024-04-09 | 52 | 1630.5566 | 1826.0799 | 54885.8384 | 61521.2763
[17 empty] | 107 | 2024-04-10 | 53 | 1630.5566 | 1826.0799 | 56516.395 | 63347.3562
[17 empty] | 107 | 2024-04-11 | 54 | 1630.5566 | 1826.0799 | 58146.9516 | 65173.4361
[17 empty] | 107 | 2024-04-12 | 55 | 1630.5566 | 1826.0799 | 59777.5082 | 66999.516
[17 empty] | 107 | 2024-04-13 | 56 | 0 | 0 | 59777.5082 | 66999.516
[17 empty] | 107 | 2024-04-14 | 57 | 0 | 0 | 59777.5082 | 66999.516
[17 empty] | 107 | 2024-04-15 | 58 | 3728.7656 | 4176.0739 | 63506.2738 | 71175.5899
[17 empty] | 107 | 2024-04-16 | 59 | 2367.5764 | 2665.1539 | 65873.8502 | 73840.7439
[17 empty] | 107 | 2024-04-17 | 60 | 2367.5764 | 2665.1539 | 68241.4266 | 76505.8978
[17 empty] | 107 | 2024-04-18 | 61 | 2367.5764 | 2665.1539 | 70609.003 | 79171.0517
[17 empty] | 107 | 2024-04-19 | 62 | 2367.5764 | 2665.1539 | 72976.5794 | 81836.2056
[17 empty] | 107 | 2024-04-20 | 63 | 0 | 0 | 72976.5794 | 81836.2056
[17 empty] | 107 | 2024-04-21 | 64 | 0 | 0 | 72976.5794 | 81836.2056
[17 empty] | 107 | 2024-04-22 | 65 | 2367.5764 | 2665.1539 | 75344.1558 | 84501.3596
[17 empty] | 107 | 2024-04-23 | 66 | 2367.5764 | 2665.1539 | 77711.7322 | 87166.5135
[17 empty] | 107 | 2024-04-24 | 67 | 2367.5764 | 2665.1539 | 80079.3086 | 89831.6674
[17 empty] | 107 | 2024-04-25 | 68 | 2367.5764 | 2665.1539 | 82446.885 | 92496.8214
[17 empty] | 107 | 2024-04-26 | 69 | 2367.5764 | 2665.1539 | 84814.4613 | 95161.9753
[17 empty] | 107 | 2024-04-27 | 70 | 0 | 0 | 84814.4613 | 95161.9753
[17 empty] | 107 | 2024-04-28 | 71 | 0 | 0 | 84814.4613 | 95161.9753
[17 empty] | 107 | 2024-04-29 | 72 | 2367.5764 | 2665.1539 | 87182.0377 | 97827.1292
[17 empty] | 107 | 2024-04-30 | 73 | 2367.5764 | 2665.1539 | 89549.6141 | 100492.2832
[17 empty] | 107 | 2024-05-01 | 74 | 2367.5764 | 2665.1539 | 91917.1905 | 103157.4371
[17 empty] | 107 | 2024-05-02 | 75 | 2367.5764 | 2665.1539 | 94284.7669 | 105822.591
[17 empty] | 107 | 2024-05-03 | 76 | 2367.5764 | 2665.1539 | 96652.3433 | 108487.7449
[17 empty] | 107 | 2024-05-04 | 77 | 0 | 0 | 96652.3433 | 108487.7449
[17 empty] | 107 | 2024-05-05 | 78 | 0 | 0 | 96652.3433 | 108487.7449
[17 empty] | 107 | 2024-05-06 | 79 | 2367.5764 | 2665.1539 | 99019.9197 | 111152.8989
[17 empty] | 107 | 2024-05-07 | 80 | 2367.5764 | 2665.1539 | 101387.4961 | 113818.0528
[17 empty] | 107 | 2024-05-08 | 81 | 2367.5764 | 2665.1539 | 103755.0725 | 116483.2067
[17 empty] | 107 | 2024-05-09 | 82 | 2367.5764 | 2665.1539 | 106122.6489 | 119148.3607
[17 empty] | 107 | 2024-05-10 | 83 | 2367.5764 | 2665.1539 | 108490.2253 | 121813.5146
[17 empty] | 107 | 2024-05-11 | 84 | 0 | 0 | 108490.2253 | 121813.5146
[17 empty] | 107 | 2024-05-12 | 85 | 0 | 0 | 108490.2253 | 121813.5146
[17 empty] | 107 | 2024-05-13 | 86 | 2367.5764 | 2665.1539 | 110857.8016 | 124478.6685
[17 empty] | 107 | 2024-05-14 | 87 | 2367.5764 | 2665.1539 | 113225.378 | 127143.8225
[17 empty] | 107 | 2024-05-15 | 88 | 2367.5764 | 2665.1539 | 115592.9544 | 129808.9764
[17 empty] | 107 | 2024-05-16 | 89 | 2367.5764 | 2665.1539 | 117960.5308 | 132474.1303
[17 empty] | 107 | 2024-05-17 | 90 | 2367.5764 | 2665.1539 | 120328.1072 | 135139.2842
[17 empty] | 107 | 2024-05-18 | 91 | 0 | 0 | 120328.1072 | 135139.2842
[17 empty] | 107 | 2024-05-19 | 92 | 0 | 0 | 120328.1072 | 135139.2842
[17 empty] | 107 | 2024-05-20 | 93 | 2367.5764 | 2665.1539 | 122695.6836 | 137804.4382
[17 empty] | 107 | 2024-05-21 | 94 | 2367.5764 | 2665.1539 | 125063.26 | 140469.5921
[17 empty] | 107 | 2024-05-22 | 95 | 2367.5764 | 2665.1539 | 127430.8364 | 143134.746
[17 empty] | 107 | 2024-05-23 | 96 | 2367.5764 | 2665.1539 | 129798.4128 | 145799.9
[17 empty] | 107 | 2024-05-24 | 97 | 2367.5764 | 2665.1539 | 132165.9892 | 148465.0539
[17 empty] | 107 | 2024-05-25 | 98 | 0 | 0 | 132165.9892 | 148465.0539
[17 empty] | 107 | 2024-05-26 | 99 | 0 | 0 | 132165.9892 | 148465.0539
[17 empty] | 107 | 2024-05-27 | 100 | 2367.5764 | 2665.1539 | 134533.5656 | 151130.2078
[17 empty] | 107 | 2024-05-28 | 101 | 2367.5764 | 2665.1539 | 136901.142 | 153795.3618
[17 empty] | 107 | 2024-05-29 | 102 | 2367.5764 | 2665.1539 | 139268.7183 | 156460.5157
[17 empty] | 107 | 2024-05-30 | 103 | 2367.5764 | 2665.1539 | 141636.2947 | 159125.6696
[17 empty] | 107 | 2024-05-31 | 104 | 2367.5764 | 2665.1539 | 144003.8711 | 161790.8235
[17 empty] | 107 | 2024-06-01 | 105 | 0 | 0 | 144003.8711 | 161790.8235
[17 empty] | 107 | 2024-06-02 | 106 | 0 | 0 | 144003.8711 | 161790.8235
[17 empty] | 107 | 2024-06-03 | 107 | 2367.5764 | 2665.1539 | 146371.4475 | 164455.9775
[17 empty] | 107 | 2024-06-04 | 108 | 2367.5764 | 2665.1539 | 148739.0239 | 167121.1314
[17 empty] | 107 | 2024-06-05 | 109 | 2367.5764 | 2665.1539 | 151106.6003 | 169786.2853
[17 empty] | 107 | 2024-06-06 | 110 | 2367.5764 | 2665.1539 | 153474.1767 | 172451.4393
[17 empty] | 107 | 2024-06-07 | 111 | 2367.5764 | 2665.1539 | 155841.7531 | 175116.5932
[17 empty] | 107 | 2024-06-08 | 112 | 0 | 0 | 155841.7531 | 175116.5932
[17 empty] | 107 | 2024-06-09 | 113 | 0 | 0 | 155841.7531 | 175116.5932
[17 empty] | 107 | 2024-06-10 | 114 | 2367.5764 | 2665.1539 | 158209.3295 | 177781.7471
[17 empty] | 107 | 2024-06-11 | 115 | 2367.5764 | 2665.1539 | 160576.9059 | 180446.9011
[17 empty] | 107 | 2024-06-12 | 116 | 2367.5764 | 2665.1539 | 162944.4823 | 183112.055
[17 empty] | 107 | 2024-06-13 | 117 | 2367.5764 | 2665.1539 | 165312.0586 | 185777.2089
[17 empty] | 107 | 2024-06-14 | 118 | 2367.5764 | 2665.1539 | 167679.635 | 188442.3628
[17 empty] | 107 | 2024-06-15 | 119 | 0 | 0 | 167679.635 | 188442.3628
[17 empty] | 107 | 2024-06-16 | 120 | 0 | 0 | 167679.635 | 188442.3628
[17 empty] | 107 | 2024-06-17 | 121 | 2367.5764 | 2665.1539 | 170047.2114 | 191107.5168
[17 empty] | 107 | 2024-06-18 | 122 | 2367.5764 | 2665.1539 | 172414.7878 | 193772.6707
[17 empty] | 107 | 2024-06-19 | 123 | 2367.5764 | 2665.1539 | 174782.3642 | 196437.8246
[17 empty] | 107 | 2024-06-20 | 124 | 2367.5764 | 2665.1539 | 177149.9406 | 199102.9786
[17 empty] | 107 | 2024-06-21 | 125 | 2367.5764 | 2665.1539 | 179517.517 | 201768.1325
[17 empty] | 107 | 2024-06-22 | 126 | 0 | 0 | 179517.517 | 201768.1325
[17 empty] | 107 | 2024-06-23 | 127 | 0 | 0 | 179517.517 | 201768.1325
[17 empty] | 107 | 2024-06-24 | 128 | 2367.5764 | 2665.1539 | 181885.0934 | 204433.2864
[17 empty] | 107 | 2024-06-25 | 129 | 2367.5764 | 2665.1539 | 184252.6698 | 207098.4404
[17 empty] | 107 | 2024-06-26 | 130 | 4795.1764 | 5602.5499 | 189047.8462 | 212700.9903
[17 empty] | 107 | 2024-06-27 | 131 | 4795.1764 | 5602.5499 | 193843.0226 | 218303.5402
[17 empty] | 107 | 2024-06-28 | 132 | 4795.1764 | 5602.5499 | 198638.1989 | 223906.0901
[17 empty] | 107 | 2024-06-29 | 133 | 0 | 0 | 198638.1989 | 223906.0901
[17 empty] | 107 | 2024-06-30 | 134 | 0 | 0 | 198638.1989 | 223906.0901
[17 empty] | 107 | 2024-07-01 | 135 | 4795.1764 | 5602.5499 | 203433.3753 | 229508.6401
[17 empty] | 107 | 2024-07-02 | 136 | 4795.1764 | 5602.5499 | 208228.5517 | 235111.19
[17 empty] | 107 | 2024-07-03 | 137 | 4795.1764 | 5602.5499 | 213023.7281 | 240713.7399
[17 empty] | 107 | 2024-07-04 | 138 | 4795.1764 | 5602.5499 | 217818.9045 | 246316.2899
[17 empty] | 107 | 2024-07-05 | 139 | 4795.1764 | 5602.5499 | 222614.0809 | 251918.8398
[17 empty] | 107 | 2024-07-06 | 140 | 0 | 0 | 222614.0809 | 251918.8398
[17 empty] | 107 | 2024-07-07 | 141 | 0 | 0 | 222614.0809 | 251918.8398
[17 empty] | 107 | 2024-07-08 | 142 | 7153.1764 | 8479.3099 | 229767.2573 | 260398.1497
[17 empty] | 107 | 2024-07-09 | 143 | 7153.1764 | 8479.3099 | 236920.4337 | 268877.4597
[17 empty] | 107 | 2024-07-10 | 144 | 7153.1764 | 8479.3099 | 244073.6101 | 277356.7696
[17 empty] | 107 | 2024-07-11 | 145 | 7153.1764 | 8479.3099 | 251226.7865 | 285836.0795
[17 empty] | 107 | 2024-07-12 | 146 | 7153.1764 | 8479.3099 | 258379.9629 | 294315.3894
[17 empty] | 107 | 2024-07-13 | 147 | 0 | 0 | 258379.9629 | 294315.3894
[17 empty] | 107 | 2024-07-14 | 148 | 0 | 0 | 258379.9629 | 294315.3894
[17 empty] | 107 | 2024-07-15 | 149 | 7153.1764 | 8479.3099 | 265533.1392 | 302794.6994
[17 empty] | 107 | 2024-07-16 | 150 | 7153.1764 | 8479.3099 | 272686.3156 | 311274.0093
[17 empty] | 107 | 2024-07-17 | 151 | 5054.9674 | 6129.3159 | 277741.2831 | 317403.3252
[17 empty] | 107 | 2024-07-18 | 152 | 5054.9674 | 6129.3159 | 282796.2505 | 323532.6411
[17 empty] | 107 | 2024-07-19 | 153 | 5054.9674 | 6129.3159 | 287851.2179 | 329661.957
[17 empty] | 107 | 2024-07-20 | 154 | 0 | 0 | 287851.2179 | 329661.957
[17 empty] | 107 | 2024-07-21 | 155 | 0 | 0 | 287851.2179 | 329661.957
[17 empty] | 107 | 2024-07-22 | 156 | 5054.9674 | 6129.3159 | 292906.1854 | 335791.2729
[17 empty] | 107 | 2024-07-23 | 157 | 5054.9674 | 6129.3159 | 297961.1528 | 341920.5888
[17 empty] | 107 | 2024-07-24 | 158 | 5054.9674 | 6129.3159 | 303016.1203 | 348049.9047
[17 empty] | 107 | 2024-07-25 | 159 | 5054.9674 | 6129.3159 | 308071.0877 | 354179.2206
[17 empty] | 107 | 2024-07-26 | 160 | 5054.9674 | 6129.3159 | 313126.0551 | 360308.5365
[17 empty] | 107 | 2024-07-27 | 161 | 0 | 0 | 313126.0551 | 360308.5365
[17 empty] | 107 | 2024-07-28 | 162 | 0 | 0 | 313126.0551 | 360308.5365
[17 empty] | 107 | 2024-07-29 | 163 | 5054.9674 | 6129.3159 | 318181.0226 | 366437.8524
[17 empty] | 107 | 2024-07-30 | 164 | 5054.9674 | 6129.3159 | 323235.99 | 372567.1683
[17 empty] | 107 | 2024-07-31 | 165 | 5054.9674 | 6129.3159 | 328290.9574 | 378696.4842
[17 empty] | 107 | 2024-08-01 | 166 | 5054.9674 | 6129.3159 | 333345.9249 | 384825.8001
[17 empty] | 107 | 2024-08-02 | 167 | 5054.9674 | 6129.3159 | 338400.8923 | 390955.116
[17 empty] | 107 | 2024-08-03 | 168 | 0 | 0 | 338400.8923 | 390955.116
[17 empty] | 107 | 2024-08-04 | 169 | 0 | 0 | 338400.8923 | 390955.116
[17 empty] | 107 | 2024-08-05 | 170 | 5054.9674 | 6129.3159 | 343455.8597 | 397084.4319
[17 empty] | 107 | 2024-08-06 | 171 | 5054.9674 | 6129.3159 | 348510.8272 | 403213.7478
[17 empty] | 107 | 2024-08-07 | 172 | 5054.9674 | 6129.3159 | 353565.7946 | 409343.0637
[17 empty] | 107 | 2024-08-08 | 173 | 5054.9674 | 6129.3159 | 358620.7621 | 415472.3796
[17 empty] | 107 | 2024-08-09 | 174 | 5054.9674 | 6129.3159 | 363675.7295 | 421601.6955
[17 empty] | 107 | 2024-08-10 | 175 | 0 | 0 | 363675.7295 | 421601.6955
[17 empty] | 107 | 2024-08-11 | 176 | 0 | 0 | 363675.7295 | 421601.6955
[17 empty] | 107 | 2024-08-12 | 177 | 5054.9674 | 6129.3159 | 368730.6969 | 427731.0114
[17 empty] | 107 | 2024-08-13 | 178 | 5054.9674 | 6129.3159 | 373785.6644 | 433860.3273
[17 empty] | 107 | 2024-08-14 | 179 | 2627.3674 | 3191.9199 | 376413.0318 | 437052.2472
[17 empty] | 107 | 2024-08-15 | 180 | 2627.3674 | 3191.9199 | 379040.3992 | 440244.1671
[17 empty] | 107 | 2024-08-16 | 181 | 2627.3674 | 3191.9199 | 381667.7667 | 443436.087
[17 empty] | 107 | 2024-08-17 | 182 | 0 | 0 | 381667.7667 | 443436.087
[17 empty] | 107 | 2024-08-18 | 183 | 0 | 0 | 381667.7667 | 443436.087
[17 empty] | 107 | 2024-08-19 | 184 | 2627.3674 | 3191.9199 | 384295.1341 | 446628.0069
[17 empty] | 107 | 2024-08-20 | 185 | 2627.3674 | 3191.9199 | 386922.5015 | 449819.9268
[17 empty] | 107 | 2024-08-21 | 186 | 2627.3674 | 3191.9199 | 389549.869 | 453011.8467
[17 empty] | 107 | 2024-08-22 | 187 | 2627.3674 | 3191.9199 | 392177.2364 | 456203.7666
[17 empty] | 107 | 2024-08-23 | 188 | 2627.3674 | 3191.9199 | 394804.6038 | 459395.6865
[17 empty] | 107 | 2024-08-24 | 189 | 0 | 0 | 394804.6038 | 459395.6865
[17 empty] | 107 | 2024-08-25 | 190 | 0 | 0 | 394804.6038 | 459395.6865
[17 empty] | 107 | 2024-08-26 | 191 | 2627.3674 | 3191.9199 | 397431.9713 | 462587.6064
[17 empty] | 107 | 2024-08-27 | 192 | 2627.3674 | 3191.9199 | 400059.3387 | 465779.5263
[17 empty] | 107 | 2024-08-28 | 193 | 2627.3674 | 3191.9199 | 402686.7062 | 468971.4462
[17 empty] | 107 | 2024-08-29 | 194 | 2627.3674 | 3191.9199 | 405314.0736 | 472163.3661
[17 empty] | 107 | 2024-08-30 | 195 | 2627.3674 | 3191.9199 | 407941.441 | 475355.286
[17 empty] | 107 | 2024-08-31 | 196 | 0 | 0 | 407941.441 | 475355.286
[17 empty] | 107 | 2024-09-01 | 197 | 0 | 0 | 407941.441 | 475355.286
[17 empty] | 107 | 2024-09-02 | 198 | 2627.3674 | 3191.9199 | 410568.8085 | 478547.2059
[17 empty] | 107 | 2024-09-03 | 199 | 2627.3674 | 3191.9199 | 413196.1759 | 481739.1258
[17 empty] | 107 | 2024-09-04 | 200 | 2627.3674 | 3191.9199 | 415823.5433 | 484931.0457
[17 empty] | 107 | 2024-09-05 | 201 | 2627.3674 | 3191.9199 | 418450.9108 | 488122.9656
[17 empty] | 107 | 2024-09-06 | 202 | 2627.3674 | 3191.9199 | 421078.2782 | 491314.8855
[17 empty] | 107 | 2024-09-07 | 203 | 0 | 0 | 421078.2782 | 491314.8855
[17 empty] | 107 | 2024-09-08 | 204 | 0 | 0 | 421078.2782 | 491314.8855
[17 empty] | 107 | 2024-09-09 | 205 | 2627.3674 | 3191.9199 | 423705.6456 | 494506.8054
[17 empty] | 107 | 2024-09-10 | 206 | 2627.3674 | 3191.9199 | 426333.0131 | 497698.7253
[17 empty] | 107 | 2024-09-11 | 207 | 2627.3674 | 3191.9199 | 428960.3805 | 500890.6452
[17 empty] | 107 | 2024-09-12 | 208 | 2627.3674 | 3191.9199 | 431587.7479 | 504082.5651
[17 empty] | 107 | 2024-09-13 | 209 | 2627.3674 | 3191.9199 | 434215.1154 | 507274.485
[17 empty] | 107 | 2024-09-14 | 210 | 0 | 0 | 434215.1154 | 507274.485
[17 empty] | 107 | 2024-09-15 | 211 | 0 | 0 | 434215.1154 | 507274.485
[17 empty] | 107 | 2024-09-16 | 212 | 2627.3674 | 3191.9199 | 436842.4828 | 510466.4049
[17 empty] | 107 | 2024-09-17 | 213 | 2627.3674 | 3191.9199 | 439469.8503 | 513658.3248
[17 empty] | 107 | 2024-09-18 | 214 | 2627.3674 | 3191.9199 | 442097.2177 | 516850.2447
[17 empty] | 107 | 2024-09-19 | 215 | 2627.3674 | 3191.9199 | 444724.5851 | 520042.1646
[17 empty] | 107 | 2024-09-20 | 216 | 2627.3674 | 3191.9199 | 447351.9526 | 523234.0845
[17 empty] | 107 | 2024-09-21 | 217 | 0 | 0 | 447351.9526 | 523234.0845
[17 empty] | 107 | 2024-09-22 | 218 | 0 | 0 | 447351.9526 | 523234.0845
[17 empty] | 107 | 2024-09-23 | 219 | 2627.3674 | 3191.9199 | 449979.32 | 526426.0044
[17 empty] | 107 | 2024-09-24 | 220 | 2627.3674 | 3191.9199 | 452606.6874 | 529617.9243
[17 empty] | 107 | 2024-09-25 | 221 | 2627.3674 | 3191.9199 | 455234.0549 | 532809.8442
[17 empty] | 107 | 2024-09-26 | 222 | 2627.3674 | 3191.9199 | 457861.4223 | 536001.7641
[17 empty] | 107 | 2024-09-27 | 223 | 2627.3674 | 3191.9199 | 460488.7897 | 539193.684
[17 empty] | 107 | 2024-09-28 | 224 | 0 | 0 | 460488.7897 | 539193.684
[17 empty] | 107 | 2024-09-29 | 225 | 0 | 0 | 460488.7897 | 539193.684
[17 empty] | 107 | 2024-09-30 | 226 | 2627.3674 | 3191.9199 | 463116.1572 | 542385.6039
[17 empty] | 107 | 2024-10-01 | 227 | 2627.3674 | 3191.9199 | 465743.5246 | 545577.5238
[17 empty] | 107 | 2024-10-02 | 228 | 2627.3674 | 3191.9199 | 468370.8921 | 548769.4437
[17 empty] | 107 | 2024-10-03 | 229 | 2627.3674 | 3191.9199 | 470998.2595 | 551961.3636
[17 empty] | 107 | 2024-10-04 | 230 | 2627.3674 | 3191.9199 | 473625.6269 | 555153.2835
[17 empty] | 107 | 2024-10-05 | 231 | 0 | 0 | 473625.6269 | 555153.2835
[17 empty] | 107 | 2024-10-06 | 232 | 0 | 0 | 473625.6269 | 555153.2835
[17 empty] | 107 | 2024-10-07 | 233 | 2627.3674 | 3191.9199 | 476252.9944 | 558345.2034
[17 empty] | 107 | 2024-10-08 | 234 | 2627.3674 | 3191.9199 | 478880.3618 | 561537.1233
[17 empty] | 107 | 2024-10-09 | 235 | 2627.3674 | 3191.9199 | 481507.7292 | 564729.0432
[17 empty] | 107 | 2024-10-10 | 236 | 2627.3674 | 3191.9199 | 484135.0967 | 567920.9631
[17 empty] | 107 | 2024-10-11 | 237 | 2627.3674 | 3191.9199 | 486762.4641 | 571112.883
[17 empty] | 107 | 2024-10-12 | 238 | 0 | 0 | 486762.4641 | 571112.883
[17 empty] | 107 | 2024-10-13 | 239 | 0 | 0 | 486762.4641 | 571112.883
[17 empty] | 107 | 2024-10-14 | 240 | 2627.3674 | 3191.9199 | 489389.8315 | 574304.8029
[17 empty] | 107 | 2024-10-15 | 241 | 2627.3674 | 3191.9199 | 492017.199 | 577496.7228
[17 empty] | 107 | 2024-10-16 | 242 | 2627.3674 | 3191.9199 | 494644.5664 | 580688.6427
[17 empty] | 107 | 2024-10-17 | 243 | 2627.3674 | 3191.9199 | 497271.9338 | 583880.5626
[17 empty] | 107 | 2024-10-18 | 244 | 2627.3674 | 3191.9199 | 499899.3013 | 587072.4825
[17 empty] | 107 | 2024-10-19 | 245 | 0 | 0 | 499899.3013 | 587072.4825
[17 empty] | 107 | 2024-10-20 | 246 | 0 | 0 | 499899.3013 | 587072.4825
[17 empty] | 107 | 2024-10-21 | 247 | 2627.3674 | 3191.9199 | 502526.6687 | 590264.4024
[17 empty] | 107 | 2024-10-22 | 248 | 2627.3674 | 3191.9199 | 505154.0362 | 593456.3223
[17 empty] | 107 | 2024-10-23 | 249 | 2627.3674 | 3191.9199 | 507781.4036 | 596648.2422
[17 empty] | 107 | 2024-10-24 | 250 | 2627.3674 | 3191.9199 | 510408.771 | 599840.1621
[17 empty] | 107 | 2024-10-25 | 251 | 2627.3674 | 3191.9199 | 513036.1385 | 603032.082
[17 empty] | 107 | 2024-10-26 | 252 | 0 | 0 | 513036.1385 | 603032.082
[17 empty] | 107 | 2024-10-27 | 253 | 0 | 0 | 513036.1385 | 603032.082
[17 empty] | 107 | 2024-10-28 | 254 | 2627.3674 | 3191.9199 | 515663.5059 | 606224.0019
[17 empty] | 107 | 2024-10-29 | 255 | 2627.3674 | 3191.9199 | 518290.8733 | 609415.9218
[17 empty] | 107 | 2024-10-30 | 256 | 2627.3674 | 3191.9199 | 520918.2408 | 612607.8417
[17 empty] | 107 | 2024-10-31 | 257 | 2627.3674 | 3191.9199 | 523545.6082 | 615799.7616
[17 empty] | 107 | 2024-11-01 | 258 | 2627.3674 | 3191.9199 | 526172.9756 | 618991.6815
[17 empty] | 107 | 2024-11-02 | 259 | 0 | 0 | 526172.9756 | 618991.6815
[17 empty] | 107 | 2024-11-03 | 260 | 0 | 0 | 526172.9756 | 618991.6815
[17 empty] | 107 | 2024-11-04 | 261 | 2627.3674 | 3191.9199 | 528800.3431 | 622183.6014
[17 empty] | 107 | 2024-11-05 | 262 | 2627.3674 | 3191.9199 | 531427.7105 | 625375.5213
[17 empty] | 107 | 2024-11-06 | 263 | 2627.3674 | 3191.9199 | 534055.0779 | 628567.4412
[17 empty] | 107 | 2024-11-07 | 264 | 2627.3674 | 3191.9199 | 536682.4454 | 631759.3611
[17 empty] | 107 | 2024-11-08 | 265 | 2627.3674 | 3191.9199 | 539309.8128 | 634951.281
[17 empty] | 107 | 2024-11-09 | 266 | 0 | 0 | 539309.8128 | 634951.281
[17 empty] | 107 | 2024-11-10 | 267 | 0 | 0 | 539309.8128 | 634951.281
[17 empty] | 107 | 2024-11-11 | 268 | 2627.3674 | 3191.9199 | 541937.1803 | 638143.2009
[17 empty] | 107 | 2024-11-12 | 269 | 2627.3674 | 3191.9199 | 544564.5477 | 641335.1208
[17 empty] | 107 | 2024-11-13 | 270 | 2627.3674 | 3191.9199 | 547191.9151 | 644527.0407
[17 empty] | 107 | 2024-11-14 | 271 | 2627.3674 | 3191.9199 | 549819.2826 | 647718.9606
[17 empty] | 107 | 2024-11-15 | 272 | 2627.3674 | 3191.9199 | 552446.65 | 650910.8805
[17 empty] | 107 | 2024-11-16 | 273 | 0 | 0 | 552446.65 | 650910.8805
[17 empty] | 107 | 2024-11-17 | 274 | 0 | 0 | 552446.65 | 650910.8805
[17 empty] | 107 | 2024-11-18 | 275 | 2627.3674 | 3191.9199 | 555074.0174 | 654102.8004
[17 empty] | 107 | 2024-11-19 | 276 | 2627.3674 | 3191.9199 | 557701.3849 | 657294.7203
[17 empty] | 107 | 2024-11-20 | 277 | 2627.3674 | 3191.9199 | 560328.7523 | 660486.6402
[17 empty] | 107 | 2024-11-21 | 278 | 2627.3674 | 3191.9199 | 562956.1197 | 663678.5601
[17 empty] | 107 | 2024-11-22 | 279 | 2627.3674 | 3191.9199 | 565583.4872 | 666870.48
[17 empty] | 107 | 2024-11-23 | 280 | 0 | 0 | 565583.4872 | 666870.48
[17 empty] | 107 | 2024-11-24 | 281 | 0 | 0 | 565583.4872 | 666870.48
[17 empty] | 107 | 2024-11-25 | 282 | 2627.3674 | 3191.9199 | 568210.8546 | 670062.3999
[17 empty] | 107 | 2024-11-26 | 283 | 2627.3674 | 3191.9199 | 570838.2221 | 673254.3198
[17 empty] | 107 | 2024-11-27 | 284 | 2627.3674 | 3191.9199 | 573465.5895 | 676446.2397
[17 empty] | 107 | 2024-11-28 | 285 | 2627.3674 | 3191.9199 | 576092.9569 | 679638.1596
[17 empty] | 107 | 2024-11-29 | 286 | 2627.3674 | 3191.9199 | 578720.3244 | 682830.0795
[17 empty] | 107 | 2024-11-30 | 287 | 0 | 0 | 578720.3244 | 682830.0795
[17 empty] | 107 | 2024-12-01 | 288 | 0 | 0 | 578720.3244 | 682830.0795
[17 empty] | 107 | 2024-12-02 | 289 | 2627.3674 | 3191.9199 | 581347.6918 | 686021.9994
[17 empty] | 107 | 2024-12-03 | 290 | 2627.3674 | 3191.9199 | 583975.0592 | 689213.9193
[17 empty] | 107 | 2024-12-04 | 291 | 2627.3674 | 3191.9199 | 586602.4267 | 692405.8392
[17 empty] | 107 | 2024-12-05 | 292 | 2627.3674 | 3191.9199 | 589229.7941 | 695597.7591
[17 empty] | 107 | 2024-12-06 | 293 | 2627.3674 | 3191.9199 | 591857.1615 | 698789.679
[17 empty] | 107 | 2024-12-07 | 294 | 0 | 0 | 591857.1615 | 698789.679
[17 empty] | 107 | 2024-12-08 | 295 | 0 | 0 | 591857.1615 | 698789.679
[17 empty] | 107 | 2024-12-09 | 296 | 2627.3674 | 3191.9199 | 594484.529 | 701981.5989
[17 empty] | 107 | 2024-12-10 | 297 | 2627.3674 | 3191.9199 | 597111.8964 | 705173.5188
[17 empty] | 107 | 2024-12-11 | 298 | 2627.3674 | 3191.9199 | 599739.2638 | 708365.4387
[17 empty] | 107 | 2024-12-12 | 299 | 2627.3674 | 3191.9199 | 602366.6313 | 711557.3586
[17 empty] | 107 | 2024-12-13 | 300 | 2627.3674 | 3191.9199 | 604993.9987 | 714749.2785
[17 empty] | 107 | 2024-12-14 | 301 | 0 | 0 | 604993.9987 | 714749.2785
[17 empty] | 107 | 2024-12-15 | 302 | 0 | 0 | 604993.9987 | 714749.2785
[17 empty] | 107 | 2024-12-16 | 303 | 2627.3674 | 3191.9199 | 607621.3662 | 717941.1984
[17 empty] | 107 | 2024-12-17 | 304 | 2627.3674 | 3191.9199 | 610248.7336 | 721133.1183
[17 empty] | 107 | 2024-12-18 | 305 | 2627.3674 | 3191.9199 | 612876.101 | 724325.0382
[17 empty] | 107 | 2024-12-19 | 306 | 2627.3674 | 3191.9199 | 615503.4685 | 727516.9581
[17 empty] | 107 | 2024-12-20 | 307 | 2627.3674 | 3191.9199 | 618130.8359 | 730708.878
[17 empty] | 107 | 2024-12-21 | 308 | 0 | 0 | 618130.8359 | 730708.878
[17 empty] | 107 | 2024-12-22 | 309 | 0 | 0 | 618130.8359 | 730708.878
[17 empty] | 107 | 2024-12-23 | 310 | 2627.3674 | 3191.9199 | 620758.2033 | 733900.7979
[17 empty] | 107 | 2024-12-24 | 311 | 2627.3674 | 3191.9199 | 623385.5708 | 737092.7178
[17 empty] | 107 | 2024-12-25 | 312 | 2627.3674 | 3191.9199 | 626012.9382 | 740284.6377
[17 empty] | 107 | 2024-12-26 | 313 | 2627.3674 | 3191.9199 | 628640.3056 | 743476.5576
[17 empty] | 107 | 2024-12-27 | 314 | 2627.3674 | 3191.9199 | 631267.6731 | 746668.4775
[17 empty] | 107 | 2024-12-28 | 315 | 0 | 0 | 631267.6731 | 746668.4775
[17 empty] | 107 | 2024-12-29 | 316 | 0 | 0 | 631267.6731 | 746668.4775
[17 empty] | 107 | 2024-12-30 | 317 | 2627.3674 | 3191.9199 | 633895.0405 | 749860.3974
[17 empty] | 107 | 2024-12-31 | 318 | 269.3674 | 315.1599 | 634164.4079 | 750175.5573
[17 empty] | 107 | 2025-01-01 | 319 | 269.3674 | 315.1599 | 634433.7754 | 750490.7172
[17 empty] | 107 | 2025-01-02 | 320 | 269.3674 | 315.1599 | 634703.1428 | 750805.8771
[17 empty] | 107 | 2025-01-03 | 321 | 269.3674 | 315.1599 | 634972.5103 | 751121.037
[17 empty] | 107 | 2025-01-04 | 322 | 0 | 0 | 634972.5103 | 751121.037
[17 empty] | 107 | 2025-01-05 | 323 | 0 | 0 | 634972.5103 | 751121.037
[17 empty] | 107 | 2025-01-06 | 324 | 269.3674 | 315.1599 | 635241.8777 | 751436.1969
[17 empty] | 107 | 2025-01-07 | 325 | 269.3674 | 315.1599 | 635511.2451 | 751751.3568
[17 empty] | 107 | 2025-01-08 | 326 | 269.3674 | 315.1599 | 635780.6126 | 752066.5167
[17 empty] | 107 | 2025-01-09 | 327 | 269.3674 | 315.1599 | 636049.98 | 752381.6766
[17 empty] | 109 | 2024-04-12 | 1 | 277.0144 | 304.7158 | 277.0144 | 304.7158
[17 empty] | 109 | 2024-04-13 | 2 | 0 | 0 | 277.0144 | 304.7158
[17 empty] | 109 | 2024-04-14 | 3 | 0 | 0 | 277.0144 | 304.7158
[17 empty] | 109 | 2024-04-15 | 4 | 277.0144 | 304.7158 | 554.0288 | 609.4317
[17 empty] | 109 | 2024-04-16 | 5 | 277.0144 | 304.7158 | 831.0432 | 914.1475
[17 empty] | 109 | 2024-04-17 | 6 | 1673.5858 | 1938.7044 | 2504.629 | 2852.8519
[17 empty] | 109 | 2024-04-18 | 7 | 1673.5858 | 1938.7044 | 4178.2149 | 4791.5563
[17 empty] | 109 | 2024-04-19 | 8 | 1673.5858 | 1938.7044 | 5851.8007 | 6730.2608
[17 empty] | 109 | 2024-04-20 | 9 | 0 | 0 | 5851.8007 | 6730.2608
[17 empty] | 109 | 2024-04-21 | 10 | 0 | 0 | 5851.8007 | 6730.2608
[17 empty] | 109 | 2024-04-22 | 11 | 1673.5858 | 1938.7044 | 7525.3865 | 8668.9652
[17 empty] | 109 | 2024-04-23 | 12 | 1673.5858 | 1938.7044 | 9198.9723 | 10607.6696
[17 empty] | 109 | 2024-04-24 | 13 | 1673.5858 | 1938.7044 | 10872.5582 | 12546.374
[17 empty] | 109 | 2024-04-25 | 14 | 1673.5858 | 1938.7044 | 12546.144 | 14485.0784
[17 empty] | 109 | 2024-04-26 | 15 | 1673.5858 | 1938.7044 | 14219.7298 | 16423.7828
[17 empty] | 109 | 2024-04-27 | 16 | 0 | 0 | 14219.7298 | 16423.7828
[17 empty] | 109 | 2024-04-28 | 17 | 0 | 0 | 14219.7298 | 16423.7828
[17 empty] | 109 | 2024-04-29 | 18 | 1673.5858 | 1938.7044 | 15893.3157 | 18362.4872
[17 empty] | 109 | 2024-04-30 | 19 | 1673.5858 | 1938.7044 | 17566.9015 | 20301.1916
[17 empty] | 109 | 2024-05-01 | 20 | 1673.5858 | 1938.7044 | 19240.4873 | 22239.896
[17 empty] | 109 | 2024-05-02 | 21 | 1673.5858 | 1938.7044 | 20914.0731 | 24178.6005
[17 empty] | 109 | 2024-05-03 | 22 | 1673.5858 | 1938.7044 | 22587.659 | 26117.3049
[17 empty] | 109 | 2024-05-04 | 23 | 0 | 0 | 22587.659 | 26117.3049
[17 empty] | 109 | 2024-05-05 | 24 | 0 | 0 | 22587.659 | 26117.3049
[17 empty] | 109 | 2024-05-06 | 25 | 3276.9542 | 3782.5781 | 25864.6132 | 29899.883
[17 empty] | 109 | 2024-05-07 | 26 | 1880.3828 | 2148.5895 | 27744.996 | 32048.4725
[17 empty] | 109 | 2024-05-08 | 27 | 1880.3828 | 2148.5895 | 29625.3789 | 34197.062
[17 empty] | 109 | 2024-05-09 | 28 | 1880.3828 | 2148.5895 | 31505.7617 | 36345.6515
[17 empty] | 109 | 2024-05-10 | 29 | 1880.3828 | 2148.5895 | 33386.1445 | 38494.2411
[17 empty] | 109 | 2024-05-11 | 30 | 0 | 0 | 33386.1445 | 38494.2411
[17 empty] | 109 | 2024-05-12 | 31 | 0 | 0 | 33386.1445 | 38494.2411
[17 empty] | 109 | 2024-05-13 | 32 | 1880.3828 | 2148.5895 | 35266.5273 | 40642.8306
[17 empty] | 109 | 2024-05-14 | 33 | 1880.3828 | 2148.5895 | 37146.9101 | 42791.4201
[17 empty] | 109 | 2024-05-15 | 34 | 1880.3828 | 2148.5895 | 39027.293 | 44940.0096
[17 empty] | 109 | 2024-05-16 | 35 | 1880.3828 | 2148.5895 | 40907.6758 | 47088.5992
[17 empty] | 109 | 2024-05-17 | 36 | 1880.3828 | 2148.5895 | 42788.0586 | 49237.1887
[17 empty] | 109 | 2024-05-18 | 37 | 0 | 0 | 42788.0586 | 49237.1887
[17 empty] | 109 | 2024-05-19 | 38 | 0 | 0 | 42788.0586 | 49237.1887
[17 empty] | 109 | 2024-05-20 | 39 | 1880.3828 | 2148.5895 | 44668.4414 | 51385.7782
[17 empty] | 109 | 2024-05-21 | 40 | 1880.3828 | 2148.5895 | 46548.8243 | 53534.3677
[17 empty] | 109 | 2024-05-22 | 41 | 1880.3828 | 2148.5895 | 48429.2071 | 55682.9573
[17 empty] | 109 | 2024-05-23 | 42 | 1880.3828 | 2148.5895 | 50309.5899 | 57831.5468
[17 empty] | 109 | 2024-05-24 | 43 | 1880.3828 | 2148.5895 | 52189.9727 | 59980.1363
[17 empty] | 109 | 2024-05-25 | 44 | 0 | 0 | 52189.9727 | 59980.1363
[17 empty] | 109 | 2024-05-26 | 45 | 0 | 0 | 52189.9727 | 59980.1363
[17 empty] | 109 | 2024-05-27 | 46 | 1880.3828 | 2148.5895 | 54070.3555 | 62128.7258
[17 empty] | 109 | 2024-05-28 | 47 | 1880.3828 | 2148.5895 | 55950.7384 | 64277.3154
[17 empty] | 109 | 2024-05-29 | 48 | 1880.3828 | 2148.5895 | 57831.1212 | 66425.9049
[17 empty] | 109 | 2024-05-30 | 49 | 1880.3828 | 2148.5895 | 59711.504 | 68574.4944
[17 empty] | 109 | 2024-05-31 | 50 | 1880.3828 | 2148.5895 | 61591.8868 | 70723.0839
[17 empty] | 109 | 2024-06-01 | 51 | 0 | 0 | 61591.8868 | 70723.0839
[17 empty] | 109 | 2024-06-02 | 52 | 0 | 0 | 61591.8868 | 70723.0839
[17 empty] | 109 | 2024-06-03 | 53 | 1880.3828 | 2148.5895 | 63472.2696 | 72871.6734
[17 empty] | 109 | 2024-06-04 | 54 | 1880.3828 | 2148.5895 | 65352.6525 | 75020.263
[17 empty] | 109 | 2024-06-05 | 55 | 1880.3828 | 2148.5895 | 67233.0353 | 77168.8525
[17 empty] | 109 | 2024-06-06 | 56 | 1880.3828 | 2148.5895 | 69113.4181 | 79317.442
[17 empty] | 109 | 2024-06-07 | 57 | 1880.3828 | 2148.5895 | 70993.8009 | 81466.0315
[17 empty] | 109 | 2024-06-08 | 58 | 0 | 0 | 70993.8009 | 81466.0315
[17 empty] | 109 | 2024-06-09 | 59 | 0 | 0 | 70993.8009 | 81466.0315
[17 empty] | 109 | 2024-06-10 | 60 | 1880.3828 | 2148.5895 | 72874.1837 | 83614.6211
[17 empty] | 109 | 2024-06-11 | 61 | 1880.3828 | 2148.5895 | 74754.5666 | 85763.2106
[17 empty] | 109 | 2024-06-12 | 62 | 1880.3828 | 2148.5895 | 76634.9494 | 87911.8001
[17 empty] | 109 | 2024-06-13 | 63 | 1880.3828 | 2148.5895 | 78515.3322 | 90060.3896
[17 empty] | 109 | 2024-06-14 | 64 | 1880.3828 | 2148.5895 | 80395.715 | 92208.9792
[17 empty] | 109 | 2024-06-15 | 65 | 0 | 0 | 80395.715 | 92208.9792
[17 empty] | 109 | 2024-06-16 | 66 | 0 | 0 | 80395.715 | 92208.9792
[17 empty] | 109 | 2024-06-17 | 67 | 1880.3828 | 2148.5895 | 82276.0979 | 94357.5687
[17 empty] | 109 | 2024-06-18 | 68 | 1880.3828 | 2148.5895 | 84156.4807 | 96506.1582
[17 empty] | 109 | 2024-06-19 | 69 | 1880.3828 | 2148.5895 | 86036.8635 | 98654.7477
[17 empty] | 109 | 2024-06-20 | 70 | 1880.3828 | 2148.5895 | 87917.2463 | 100803.3373
[17 empty] | 109 | 2024-06-21 | 71 | 1880.3828 | 2148.5895 | 89797.6291 | 102951.9268
[17 empty] | 109 | 2024-06-22 | 72 | 0 | 0 | 89797.6291 | 102951.9268
[17 empty] | 109 | 2024-06-23 | 73 | 0 | 0 | 89797.6291 | 102951.9268
[17 empty] | 109 | 2024-06-24 | 74 | 1880.3828 | 2148.5895 | 91678.012 | 105100.5163
[17 empty] | 109 | 2024-06-25 | 75 | 1880.3828 | 2148.5895 | 93558.3948 | 107249.1058
[17 empty] | 109 | 2024-06-26 | 76 | 1880.3828 | 2148.5895 | 95438.7776 | 109397.6954
[17 empty] | 109 | 2024-06-27 | 77 | 1880.3828 | 2148.5895 | 97319.1604 | 111546.2849
[17 empty] | 109 | 2024-06-28 | 78 | 1880.3828 | 2148.5895 | 99199.5432 | 113694.8744
[17 empty] | 109 | 2024-06-29 | 79 | 0 | 0 | 99199.5432 | 113694.8744
[17 empty] | 109 | 2024-06-30 | 80 | 0 | 0 | 99199.5432 | 113694.8744
[17 empty] | 109 | 2024-07-01 | 81 | 1880.3828 | 2148.5895 | 101079.9261 | 115843.4639
[17 empty] | 109 | 2024-07-02 | 82 | 1880.3828 | 2148.5895 | 102960.3089 | 117992.0535
[17 empty] | 109 | 2024-07-03 | 83 | 4412.9345 | 5390.2557 | 107373.2434 | 123382.3092
[17 empty] | 109 | 2024-07-04 | 84 | 4412.9345 | 5390.2557 | 111786.178 | 128772.5649
[17 empty] | 109 | 2024-07-05 | 85 | 4412.9345 | 5390.2557 | 116199.1125 | 134162.8207
[17 empty] | 109 | 2024-07-06 | 86 | 0 | 0 | 116199.1125 | 134162.8207
[17 empty] | 109 | 2024-07-07 | 87 | 0 | 0 | 116199.1125 | 134162.8207
[17 empty] | 109 | 2024-07-08 | 88 | 4412.9345 | 5390.2557 | 120612.0471 | 139553.0764
[17 empty] | 109 | 2024-07-09 | 89 | 4412.9345 | 5390.2557 | 125024.9816 | 144943.3321
[17 empty] | 109 | 2024-07-10 | 90 | 4412.9345 | 5390.2557 | 129437.9162 | 150333.5878
[17 empty] | 109 | 2024-07-11 | 91 | 4412.9345 | 5390.2557 | 133850.8507 | 155723.8436
[17 empty] | 109 | 2024-07-12 | 92 | 4412.9345 | 5390.2557 | 138263.7852 | 161114.0993
[17 empty] | 109 | 2024-07-13 | 93 | 0 | 0 | 138263.7852 | 161114.0993
[17 empty] | 109 | 2024-07-14 | 94 | 0 | 0 | 138263.7852 | 161114.0993
[17 empty] | 109 | 2024-07-15 | 95 | 6542.9345 | 7733.2557 | 144806.7198 | 168847.355
[17 empty] | 109 | 2024-07-16 | 96 | 6542.9345 | 7733.2557 | 151349.6543 | 176580.6108
[17 empty] | 109 | 2024-07-17 | 97 | 6542.9345 | 7733.2557 | 157892.5889 | 184313.8665
[17 empty] | 109 | 2024-07-18 | 98 | 6542.9345 | 7733.2557 | 164435.5234 | 192047.1222
[17 empty] | 109 | 2024-07-19 | 99 | 6542.9345 | 7733.2557 | 170978.458 | 199780.378
[17 empty] | 109 | 2024-07-20 | 100 | 0 | 0 | 170978.458 | 199780.378
[17 empty] | 109 | 2024-07-21 | 101 | 0 | 0 | 170978.458 | 199780.378
[17 empty] | 109 | 2024-07-22 | 102 | 6542.9345 | 7733.2557 | 177521.3925 | 207513.6337
[17 empty] | 109 | 2024-07-23 | 103 | 6542.9345 | 7733.2557 | 184064.3271 | 215246.8894
[17 empty] | 109 | 2024-07-24 | 104 | 4939.5661 | 5889.382 | 189003.8932 | 221136.2715
[17 empty] | 109 | 2024-07-25 | 105 | 4939.5661 | 5889.382 | 193943.4593 | 227025.6535
[17 empty] | 109 | 2024-07-26 | 106 | 4939.5661 | 5889.382 | 198883.0254 | 232915.0356
[17 empty] | 109 | 2024-07-27 | 107 | 0 | 0 | 198883.0254 | 232915.0356
[17 empty] | 109 | 2024-07-28 | 108 | 0 | 0 | 198883.0254 | 232915.0356
[17 empty] | 109 | 2024-07-29 | 109 | 4939.5661 | 5889.382 | 203822.5916 | 238804.4176
[17 empty] | 109 | 2024-07-30 | 110 | 4939.5661 | 5889.382 | 208762.1577 | 244693.7997
[17 empty] | 109 | 2024-07-31 | 111 | 4939.5661 | 5889.382 | 213701.7238 | 250583.1817
[17 empty] | 109 | 2024-08-01 | 112 | 4939.5661 | 5889.382 | 218641.2899 | 256472.5638
[17 empty] | 109 | 2024-08-02 | 113 | 4939.5661 | 5889.382 | 223580.8561 | 262361.9458
[17 empty] | 109 | 2024-08-03 | 114 | 0 | 0 | 223580.8561 | 262361.9458
[17 empty] | 109 | 2024-08-04 | 115 | 0 | 0 | 223580.8561 | 262361.9458
[17 empty] | 109 | 2024-08-05 | 116 | 4939.5661 | 5889.382 | 228520.4222 | 268251.3278
[17 empty] | 109 | 2024-08-06 | 117 | 4939.5661 | 5889.382 | 233459.9883 | 274140.7099
[17 empty] | 109 | 2024-08-07 | 118 | 4939.5661 | 5889.382 | 238399.5544 | 280030.0919
[17 empty] | 109 | 2024-08-08 | 119 | 4939.5661 | 5889.382 | 243339.1206 | 285919.474
[17 empty] | 109 | 2024-08-09 | 120 | 4939.5661 | 5889.382 | 248278.6867 | 291808.856
[17 empty] | 109 | 2024-08-10 | 121 | 0 | 0 | 248278.6867 | 291808.856
[17 empty] | 109 | 2024-08-11 | 122 | 0 | 0 | 248278.6867 | 291808.856
[17 empty] | 109 | 2024-08-12 | 123 | 4939.5661 | 5889.382 | 253218.2528 | 297698.2381
[17 empty] | 109 | 2024-08-13 | 124 | 2407.0144 | 2647.7158 | 255625.2672 | 300345.9539
[17 empty] | 109 | 2024-08-14 | 125 | 2407.0144 | 2647.7158 | 258032.2816 | 302993.6698
[17 empty] | 109 | 2024-08-15 | 126 | 2407.0144 | 2647.7158 | 260439.296 | 305641.3856
[17 empty] | 109 | 2024-08-16 | 127 | 2407.0144 | 2647.7158 | 262846.3104 | 308289.1014
[17 empty] | 109 | 2024-08-17 | 128 | 0 | 0 | 262846.3104 | 308289.1014
[17 empty] | 109 | 2024-08-18 | 129 | 0 | 0 | 262846.3104 | 308289.1014
[17 empty] | 109 | 2024-08-19 | 130 | 2407.0144 | 2647.7158 | 265253.3248 | 310936.8173
[17 empty] | 109 | 2024-08-20 | 131 | 2407.0144 | 2647.7158 | 267660.3392 | 313584.5331
[17 empty] | 109 | 2024-08-21 | 132 | 2407.0144 | 2647.7158 | 270067.3536 | 316232.249
[17 empty] | 109 | 2024-08-22 | 133 | 2407.0144 | 2647.7158 | 272474.368 | 318879.9648
[17 empty] | 109 | 2024-08-23 | 134 | 2407.0144 | 2647.7158 | 274881.3824 | 321527.6806
[17 empty] | 109 | 2024-08-24 | 135 | 0 | 0 | 274881.3824 | 321527.6806
[17 empty] | 109 | 2024-08-25 | 136 | 0 | 0 | 274881.3824 | 321527.6806
[17 empty] | 109 | 2024-08-26 | 137 | 2407.0144 | 2647.7158 | 277288.3968 | 324175.3965
[17 empty] | 109 | 2024-08-27 | 138 | 2407.0144 | 2647.7158 | 279695.4112 | 326823.1123
[17 empty] | 109 | 2024-08-28 | 139 | 2407.0144 | 2647.7158 | 282102.4256 | 329470.8282
[17 empty] | 109 | 2024-08-29 | 140 | 2407.0144 | 2647.7158 | 284509.44 | 332118.544
[17 empty] | 109 | 2024-08-30 | 141 | 2407.0144 | 2647.7158 | 286916.4544 | 334766.2598
[17 empty] | 109 | 2024-08-31 | 142 | 0 | 0 | 286916.4544 | 334766.2598
[17 empty] | 109 | 2024-09-01 | 143 | 0 | 0 | 286916.4544 | 334766.2598
[17 empty] | 109 | 2024-09-02 | 144 | 2407.0144 | 2647.7158 | 289323.4688 | 337413.9757
[17 empty] | 109 | 2024-09-03 | 145 | 2407.0144 | 2647.7158 | 291730.4832 | 340061.6915
[17 empty] | 109 | 2024-09-04 | 146 | 2407.0144 | 2647.7158 | 294137.4976 | 342709.4074
[17 empty] | 109 | 2024-09-05 | 147 | 2407.0144 | 2647.7158 | 296544.512 | 345357.1232
[17 empty] | 109 | 2024-09-06 | 148 | 2407.0144 | 2647.7158 | 298951.5264 | 348004.839
[17 empty] | 109 | 2024-09-07 | 149 | 0 | 0 | 298951.5264 | 348004.839
[17 empty] | 109 | 2024-09-08 | 150 | 0 | 0 | 298951.5264 | 348004.839
[17 empty] | 109 | 2024-09-09 | 151 | 2407.0144 | 2647.7158 | 301358.5408 | 350652.5549
[17 empty] | 109 | 2024-09-10 | 152 | 2407.0144 | 2647.7158 | 303765.5552 | 353300.2707
[17 empty] | 109 | 2024-09-11 | 153 | 2407.0144 | 2647.7158 | 306172.5696 | 355947.9866
[17 empty] | 109 | 2024-09-12 | 154 | 2407.0144 | 2647.7158 | 308579.584 | 358595.7024
[17 empty] | 109 | 2024-09-13 | 155 | 2407.0144 | 2647.7158 | 310986.5984 | 361243.4182
[17 empty] | 109 | 2024-09-14 | 156 | 0 | 0 | 310986.5984 | 361243.4182
[17 empty] | 109 | 2024-09-15 | 157 | 0 | 0 | 310986.5984 | 361243.4182
[17 empty] | 109 | 2024-09-16 | 158 | 2407.0144 | 2647.7158 | 313393.6128 | 363891.1341
[17 empty] | 109 | 2024-09-17 | 159 | 2407.0144 | 2647.7158 | 315800.6272 | 366538.8499
[17 empty] | 109 | 2024-09-18 | 160 | 2407.0144 | 2647.7158 | 318207.6416 | 369186.5658
[17 empty] | 109 | 2024-09-19 | 161 | 2407.0144 | 2647.7158 | 320614.656 | 371834.2816
[17 empty] | 109 | 2024-09-20 | 162 | 2407.0144 | 2647.7158 | 323021.6704 | 374481.9974
[17 empty] | 109 | 2024-09-21 | 163 | 0 | 0 | 323021.6704 | 374481.9974
[17 empty] | 109 | 2024-09-22 | 164 | 0 | 0 | 323021.6704 | 374481.9974
[17 empty] | 109 | 2024-09-23 | 165 | 2407.0144 | 2647.7158 | 325428.6848 | 377129.7133
[17 empty] | 109 | 2024-09-24 | 166 | 2407.0144 | 2647.7158 | 327835.6992 | 379777.4291
[17 empty] | 109 | 2024-09-25 | 167 | 2407.0144 | 2647.7158 | 330242.7136 | 382425.145
[17 empty] | 109 | 2024-09-26 | 168 | 2407.0144 | 2647.7158 | 332649.728 | 385072.8608
[17 empty] | 109 | 2024-09-27 | 169 | 2407.0144 | 2647.7158 | 335056.7424 | 387720.5766
[17 empty] | 109 | 2024-09-28 | 170 | 0 | 0 | 335056.7424 | 387720.5766
[17 empty] | 109 | 2024-09-29 | 171 | 0 | 0 | 335056.7424 | 387720.5766
[17 empty] | 109 | 2024-09-30 | 172 | 2407.0144 | 2647.7158 | 337463.7568 | 390368.2925
[17 empty] | 109 | 2024-10-01 | 173 | 2407.0144 | 2647.7158 | 339870.7712 | 393016.0083
[17 empty] | 109 | 2024-10-02 | 174 | 2407.0144 | 2647.7158 | 342277.7856 | 395663.7242
[17 empty] | 109 | 2024-10-03 | 175 | 2407.0144 | 2647.7158 | 344684.8 | 398311.44
[17 empty] | 109 | 2024-10-04 | 176 | 2407.0144 | 2647.7158 | 347091.8144 | 400959.1558
[17 empty] | 109 | 2024-10-05 | 177 | 0 | 0 | 347091.8144 | 400959.1558
[17 empty] | 109 | 2024-10-06 | 178 | 0 | 0 | 347091.8144 | 400959.1558
[17 empty] | 109 | 2024-10-07 | 179 | 2407.0144 | 2647.7158 | 349498.8288 | 403606.8717
[17 empty] | 109 | 2024-10-08 | 180 | 2407.0144 | 2647.7158 | 351905.8432 | 406254.5875
[17 empty] | 109 | 2024-10-09 | 181 | 2407.0144 | 2647.7158 | 354312.8576 | 408902.3034
[17 empty] | 109 | 2024-10-10 | 182 | 2407.0144 | 2647.7158 | 356719.872 | 411550.0192
[17 empty] | 109 | 2024-10-11 | 183 | 2407.0144 | 2647.7158 | 359126.8864 | 414197.735
[17 empty] | 109 | 2024-10-12 | 184 | 0 | 0 | 359126.8864 | 414197.735
[17 empty] | 109 | 2024-10-13 | 185 | 0 | 0 | 359126.8864 | 414197.735
[17 empty] | 109 | 2024-10-14 | 186 | 2407.0144 | 2647.7158 | 361533.9008 | 416845.4509
[17 empty] | 109 | 2024-10-15 | 187 | 2407.0144 | 2647.7158 | 363940.9152 | 419493.1667
[17 empty] | 109 | 2024-10-16 | 188 | 2407.0144 | 2647.7158 | 366347.9296 | 422140.8826
[17 empty] | 109 | 2024-10-17 | 189 | 2407.0144 | 2647.7158 | 368754.944 | 424788.5984
[17 empty] | 109 | 2024-10-18 | 190 | 2407.0144 | 2647.7158 | 371161.9584 | 427436.3142
[17 empty] | 109 | 2024-10-19 | 191 | 0 | 0 | 371161.9584 | 427436.3142
[17 empty] | 109 | 2024-10-20 | 192 | 0 | 0 | 371161.9584 | 427436.3142
[17 empty] | 109 | 2024-10-21 | 193 | 2407.0144 | 2647.7158 | 373568.9728 | 430084.0301
[17 empty] | 109 | 2024-10-22 | 194 | 2407.0144 | 2647.7158 | 375975.9872 | 432731.7459
[17 empty] | 109 | 2024-10-23 | 195 | 2407.0144 | 2647.7158 | 378383.0016 | 435379.4618
[17 empty] | 109 | 2024-10-24 | 196 | 2407.0144 | 2647.7158 | 380790.016 | 438027.1776
[17 empty] | 109 | 2024-10-25 | 197 | 2407.0144 | 2647.7158 | 383197.0304 | 440674.8934
[17 empty] | 109 | 2024-10-26 | 198 | 0 | 0 | 383197.0304 | 440674.8934
[17 empty] | 109 | 2024-10-27 | 199 | 0 | 0 | 383197.0304 | 440674.8934
[17 empty] | 109 | 2024-10-28 | 200 | 2407.0144 | 2647.7158 | 385604.0448 | 443322.6093
[17 empty] | 109 | 2024-10-29 | 201 | 277.0144 | 304.7158 | 385881.0592 | 443627.3251
[17 empty] | 109 | 2024-10-30 | 202 | 277.0144 | 304.7158 | 386158.0736 | 443932.041
[17 empty] | 109 | 2024-10-31 | 203 | 277.0144 | 304.7158 | 386435.088 | 444236.7568
[17 empty] | 109 | 2024-11-01 | 204 | 277.0144 | 304.7158 | 386712.1024 | 444541.4726
[17 empty] | 109 | 2024-11-02 | 205 | 0 | 0 | 386712.1024 | 444541.4726
[17 empty] | 109 | 2024-11-03 | 206 | 0 | 0 | 386712.1024 | 444541.4726
[17 empty] | 109 | 2024-11-04 | 207 | 277.0144 | 304.7158 | 386989.1168 | 444846.1885
[17 empty] | 109 | 2024-11-05 | 208 | 277.0144 | 304.7158 | 387266.1312 | 445150.9043
[17 empty] | 109 | 2024-11-06 | 209 | 277.0144 | 304.7158 | 387543.1456 | 445455.6202
[17 empty] | 109 | 2024-11-07 | 210 | 277.0144 | 304.7158 | 387820.16 | 445760.336
[17 empty] | 110 | 2024-02-27 | 1 | 389.0944 | 474.6952 | 389.0944 | 474.6952
[17 empty] | 110 | 2024-02-28 | 2 | 389.0944 | 474.6952 | 778.1889 | 949.3904
[17 empty] | 110 | 2024-02-29 | 3 | 389.0944 | 474.6952 | 1167.2833 | 1424.0856
[17 empty] | 110 | 2024-03-01 | 4 | 389.0944 | 474.6952 | 1556.3778 | 1898.7809
[17 empty] | 110 | 2024-03-02 | 5 | 0 | 0 | 1556.3778 | 1898.7809
[17 empty] | 110 | 2024-03-03 | 6 | 0 | 0 | 1556.3778 | 1898.7809
[17 empty] | 110 | 2024-03-04 | 7 | 3850.0944 | 4627.8952 | 5406.4722 | 6526.6761
[17 empty] | 110 | 2024-03-05 | 8 | 3850.0944 | 4627.8952 | 9256.5666 | 11154.5713
[17 empty] | 110 | 2024-03-06 | 9 | 3850.0944 | 4627.8952 | 13106.6611 | 15782.4665
[17 empty] | 110 | 2024-03-07 | 10 | 3850.0944 | 4627.8952 | 16956.7555 | 20410.3617
[17 empty] | 110 | 2024-03-08 | 11 | 3850.0944 | 4627.8952 | 20806.8499 | 25038.2569
[17 empty] | 110 | 2024-03-09 | 12 | 0 | 0 | 20806.8499 | 25038.2569
[17 empty] | 110 | 2024-03-10 | 13 | 0 | 0 | 20806.8499 | 25038.2569
[17 empty] | 110 | 2024-03-11 | 14 | 3850.0944 | 4627.8952 | 24656.9444 | 29666.1521
[17 empty] | 110 | 2024-03-12 | 15 | 3850.0944 | 4627.8952 | 28507.0388 | 34294.0474
[17 empty] | 110 | 2024-03-13 | 16 | 3850.0944 | 4627.8952 | 32357.1333 | 38921.9426
[17 empty] | 110 | 2024-03-14 | 17 | 3850.0944 | 4627.8952 | 36207.2277 | 43549.8378
[17 empty] | 110 | 2024-03-15 | 18 | 3850.0944 | 4627.8952 | 40057.3221 | 48177.733
[17 empty] | 110 | 2024-03-16 | 19 | 0 | 0 | 40057.3221 | 48177.733
[17 empty] | 110 | 2024-03-17 | 20 | 0 | 0 | 40057.3221 | 48177.733
[17 empty] | 110 | 2024-03-18 | 21 | 3850.0944 | 4627.8952 | 43907.4166 | 52805.6282
[17 empty] | 110 | 2024-03-19 | 22 | 3850.0944 | 4627.8952 | 47757.511 | 57433.5234
[17 empty] | 110 | 2024-03-20 | 23 | 3850.0944 | 4627.8952 | 51607.6054 | 62061.4186
[17 empty] | 110 | 2024-03-21 | 24 | 7811.4898 | 9500.4115 | 59419.0952 | 71561.8301
[17 empty] | 110 | 2024-03-22 | 25 | 4350.4898 | 5347.2115 | 63769.585 | 76909.0416
[17 empty] | 110 | 2024-03-23 | 26 | 0 | 0 | 63769.585 | 76909.0416
[17 empty] | 110 | 2024-03-24 | 27 | 0 | 0 | 63769.585 | 76909.0416
[17 empty] | 110 | 2024-03-25 | 28 | 4350.4898 | 5347.2115 | 68120.0748 | 82256.2531
[17 empty] | 110 | 2024-03-26 | 29 | 4350.4898 | 5347.2115 | 72470.5646 | 87603.4646
[17 empty] | 110 | 2024-03-27 | 30 | 4350.4898 | 5347.2115 | 76821.0544 | 92950.6761
[17 empty] | 110 | 2024-03-28 | 31 | 4350.4898 | 5347.2115 | 81171.5442 | 98297.8876
[17 empty] | 110 | 2024-03-29 | 32 | 4350.4898 | 5347.2115 | 85522.034 | 103645.0991
[17 empty] | 110 | 2024-03-30 | 33 | 0 | 0 | 85522.034 | 103645.0991
[17 empty] | 110 | 2024-03-31 | 34 | 0 | 0 | 85522.034 | 103645.0991
[17 empty] | 110 | 2024-04-01 | 35 | 4350.4898 | 5347.2115 | 89872.5237 | 108992.3106
[17 empty] | 110 | 2024-04-02 | 36 | 4350.4898 | 5347.2115 | 94223.0135 | 114339.5221
[17 empty] | 110 | 2024-04-03 | 37 | 4350.4898 | 5347.2115 | 98573.5033 | 119686.7336
[17 empty] | 110 | 2024-04-04 | 38 | 4350.4898 | 5347.2115 | 102923.9931 | 125033.9451
[17 empty] | 110 | 2024-04-05 | 39 | 4350.4898 | 5347.2115 | 107274.4829 | 130381.1566
[17 empty] | 110 | 2024-04-06 | 40 | 0 | 0 | 107274.4829 | 130381.1566
[17 empty] | 110 | 2024-04-07 | 41 | 0 | 0 | 107274.4829 | 130381.1566
[17 empty] | 110 | 2024-04-08 | 42 | 4350.4898 | 5347.2115 | 111624.9727 | 135728.3681
[17 empty] | 110 | 2024-04-09 | 43 | 4350.4898 | 5347.2115 | 115975.4625 | 141075.5795
[17 empty] | 110 | 2024-04-10 | 44 | 4350.4898 | 5347.2115 | 120325.9522 | 146422.791
[17 empty] | 110 | 2024-04-11 | 45 | 4350.4898 | 5347.2115 | 124676.442 | 151770.0025
[17 empty] | 110 | 2024-04-12 | 46 | 4350.4898 | 5347.2115 | 129026.9318 | 157117.214
[17 empty] | 110 | 2024-04-13 | 47 | 0 | 0 | 129026.9318 | 157117.214
[17 empty] | 110 | 2024-04-14 | 48 | 0 | 0 | 129026.9318 | 157117.214
[17 empty] | 110 | 2024-04-15 | 49 | 4350.4898 | 5347.2115 | 133377.4216 | 162464.4255
[17 empty] | 110 | 2024-04-16 | 50 | 4350.4898 | 5347.2115 | 137727.9114 | 167811.637
[17 empty] | 110 | 2024-04-17 | 51 | 4350.4898 | 5347.2115 | 142078.4012 | 173158.8485
[17 empty] | 110 | 2024-04-18 | 52 | 4350.4898 | 5347.2115 | 146428.891 | 178506.06
[17 empty] | 110 | 2024-04-19 | 53 | 4350.4898 | 5347.2115 | 150779.3808 | 183853.2715
[17 empty] | 110 | 2024-04-20 | 54 | 0 | 0 | 150779.3808 | 183853.2715
[17 empty] | 110 | 2024-04-21 | 55 | 0 | 0 | 150779.3808 | 183853.2715
[17 empty] | 110 | 2024-04-22 | 56 | 4350.4898 | 5347.2115 | 155129.8705 | 189200.483
[17 empty] | 110 | 2024-04-23 | 57 | 4350.4898 | 5347.2115 | 159480.3603 | 194547.6945
[17 empty] | 110 | 2024-04-24 | 58 | 4350.4898 | 5347.2115 | 163830.8501 | 199894.906
[17 empty] | 110 | 2024-04-25 | 59 | 4350.4898 | 5347.2115 | 168181.3399 | 205242.1175
[17 empty] | 110 | 2024-04-26 | 60 | 4350.4898 | 5347.2115 | 172531.8297 | 210589.329
[17 empty] | 110 | 2024-04-27 | 61 | 0 | 0 | 172531.8297 | 210589.329
[17 empty] | 110 | 2024-04-28 | 62 | 0 | 0 | 172531.8297 | 210589.329
[17 empty] | 110 | 2024-04-29 | 63 | 4350.4898 | 5347.2115 | 176882.3195 | 215936.5405
[17 empty] | 110 | 2024-04-30 | 64 | 4350.4898 | 5347.2115 | 181232.8093 | 221283.7519
[17 empty] | 110 | 2024-05-01 | 65 | 4350.4898 | 5347.2115 | 185583.299 | 226630.9634
[17 empty] | 110 | 2024-05-02 | 66 | 4350.4898 | 5347.2115 | 189933.7888 | 231978.1749
[17 empty] | 110 | 2024-05-03 | 67 | 4350.4898 | 5347.2115 | 194284.2786 | 237325.3864
[17 empty] | 110 | 2024-05-04 | 68 | 0 | 0 | 194284.2786 | 237325.3864
[17 empty] | 110 | 2024-05-05 | 69 | 0 | 0 | 194284.2786 | 237325.3864
[17 empty] | 110 | 2024-05-06 | 70 | 4350.4898 | 5347.2115 | 198634.7684 | 242672.5979
[17 empty] | 110 | 2024-05-07 | 71 | 4350.4898 | 5347.2115 | 202985.2582 | 248019.8094
[17 empty] | 110 | 2024-05-08 | 72 | 4350.4898 | 5347.2115 | 207335.748 | 253367.0209
[17 empty] | 110 | 2024-05-09 | 73 | 4350.4898 | 5347.2115 | 211686.2378 | 258714.2324
[17 empty] | 110 | 2024-05-10 | 74 | 4350.4898 | 5347.2115 | 216036.7276 | 264061.4439
[17 empty] | 110 | 2024-05-11 | 75 | 0 | 0 | 216036.7276 | 264061.4439
[17 empty] | 110 | 2024-05-12 | 76 | 0 | 0 | 216036.7276 | 264061.4439
[17 empty] | 110 | 2024-05-13 | 77 | 4350.4898 | 5347.2115 | 220387.2173 | 269408.6554
[17 empty] | 110 | 2024-05-14 | 78 | 4350.4898 | 5347.2115 | 224737.7071 | 274755.8669
[17 empty] | 110 | 2024-05-15 | 79 | 4350.4898 | 5347.2115 | 229088.1969 | 280103.0784
[17 empty] | 110 | 2024-05-16 | 80 | 4350.4898 | 5347.2115 | 233438.6867 | 285450.2899
[17 empty] | 110 | 2024-05-17 | 81 | 4350.4898 | 5347.2115 | 237789.1765 | 290797.5014
[17 empty] | 110 | 2024-05-18 | 82 | 0 | 0 | 237789.1765 | 290797.5014
[17 empty] | 110 | 2024-05-19 | 83 | 0 | 0 | 237789.1765 | 290797.5014
[17 empty] | 110 | 2024-05-20 | 84 | 4350.4898 | 5347.2115 | 242139.6663 | 296144.7129
[17 empty] | 110 | 2024-05-21 | 85 | 4350.4898 | 5347.2115 | 246490.1561 | 301491.9243
[17 empty] | 110 | 2024-05-22 | 86 | 4350.4898 | 5347.2115 | 250840.6458 | 306839.1358
[17 empty] | 110 | 2024-05-23 | 87 | 4350.4898 | 5347.2115 | 255191.1356 | 312186.3473
[17 empty] | 110 | 2024-05-24 | 88 | 4350.4898 | 5347.2115 | 259541.6254 | 317533.5588
[17 empty] | 110 | 2024-05-25 | 89 | 0 | 0 | 259541.6254 | 317533.5588
[17 empty] | 110 | 2024-05-26 | 90 | 0 | 0 | 259541.6254 | 317533.5588
[17 empty] | 110 | 2024-05-27 | 91 | 4350.4898 | 5347.2115 | 263892.1152 | 322880.7703
[17 empty] | 110 | 2024-05-28 | 92 | 4350.4898 | 5347.2115 | 268242.605 | 328227.9818
[17 empty] | 110 | 2024-05-29 | 93 | 4350.4898 | 5347.2115 | 272593.0948 | 333575.1933
[17 empty] | 110 | 2024-05-30 | 94 | 4350.4898 | 5347.2115 | 276943.5846 | 338922.4048
[17 empty] | 110 | 2024-05-31 | 95 | 4350.4898 | 5347.2115 | 281294.0744 | 344269.6163
[17 empty] | 110 | 2024-06-01 | 96 | 0 | 0 | 281294.0744 | 344269.6163
[17 empty] | 110 | 2024-06-02 | 97 | 0 | 0 | 281294.0744 | 344269.6163
[17 empty] | 110 | 2024-06-03 | 98 | 4350.4898 | 5347.2115 | 285644.5641 | 349616.8278
[17 empty] | 110 | 2024-06-04 | 99 | 4350.4898 | 5347.2115 | 289995.0539 | 354964.0393
[17 empty] | 110 | 2024-06-05 | 100 | 4350.4898 | 5347.2115 | 294345.5437 | 360311.2508
[17 empty] | 110 | 2024-06-06 | 101 | 4350.4898 | 5347.2115 | 298696.0335 | 365658.4623
[17 empty] | 110 | 2024-06-07 | 102 | 4350.4898 | 5347.2115 | 303046.5233 | 371005.6738
[17 empty] | 110 | 2024-06-08 | 103 | 0 | 0 | 303046.5233 | 371005.6738
[17 empty] | 110 | 2024-06-09 | 104 | 0 | 0 | 303046.5233 | 371005.6738
[17 empty] | 110 | 2024-06-10 | 105 | 4350.4898 | 5347.2115 | 307397.0131 | 376352.8853
[17 empty] | 110 | 2024-06-11 | 106 | 4350.4898 | 5347.2115 | 311747.5029 | 381700.0967
[17 empty] | 110 | 2024-06-12 | 107 | 4350.4898 | 5347.2115 | 316097.9926 | 387047.3082
[17 empty] | 110 | 2024-06-13 | 108 | 4350.4898 | 5347.2115 | 320448.4824 | 392394.5197
[17 empty] | 110 | 2024-06-14 | 109 | 4350.4898 | 5347.2115 | 324798.9722 | 397741.7312
[17 empty] | 110 | 2024-06-15 | 110 | 0 | 0 | 324798.9722 | 397741.7312
[17 empty] | 110 | 2024-06-16 | 111 | 0 | 0 | 324798.9722 | 397741.7312
[17 empty] | 110 | 2024-06-17 | 112 | 4350.4898 | 5347.2115 | 329149.462 | 403088.9427
[17 empty] | 110 | 2024-06-18 | 113 | 4350.4898 | 5347.2115 | 333499.9518 | 408436.1542
[17 empty] | 110 | 2024-06-19 | 114 | 4350.4898 | 5347.2115 | 337850.4416 | 413783.3657
[17 empty] | 110 | 2024-06-20 | 115 | 4350.4898 | 5347.2115 | 342200.9314 | 419130.5772
[17 empty] | 110 | 2024-06-21 | 116 | 4350.4898 | 5347.2115 | 346551.4212 | 424477.7887
[17 empty] | 110 | 2024-06-22 | 117 | 0 | 0 | 346551.4212 | 424477.7887
[17 empty] | 110 | 2024-06-23 | 118 | 0 | 0 | 346551.4212 | 424477.7887
[17 empty] | 110 | 2024-06-24 | 119 | 4350.4898 | 5347.2115 | 350901.9109 | 429825.0002
[17 empty] | 110 | 2024-06-25 | 120 | 4350.4898 | 5347.2115 | 355252.4007 | 435172.2117
[17 empty] | 110 | 2024-06-26 | 121 | 4350.4898 | 5347.2115 | 359602.8905 | 440519.4232
[17 empty] | 110 | 2024-06-27 | 122 | 4350.4898 | 5347.2115 | 363953.3803 | 445866.6347
[17 empty] | 110 | 2024-06-28 | 123 | 9081.3698 | 10882.3411 | 373034.7501 | 456748.9758
[17 empty] | 110 | 2024-06-29 | 124 | 0 | 0 | 373034.7501 | 456748.9758
[17 empty] | 110 | 2024-06-30 | 125 | 0 | 0 | 373034.7501 | 456748.9758
[17 empty] | 110 | 2024-07-01 | 126 | 9081.3698 | 10882.3411 | 382116.1199 | 467631.3169
[17 empty] | 110 | 2024-07-02 | 127 | 9081.3698 | 10882.3411 | 391197.4897 | 478513.6579
[17 empty] | 110 | 2024-07-03 | 128 | 9081.3698 | 10882.3411 | 400278.8594 | 489395.999
[17 empty] | 110 | 2024-07-04 | 129 | 9081.3698 | 10882.3411 | 409360.2292 | 500278.3401
[17 empty] | 110 | 2024-07-05 | 130 | 9081.3698 | 10882.3411 | 418441.599 | 511160.6812
[17 empty] | 110 | 2024-07-06 | 131 | 0 | 0 | 418441.599 | 511160.6812
[17 empty] | 110 | 2024-07-07 | 132 | 0 | 0 | 418441.599 | 511160.6812
[17 empty] | 110 | 2024-07-08 | 133 | 13776.2355 | 16281.4366 | 432217.8345 | 527442.1178
[17 empty] | 110 | 2024-07-09 | 134 | 13776.2355 | 16281.4366 | 445994.0699 | 543723.5545
[17 empty] | 110 | 2024-07-10 | 135 | 13776.2355 | 16281.4366 | 459770.3054 | 560004.9911
[17 empty] | 110 | 2024-07-11 | 136 | 13776.2355 | 16281.4366 | 473546.5409 | 576286.4277
[17 empty] | 110 | 2024-07-12 | 137 | 13776.2355 | 16281.4366 | 487322.7763 | 592567.8643
[17 empty] | 110 | 2024-07-13 | 138 | 0 | 0 | 487322.7763 | 592567.8643
[17 empty] | 110 | 2024-07-14 | 139 | 0 | 0 | 487322.7763 | 592567.8643
[17 empty] | 110 | 2024-07-15 | 140 | 13776.2355 | 16281.4366 | 501099.0118 | 608849.3009
[17 empty] | 110 | 2024-07-16 | 141 | 13776.2355 | 16281.4366 | 514875.2472 | 625130.7375
[17 empty] | 110 | 2024-07-17 | 142 | 13776.2355 | 16281.4366 | 528651.4827 | 641412.1741
[17 empty] | 110 | 2024-07-18 | 143 | 13776.2355 | 16281.4366 | 542427.7181 | 657693.6108
[17 empty] | 110 | 2024-07-19 | 144 | 9814.8401 | 11408.9203 | 552242.5583 | 669102.5311
[17 empty] | 110 | 2024-07-20 | 145 | 0 | 0 | 552242.5583 | 669102.5311
[17 empty] | 110 | 2024-07-21 | 146 | 0 | 0 | 552242.5583 | 669102.5311
[17 empty] | 110 | 2024-07-22 | 147 | 9814.8401 | 11408.9203 | 562057.3984 | 680511.4514
[17 empty] | 110 | 2024-07-23 | 148 | 9814.8401 | 11408.9203 | 571872.2385 | 691920.3718
[17 empty] | 110 | 2024-07-24 | 149 | 9814.8401 | 11408.9203 | 581687.0786 | 703329.2921
[17 empty] | 110 | 2024-07-25 | 150 | 9814.8401 | 11408.9203 | 591501.9187 | 714738.2124
[17 empty] | 110 | 2024-07-26 | 151 | 9814.8401 | 11408.9203 | 601316.7588 | 726147.1328
[17 empty] | 110 | 2024-07-27 | 152 | 0 | 0 | 601316.7588 | 726147.1328
[17 empty] | 110 | 2024-07-28 | 153 | 0 | 0 | 601316.7588 | 726147.1328
[17 empty] | 110 | 2024-07-29 | 154 | 9814.8401 | 11408.9203 | 611131.5989 | 737556.0531
[17 empty] | 110 | 2024-07-30 | 155 | 9814.8401 | 11408.9203 | 620946.439 | 748964.9735
[17 empty] | 110 | 2024-07-31 | 156 | 9814.8401 | 11408.9203 | 630761.2791 | 760373.8938
[17 empty] | 110 | 2024-08-01 | 157 | 9814.8401 | 11408.9203 | 640576.1192 | 771782.8141
[17 empty] | 110 | 2024-08-02 | 158 | 5083.9601 | 5873.7907 | 645660.0793 | 777656.6049
[17 empty] | 110 | 2024-08-03 | 159 | 0 | 0 | 645660.0793 | 777656.6049
[17 empty] | 110 | 2024-08-04 | 160 | 0 | 0 | 645660.0793 | 777656.6049
[17 empty] | 110 | 2024-08-05 | 161 | 5083.9601 | 5873.7907 | 650744.0395 | 783530.3956
[17 empty] | 110 | 2024-08-06 | 162 | 5083.9601 | 5873.7907 | 655827.9996 | 789404.1863
[17 empty] | 110 | 2024-08-07 | 163 | 5083.9601 | 5873.7907 | 660911.9597 | 795277.9771
[17 empty] | 110 | 2024-08-08 | 164 | 5083.9601 | 5873.7907 | 665995.9198 | 801151.7678
[17 empty] | 110 | 2024-08-09 | 165 | 5083.9601 | 5873.7907 | 671079.8799 | 807025.5585
[17 empty] | 110 | 2024-08-10 | 166 | 0 | 0 | 671079.8799 | 807025.5585
[17 empty] | 110 | 2024-08-11 | 167 | 0 | 0 | 671079.8799 | 807025.5585
[17 empty] | 110 | 2024-08-12 | 168 | 5083.9601 | 5873.7907 | 676163.84 | 812899.3493
[17 empty] | 110 | 2024-08-13 | 169 | 5083.9601 | 5873.7907 | 681247.8001 | 818773.14
[17 empty] | 110 | 2024-08-14 | 170 | 5083.9601 | 5873.7907 | 686331.7602 | 824646.9308
[17 empty] | 110 | 2024-08-15 | 171 | 5083.9601 | 5873.7907 | 691415.7203 | 830520.7215
[17 empty] | 110 | 2024-08-16 | 172 | 5083.9601 | 5873.7907 | 696499.6804 | 836394.5122
[17 empty] | 110 | 2024-08-17 | 173 | 0 | 0 | 696499.6804 | 836394.5122
[17 empty] | 110 | 2024-08-18 | 174 | 0 | 0 | 696499.6804 | 836394.5122
[17 empty] | 110 | 2024-08-19 | 175 | 5083.9601 | 5873.7907 | 701583.6406 | 842268.303
[17 empty] | 110 | 2024-08-20 | 176 | 5083.9601 | 5873.7907 | 706667.6007 | 848142.0937
[17 empty] | 110 | 2024-08-21 | 177 | 5083.9601 | 5873.7907 | 711751.5608 | 854015.8844
[17 empty] | 110 | 2024-08-22 | 178 | 5083.9601 | 5873.7907 | 716835.5209 | 859889.6752
[17 empty] | 110 | 2024-08-23 | 179 | 5083.9601 | 5873.7907 | 721919.481 | 865763.4659
[17 empty] | 110 | 2024-08-24 | 180 | 0 | 0 | 721919.481 | 865763.4659
[17 empty] | 110 | 2024-08-25 | 181 | 0 | 0 | 721919.481 | 865763.4659
[17 empty] | 110 | 2024-08-26 | 182 | 5083.9601 | 5873.7907 | 727003.4411 | 871637.2567
[17 empty] | 110 | 2024-08-27 | 183 | 5083.9601 | 5873.7907 | 732087.4012 | 877511.0474
[17 empty] | 110 | 2024-08-28 | 184 | 5083.9601 | 5873.7907 | 737171.3613 | 883384.8381
[17 empty] | 110 | 2024-08-29 | 185 | 5083.9601 | 5873.7907 | 742255.3214 | 889258.6289
[17 empty] | 110 | 2024-08-30 | 186 | 5083.9601 | 5873.7907 | 747339.2815 | 895132.4196
[17 empty] | 110 | 2024-08-31 | 187 | 0 | 0 | 747339.2815 | 895132.4196
[17 empty] | 110 | 2024-09-01 | 188 | 0 | 0 | 747339.2815 | 895132.4196
[17 empty] | 110 | 2024-09-02 | 189 | 5083.9601 | 5873.7907 | 752423.2416 | 901006.2103
[17 empty] | 110 | 2024-09-03 | 190 | 5083.9601 | 5873.7907 | 757507.2018 | 906880.0011
[17 empty] | 110 | 2024-09-04 | 191 | 5083.9601 | 5873.7907 | 762591.1619 | 912753.7918
[17 empty] | 110 | 2024-09-05 | 192 | 5083.9601 | 5873.7907 | 767675.122 | 918627.5825
[17 empty] | 110 | 2024-09-06 | 193 | 5083.9601 | 5873.7907 | 772759.0821 | 924501.3733
[17 empty] | 110 | 2024-09-07 | 194 | 0 | 0 | 772759.0821 | 924501.3733
[17 empty] | 110 | 2024-09-08 | 195 | 0 | 0 | 772759.0821 | 924501.3733
[17 empty] | 110 | 2024-09-09 | 196 | 5083.9601 | 5873.7907 | 777843.0422 | 930375.164
[17 empty] | 110 | 2024-09-10 | 197 | 5083.9601 | 5873.7907 | 782927.0023 | 936248.9548
[17 empty] | 110 | 2024-09-11 | 198 | 5083.9601 | 5873.7907 | 788010.9624 | 942122.7455
[17 empty] | 110 | 2024-09-12 | 199 | 5083.9601 | 5873.7907 | 793094.9225 | 947996.5362
[17 empty] | 110 | 2024-09-13 | 200 | 5083.9601 | 5873.7907 | 798178.8826 | 953870.327
[17 empty] | 110 | 2024-09-14 | 201 | 0 | 0 | 798178.8826 | 953870.327
[17 empty] | 110 | 2024-09-15 | 202 | 0 | 0 | 798178.8826 | 953870.327
[17 empty] | 110 | 2024-09-16 | 203 | 5083.9601 | 5873.7907 | 803262.8427 | 959744.1177
[17 empty] | 110 | 2024-09-17 | 204 | 5083.9601 | 5873.7907 | 808346.8029 | 965617.9084
[17 empty] | 110 | 2024-09-18 | 205 | 5083.9601 | 5873.7907 | 813430.763 | 971491.6992
[17 empty] | 110 | 2024-09-19 | 206 | 5083.9601 | 5873.7907 | 818514.7231 | 977365.4899
[17 empty] | 110 | 2024-09-20 | 207 | 5083.9601 | 5873.7907 | 823598.6832 | 983239.2806
[17 empty] | 110 | 2024-09-21 | 208 | 0 | 0 | 823598.6832 | 983239.2806
[17 empty] | 110 | 2024-09-22 | 209 | 0 | 0 | 823598.6832 | 983239.2806
[17 empty] | 110 | 2024-09-23 | 210 | 5083.9601 | 5873.7907 | 828682.6433 | 989113.0714
[17 empty] | 110 | 2024-09-24 | 211 | 5083.9601 | 5873.7907 | 833766.6034 | 994986.8621
[17 empty] | 110 | 2024-09-25 | 212 | 5083.9601 | 5873.7907 | 838850.5635 | 1000860.6529
[17 empty] | 110 | 2024-09-26 | 213 | 5083.9601 | 5873.7907 | 843934.5236 | 1006734.4436
[17 empty] | 110 | 2024-09-27 | 214 | 5083.9601 | 5873.7907 | 849018.4837 | 1012608.2343
[17 empty] | 110 | 2024-09-28 | 215 | 0 | 0 | 849018.4837 | 1012608.2343
[17 empty] | 110 | 2024-09-29 | 216 | 0 | 0 | 849018.4837 | 1012608.2343
[17 empty] | 110 | 2024-09-30 | 217 | 5083.9601 | 5873.7907 | 854102.4438 | 1018482.0251
[17 empty] | 110 | 2024-10-01 | 218 | 5083.9601 | 5873.7907 | 859186.4039 | 1024355.8158
[17 empty] | 110 | 2024-10-02 | 219 | 5083.9601 | 5873.7907 | 864270.3641 | 1030229.6065
[17 empty] | 110 | 2024-10-03 | 220 | 5083.9601 | 5873.7907 | 869354.3242 | 1036103.3973
[17 empty] | 110 | 2024-10-04 | 221 | 5083.9601 | 5873.7907 | 874438.2843 | 1041977.188
[17 empty] | 110 | 2024-10-05 | 222 | 0 | 0 | 874438.2843 | 1041977.188
[17 empty] | 110 | 2024-10-06 | 223 | 0 | 0 | 874438.2843 | 1041977.188
[17 empty] | 110 | 2024-10-07 | 224 | 5083.9601 | 5873.7907 | 879522.2444 | 1047850.9787
[17 empty] | 110 | 2024-10-08 | 225 | 5083.9601 | 5873.7907 | 884606.2045 | 1053724.7695
[17 empty] | 110 | 2024-10-09 | 226 | 389.0944 | 474.6952 | 884995.2989 | 1054199.4647
[17 empty] | 110 | 2024-10-10 | 227 | 389.0944 | 474.6952 | 885384.3934 | 1054674.1599
[17 empty] | 110 | 2024-10-11 | 228 | 389.0944 | 474.6952 | 885773.4878 | 1055148.8551
[17 empty] | 110 | 2024-10-12 | 229 | 0 | 0 | 885773.4878 | 1055148.8551
[17 empty] | 110 | 2024-10-13 | 230 | 0 | 0 | 885773.4878 | 1055148.8551
[17 empty] | 110 | 2024-10-14 | 231 | 389.0944 | 474.6952 | 886162.5822 | 1055623.5503
[17 empty] | 110 | 2024-10-15 | 232 | 389.0944 | 474.6952 | 886551.6767 | 1056098.2456
[17 empty] | 110 | 2024-10-16 | 233 | 389.0944 | 474.6952 | 886940.7711 | 1056572.9408
[17 empty] | 110 | 2024-10-17 | 234 | 389.0944 | 474.6952 | 887329.8656 | 1057047.636
[17 empty] | 110 | 2024-10-18 | 235 | 389.0944 | 474.6952 | 887718.96 | 1057522.3312
[17 empty] | 111 | 2024-04-11 | 1 | 433.2998 | 485.2958 | 433.2998 | 485.2958
[17 empty] | 111 | 2024-04-12 | 2 | 433.2998 | 485.2958 | 866.5997 | 970.5917
[17 empty] | 111 | 2024-04-13 | 3 | 0 | 0 | 866.5997 | 970.5917
[17 empty] | 111 | 2024-04-14 | 4 | 0 | 0 | 866.5997 | 970.5917
[17 empty] | 111 | 2024-04-15 | 5 | 433.2998 | 485.2958 | 1299.8995 | 1455.8875
[17 empty] | 111 | 2024-04-16 | 6 | 2337.7346 | 2846.795 | 3637.6342 | 4302.6824
[17 empty] | 111 | 2024-04-17 | 7 | 2337.7346 | 2846.795 | 5975.3688 | 7149.4774
[17 empty] | 111 | 2024-04-18 | 8 | 2337.7346 | 2846.795 | 8313.1034 | 9996.2723
[17 empty] | 111 | 2024-04-19 | 9 | 2337.7346 | 2846.795 | 10650.838 | 12843.0673
[17 empty] | 111 | 2024-04-20 | 10 | 0 | 0 | 10650.838 | 12843.0673
[17 empty] | 111 | 2024-04-21 | 11 | 0 | 0 | 10650.838 | 12843.0673
[17 empty] | 111 | 2024-04-22 | 12 | 2337.7346 | 2846.795 | 12988.5727 | 15689.8623
[17 empty] | 111 | 2024-04-23 | 13 | 2337.7346 | 2846.795 | 15326.3073 | 18536.6572
[17 empty] | 111 | 2024-04-24 | 14 | 2337.7346 | 2846.795 | 17664.0419 | 21383.4522
[17 empty] | 111 | 2024-04-25 | 15 | 2337.7346 | 2846.795 | 20001.7765 | 24230.2471
[17 empty] | 111 | 2024-04-26 | 16 | 2337.7346 | 2846.795 | 22339.5112 | 27077.0421
[17 empty] | 111 | 2024-04-27 | 17 | 0 | 0 | 22339.5112 | 27077.0421
[17 empty] | 111 | 2024-04-28 | 18 | 0 | 0 | 22339.5112 | 27077.0421
[17 empty] | 111 | 2024-04-29 | 19 | 2337.7346 | 2846.795 | 24677.2458 | 29923.837
[17 empty] | 111 | 2024-04-30 | 20 | 2337.7346 | 2846.795 | 27014.9804 | 32770.632
[17 empty] | 111 | 2024-05-01 | 21 | 2337.7346 | 2846.795 | 29352.7151 | 35617.427
[17 empty] | 111 | 2024-05-02 | 22 | 2337.7346 | 2846.795 | 31690.4497 | 38464.2219
[17 empty] | 111 | 2024-05-03 | 23 | 2337.7346 | 2846.795 | 34028.1843 | 41311.0169
[17 empty] | 111 | 2024-05-04 | 24 | 0 | 0 | 34028.1843 | 41311.0169
[17 empty] | 111 | 2024-05-05 | 25 | 0 | 0 | 34028.1843 | 41311.0169
[17 empty] | 111 | 2024-05-06 | 26 | 2337.7346 | 2846.795 | 36365.9189 | 44157.8118
[17 empty] | 111 | 2024-05-07 | 27 | 2337.7346 | 2846.795 | 38703.6536 | 47004.6068
[17 empty] | 111 | 2024-05-08 | 28 | 2337.7346 | 2846.795 | 41041.3882 | 49851.4017
[17 empty] | 111 | 2024-05-09 | 29 | 2337.7346 | 2846.795 | 43379.1228 | 52698.1967
[17 empty] | 111 | 2024-05-10 | 30 | 2337.7346 | 2846.795 | 45716.8574 | 55544.9916
[17 empty] | 111 | 2024-05-11 | 31 | 0 | 0 | 45716.8574 | 55544.9916
[17 empty] | 111 | 2024-05-12 | 32 | 0 | 0 | 45716.8574 | 55544.9916
[17 empty] | 111 | 2024-05-13 | 33 | 2337.7346 | 2846.795 | 48054.5921 | 58391.7866
[17 empty] | 111 | 2024-05-14 | 34 | 2337.7346 | 2846.795 | 50392.3267 | 61238.5816
[17 empty] | 111 | 2024-05-15 | 35 | 2337.7346 | 2846.795 | 52730.0613 | 64085.3765
[17 empty] | 111 | 2024-05-16 | 36 | 5051.559 | 6239.0754 | 57781.6203 | 70324.4519
[17 empty] | 111 | 2024-05-17 | 37 | 3147.1242 | 3877.5762 | 60928.7444 | 74202.0281
[17 empty] | 111 | 2024-05-18 | 38 | 0 | 0 | 60928.7444 | 74202.0281
[17 empty] | 111 | 2024-05-19 | 39 | 0 | 0 | 60928.7444 | 74202.0281
[17 empty] | 111 | 2024-05-20 | 40 | 3147.1242 | 3877.5762 | 64075.8686 | 78079.6043
[17 empty] | 111 | 2024-05-21 | 41 | 3147.1242 | 3877.5762 | 67222.9928 | 81957.1806
[17 empty] | 111 | 2024-05-22 | 42 | 3147.1242 | 3877.5762 | 70370.117 | 85834.7568
[17 empty] | 111 | 2024-05-23 | 43 | 3147.1242 | 3877.5762 | 73517.2411 | 89712.333
[17 empty] | 111 | 2024-05-24 | 44 | 3147.1242 | 3877.5762 | 76664.3653 | 93589.9093
[17 empty] | 111 | 2024-05-25 | 45 | 0 | 0 | 76664.3653 | 93589.9093
[17 empty] | 111 | 2024-05-26 | 46 | 0 | 0 | 76664.3653 | 93589.9093
[17 empty] | 111 | 2024-05-27 | 47 | 3147.1242 | 3877.5762 | 79811.4895 | 97467.4855
[17 empty] | 111 | 2024-05-28 | 48 | 3147.1242 | 3877.5762 | 82958.6136 | 101345.0617
[17 empty] | 111 | 2024-05-29 | 49 | 3147.1242 | 3877.5762 | 86105.7378 | 105222.638
[17 empty] | 111 | 2024-05-30 | 50 | 3147.1242 | 3877.5762 | 89252.862 | 109100.2142
[17 empty] | 111 | 2024-05-31 | 51 | 3147.1242 | 3877.5762 | 92399.9861 | 112977.7904
[17 empty] | 111 | 2024-06-01 | 52 | 0 | 0 | 92399.9861 | 112977.7904
[17 empty] | 111 | 2024-06-02 | 53 | 0 | 0 | 92399.9861 | 112977.7904
[17 empty] | 111 | 2024-06-03 | 54 | 3147.1242 | 3877.5762 | 95547.1103 | 116855.3666
[17 empty] | 111 | 2024-06-04 | 55 | 3147.1242 | 3877.5762 | 98694.2345 | 120732.9429
[17 empty] | 111 | 2024-06-05 | 56 | 3147.1242 | 3877.5762 | 101841.3586 | 124610.5191
[17 empty] | 111 | 2024-06-06 | 57 | 3147.1242 | 3877.5762 | 104988.4828 | 128488.0953
[17 empty] | 111 | 2024-06-07 | 58 | 3147.1242 | 3877.5762 | 108135.607 | 132365.6716
[17 empty] | 111 | 2024-06-08 | 59 | 0 | 0 | 108135.607 | 132365.6716
[17 empty] | 111 | 2024-06-09 | 60 | 0 | 0 | 108135.607 | 132365.6716
[17 empty] | 111 | 2024-06-10 | 61 | 3147.1242 | 3877.5762 | 111282.7311 | 136243.2478
[17 empty] | 111 | 2024-06-11 | 62 | 3147.1242 | 3877.5762 | 114429.8553 | 140120.824
[17 empty] | 111 | 2024-06-12 | 63 | 3147.1242 | 3877.5762 | 117576.9795 | 143998.4003
[17 empty] | 111 | 2024-06-13 | 64 | 3147.1242 | 3877.5762 | 120724.1037 | 147875.9765
[17 empty] | 111 | 2024-06-14 | 65 | 3147.1242 | 3877.5762 | 123871.2278 | 151753.5527
[17 empty] | 111 | 2024-06-15 | 66 | 0 | 0 | 123871.2278 | 151753.5527
[17 empty] | 111 | 2024-06-16 | 67 | 0 | 0 | 123871.2278 | 151753.5527
[17 empty] | 111 | 2024-06-17 | 68 | 3147.1242 | 3877.5762 | 127018.352 | 155631.129
[17 empty] | 111 | 2024-06-18 | 69 | 3147.1242 | 3877.5762 | 130165.4762 | 159508.7052
[17 empty] | 111 | 2024-06-19 | 70 | 3147.1242 | 3877.5762 | 133312.6003 | 163386.2814
[17 empty] | 111 | 2024-06-20 | 71 | 3147.1242 | 3877.5762 | 136459.7245 | 167263.8577
[17 empty] | 111 | 2024-06-21 | 72 | 3147.1242 | 3877.5762 | 139606.8487 | 171141.4339
[17 empty] | 111 | 2024-06-22 | 73 | 0 | 0 | 139606.8487 | 171141.4339
[17 empty] | 111 | 2024-06-23 | 74 | 0 | 0 | 139606.8487 | 171141.4339
[17 empty] | 111 | 2024-06-24 | 75 | 3147.1242 | 3877.5762 | 142753.9728 | 175019.0101
[17 empty] | 111 | 2024-06-25 | 76 | 3147.1242 | 3877.5762 | 145901.097 | 178896.5863
[17 empty] | 111 | 2024-06-26 | 77 | 3147.1242 | 3877.5762 | 149048.2212 | 182774.1626
[17 empty] | 111 | 2024-06-27 | 78 | 3147.1242 | 3877.5762 | 152195.3453 | 186651.7388
[17 empty] | 111 | 2024-06-28 | 79 | 3147.1242 | 3877.5762 | 155342.4695 | 190529.315
[17 empty] | 111 | 2024-06-29 | 80 | 0 | 0 | 155342.4695 | 190529.315
[17 empty] | 111 | 2024-06-30 | 81 | 0 | 0 | 155342.4695 | 190529.315
[17 empty] | 111 | 2024-07-01 | 82 | 3147.1242 | 3877.5762 | 158489.5937 | 194406.8913
[17 empty] | 111 | 2024-07-02 | 83 | 3147.1242 | 3877.5762 | 161636.7178 | 198284.4675
[17 empty] | 111 | 2024-07-03 | 84 | 3147.1242 | 3877.5762 | 164783.842 | 202162.0437
[17 empty] | 111 | 2024-07-04 | 85 | 3147.1242 | 3877.5762 | 167930.9662 | 206039.62
[17 empty] | 111 | 2024-07-05 | 86 | 3147.1242 | 3877.5762 | 171078.0904 | 209917.1962
[17 empty] | 111 | 2024-07-06 | 87 | 0 | 0 | 171078.0904 | 209917.1962
[17 empty] | 111 | 2024-07-07 | 88 | 0 | 0 | 171078.0904 | 209917.1962
[17 empty] | 111 | 2024-07-08 | 89 | 3147.1242 | 3877.5762 | 174225.2145 | 213794.7724
[17 empty] | 111 | 2024-07-09 | 90 | 3147.1242 | 3877.5762 | 177372.3387 | 217672.3487
[17 empty] | 111 | 2024-07-10 | 91 | 3147.1242 | 3877.5762 | 180519.4629 | 221549.9249
[17 empty] | 111 | 2024-07-11 | 92 | 3147.1242 | 3877.5762 | 183666.587 | 225427.5011
[17 empty] | 111 | 2024-07-12 | 93 | 3147.1242 | 3877.5762 | 186813.7112 | 229305.0773
[17 empty] | 111 | 2024-07-13 | 94 | 0 | 0 | 186813.7112 | 229305.0773
[17 empty] | 111 | 2024-07-14 | 95 | 0 | 0 | 186813.7112 | 229305.0773
[17 empty] | 111 | 2024-07-15 | 96 | 3147.1242 | 3877.5762 | 189960.8354 | 233182.6536
[17 empty] | 111 | 2024-07-16 | 97 | 3147.1242 | 3877.5762 | 193107.9595 | 237060.2298
[17 empty] | 111 | 2024-07-17 | 98 | 3147.1242 | 3877.5762 | 196255.0837 | 240937.806
[17 empty] | 111 | 2024-07-18 | 99 | 3147.1242 | 3877.5762 | 199402.2079 | 244815.3823
[17 empty] | 111 | 2024-07-19 | 100 | 3147.1242 | 3877.5762 | 202549.332 | 248692.9585
[17 empty] | 111 | 2024-07-20 | 101 | 0 | 0 | 202549.332 | 248692.9585
[17 empty] | 111 | 2024-07-21 | 102 | 0 | 0 | 202549.332 | 248692.9585
[17 empty] | 111 | 2024-07-22 | 103 | 3147.1242 | 3877.5762 | 205696.4562 | 252570.5347
[17 empty] | 111 | 2024-07-23 | 104 | 3147.1242 | 3877.5762 | 208843.5804 | 256448.111
[17 empty] | 111 | 2024-07-24 | 105 | 3147.1242 | 3877.5762 | 211990.7045 | 260325.6872
[17 empty] | 111 | 2024-07-25 | 106 | 3147.1242 | 3877.5762 | 215137.8287 | 264203.2634
[17 empty] | 111 | 2024-07-26 | 107 | 3147.1242 | 3877.5762 | 218284.9529 | 268080.8397
[17 empty] | 111 | 2024-07-27 | 108 | 0 | 0 | 218284.9529 | 268080.8397
[17 empty] | 111 | 2024-07-28 | 109 | 0 | 0 | 218284.9529 | 268080.8397
[17 empty] | 111 | 2024-07-29 | 110 | 3147.1242 | 3877.5762 | 221432.077 | 271958.4159
[17 empty] | 111 | 2024-07-30 | 111 | 3147.1242 | 3877.5762 | 224579.2012 | 275835.9921
[17 empty] | 111 | 2024-07-31 | 112 | 3147.1242 | 3877.5762 | 227726.3254 | 279713.5684
[17 empty] | 111 | 2024-08-01 | 113 | 3147.1242 | 3877.5762 | 230873.4496 | 283591.1446
[17 empty] | 111 | 2024-08-02 | 114 | 3147.1242 | 3877.5762 | 234020.5737 | 287468.7208
[17 empty] | 111 | 2024-08-03 | 115 | 0 | 0 | 234020.5737 | 287468.7208
[17 empty] | 111 | 2024-08-04 | 116 | 0 | 0 | 234020.5737 | 287468.7208
[17 empty] | 111 | 2024-08-05 | 117 | 3147.1242 | 3877.5762 | 237167.6979 | 291346.297
[17 empty] | 111 | 2024-08-06 | 118 | 3147.1242 | 3877.5762 | 240314.8221 | 295223.8733
[17 empty] | 111 | 2024-08-07 | 119 | 6655.3084 | 8332.9702 | 246970.1304 | 303556.8435
[17 empty] | 111 | 2024-08-08 | 120 | 6655.3084 | 8332.9702 | 253625.4388 | 311889.8136
[17 empty] | 111 | 2024-08-09 | 121 | 6655.3084 | 8332.9702 | 260280.7472 | 320222.7838
[17 empty] | 111 | 2024-08-10 | 122 | 0 | 0 | 260280.7472 | 320222.7838
[17 empty] | 111 | 2024-08-11 | 123 | 0 | 0 | 260280.7472 | 320222.7838
[17 empty] | 111 | 2024-08-12 | 124 | 6655.3084 | 8332.9702 | 266936.0556 | 328555.754
[17 empty] | 111 | 2024-08-13 | 125 | 6655.3084 | 8332.9702 | 273591.364 | 336888.7242
[17 empty] | 111 | 2024-08-14 | 126 | 6655.3084 | 8332.9702 | 280246.6723 | 345221.6943
[17 empty] | 111 | 2024-08-15 | 127 | 6655.3084 | 8332.9702 | 286901.9807 | 353554.6645
[17 empty] | 111 | 2024-08-16 | 128 | 6655.3084 | 8332.9702 | 293557.2891 | 361887.6347
[17 empty] | 111 | 2024-08-17 | 129 | 0 | 0 | 293557.2891 | 361887.6347
[17 empty] | 111 | 2024-08-18 | 130 | 0 | 0 | 293557.2891 | 361887.6347
[17 empty] | 111 | 2024-08-19 | 131 | 10645.3084 | 12841.6702 | 304202.5975 | 374729.3049
[17 empty] | 111 | 2024-08-20 | 132 | 10645.3084 | 12841.6702 | 314847.9059 | 387570.9751
[17 empty] | 111 | 2024-08-21 | 133 | 10645.3084 | 12841.6702 | 325493.2142 | 400412.6452
[17 empty] | 111 | 2024-08-22 | 134 | 10645.3084 | 12841.6702 | 336138.5226 | 413254.3154
[17 empty] | 111 | 2024-08-23 | 135 | 10645.3084 | 12841.6702 | 346783.831 | 426095.9856
[17 empty] | 111 | 2024-08-24 | 136 | 0 | 0 | 346783.831 | 426095.9856
[17 empty] | 111 | 2024-08-25 | 137 | 0 | 0 | 346783.831 | 426095.9856
[17 empty] | 111 | 2024-08-26 | 138 | 10645.3084 | 12841.6702 | 357429.1394 | 438937.6558
[17 empty] | 111 | 2024-08-27 | 139 | 10645.3084 | 12841.6702 | 368074.4477 | 451779.326
[17 empty] | 111 | 2024-08-28 | 140 | 7931.4841 | 9449.3898 | 376005.9318 | 461228.7157
[17 empty] | 111 | 2024-08-29 | 141 | 7931.4841 | 9449.3898 | 383937.4159 | 470678.1055
[17 empty] | 111 | 2024-08-30 | 142 | 7931.4841 | 9449.3898 | 391868.8999 | 480127.4953
[17 empty] | 111 | 2024-08-31 | 143 | 0 | 0 | 391868.8999 | 480127.4953
[17 empty] | 111 | 2024-09-01 | 144 | 0 | 0 | 391868.8999 | 480127.4953
[17 empty] | 111 | 2024-09-02 | 145 | 7931.4841 | 9449.3898 | 399800.384 | 489576.885
[17 empty] | 111 | 2024-09-03 | 146 | 7931.4841 | 9449.3898 | 407731.868 | 499026.2748
[17 empty] | 111 | 2024-09-04 | 147 | 7931.4841 | 9449.3898 | 415663.3521 | 508475.6646
[17 empty] | 111 | 2024-09-05 | 148 | 7931.4841 | 9449.3898 | 423594.8361 | 517925.0544
[17 empty] | 111 | 2024-09-06 | 149 | 7931.4841 | 9449.3898 | 431526.3202 | 527374.4441
[17 empty] | 111 | 2024-09-07 | 150 | 0 | 0 | 431526.3202 | 527374.4441
[17 empty] | 111 | 2024-09-08 | 151 | 0 | 0 | 431526.3202 | 527374.4441
[17 empty] | 111 | 2024-09-09 | 152 | 7931.4841 | 9449.3898 | 439457.8042 | 536823.8339
[17 empty] | 111 | 2024-09-10 | 153 | 7931.4841 | 9449.3898 | 447389.2883 | 546273.2237
[17 empty] | 111 | 2024-09-11 | 154 | 7931.4841 | 9449.3898 | 455320.7724 | 555722.6135
[17 empty] | 111 | 2024-09-12 | 155 | 7931.4841 | 9449.3898 | 463252.2564 | 565172.0032
[17 empty] | 111 | 2024-09-13 | 156 | 7931.4841 | 9449.3898 | 471183.7405 | 574621.393
[17 empty] | 111 | 2024-09-14 | 157 | 0 | 0 | 471183.7405 | 574621.393
[17 empty] | 111 | 2024-09-15 | 158 | 0 | 0 | 471183.7405 | 574621.393
[17 empty] | 111 | 2024-09-16 | 159 | 7931.4841 | 9449.3898 | 479115.2245 | 584070.7828
[17 empty] | 111 | 2024-09-17 | 160 | 7931.4841 | 9449.3898 | 487046.7086 | 593520.1725
[17 empty] | 111 | 2024-09-18 | 161 | 7931.4841 | 9449.3898 | 494978.1926 | 602969.5623
[17 empty] | 111 | 2024-09-19 | 162 | 7931.4841 | 9449.3898 | 502909.6767 | 612418.9521
[17 empty] | 111 | 2024-09-20 | 163 | 7931.4841 | 9449.3898 | 510841.1607 | 621868.3419
[17 empty] | 111 | 2024-09-21 | 164 | 0 | 0 | 510841.1607 | 621868.3419
[17 empty] | 111 | 2024-09-22 | 165 | 0 | 0 | 510841.1607 | 621868.3419
[17 empty] | 111 | 2024-09-23 | 166 | 7931.4841 | 9449.3898 | 518772.6448 | 631317.7316
[17 empty] | 111 | 2024-09-24 | 167 | 7931.4841 | 9449.3898 | 526704.1288 | 640767.1214
[17 empty] | 111 | 2024-09-25 | 168 | 7931.4841 | 9449.3898 | 534635.6129 | 650216.5112
[17 empty] | 111 | 2024-09-26 | 169 | 7931.4841 | 9449.3898 | 542567.097 | 659665.901
[17 empty] | 111 | 2024-09-27 | 170 | 7931.4841 | 9449.3898 | 550498.581 | 669115.2907
[17 empty] | 111 | 2024-09-28 | 171 | 0 | 0 | 550498.581 | 669115.2907
[17 empty] | 111 | 2024-09-29 | 172 | 0 | 0 | 550498.581 | 669115.2907
[17 empty] | 111 | 2024-09-30 | 173 | 4423.2998 | 4993.9958 | 554921.8809 | 674109.2866
[17 empty] | 111 | 2024-10-01 | 174 | 4423.2998 | 4993.9958 | 559345.1807 | 679103.2824
[17 empty] | 111 | 2024-10-02 | 175 | 4423.2998 | 4993.9958 | 563768.4805 | 684097.2782
[17 empty] | 111 | 2024-10-03 | 176 | 4423.2998 | 4993.9958 | 568191.7804 | 689091.274
[17 empty] | 111 | 2024-10-04 | 177 | 4423.2998 | 4993.9958 | 572615.0802 | 694085.2699
[17 empty] | 111 | 2024-10-05 | 178 | 0 | 0 | 572615.0802 | 694085.2699
[17 empty] | 111 | 2024-10-06 | 179 | 0 | 0 | 572615.0802 | 694085.2699
[17 empty] | 111 | 2024-10-07 | 180 | 4423.2998 | 4993.9958 | 577038.3801 | 699079.2657
[17 empty] | 111 | 2024-10-08 | 181 | 4423.2998 | 4993.9958 | 581461.6799 | 704073.2615
[17 empty] | 111 | 2024-10-09 | 182 | 4423.2998 | 4993.9958 | 585884.9798 | 709067.2573
[17 empty] | 111 | 2024-10-10 | 183 | 4423.2998 | 4993.9958 | 590308.2796 | 714061.2532
[17 empty] | 111 | 2024-10-11 | 184 | 4423.2998 | 4993.9958 | 594731.5795 | 719055.249
[17 empty] | 111 | 2024-10-12 | 185 | 0 | 0 | 594731.5795 | 719055.249
[17 empty] | 111 | 2024-10-13 | 186 | 0 | 0 | 594731.5795 | 719055.249
[17 empty] | 111 | 2024-10-14 | 187 | 4423.2998 | 4993.9958 | 599154.8793 | 724049.2448
[17 empty] | 111 | 2024-10-15 | 188 | 4423.2998 | 4993.9958 | 603578.1791 | 729043.2406
[17 empty] | 111 | 2024-10-16 | 189 | 4423.2998 | 4993.9958 | 608001.479 | 734037.2365
[17 empty] | 111 | 2024-10-17 | 190 | 4423.2998 | 4993.9958 | 612424.7788 | 739031.2323
[17 empty] | 111 | 2024-10-18 | 191 | 4423.2998 | 4993.9958 | 616848.0787 | 744025.2281
[17 empty] | 111 | 2024-10-19 | 192 | 0 | 0 | 616848.0787 | 744025.2281
[17 empty] | 111 | 2024-10-20 | 193 | 0 | 0 | 616848.0787 | 744025.2281
[17 empty] | 111 | 2024-10-21 | 194 | 4423.2998 | 4993.9958 | 621271.3785 | 749019.2239
[17 empty] | 111 | 2024-10-22 | 195 | 4423.2998 | 4993.9958 | 625694.6784 | 754013.2198
[17 empty] | 111 | 2024-10-23 | 196 | 4423.2998 | 4993.9958 | 630117.9782 | 759007.2156
[17 empty] | 111 | 2024-10-24 | 197 | 4423.2998 | 4993.9958 | 634541.2781 | 764001.2114
[17 empty] | 111 | 2024-10-25 | 198 | 4423.2998 | 4993.9958 | 638964.5779 | 768995.2072
[17 empty] | 111 | 2024-10-26 | 199 | 0 | 0 | 638964.5779 | 768995.2072
[17 empty] | 111 | 2024-10-27 | 200 | 0 | 0 | 638964.5779 | 768995.2072
[17 empty] | 111 | 2024-10-28 | 201 | 4423.2998 | 4993.9958 | 643387.8777 | 773989.2031
[17 empty] | 111 | 2024-10-29 | 202 | 4423.2998 | 4993.9958 | 647811.1776 | 778983.1989
[17 empty] | 111 | 2024-10-30 | 203 | 4423.2998 | 4993.9958 | 652234.4774 | 783977.1947
[17 empty] | 111 | 2024-10-31 | 204 | 4423.2998 | 4993.9958 | 656657.7773 | 788971.1905
[17 empty] | 111 | 2024-11-01 | 205 | 4423.2998 | 4993.9958 | 661081.0771 | 793965.1864
[17 empty] | 111 | 2024-11-02 | 206 | 0 | 0 | 661081.0771 | 793965.1864
[17 empty] | 111 | 2024-11-03 | 207 | 0 | 0 | 661081.0771 | 793965.1864
[17 empty] | 111 | 2024-11-04 | 208 | 4423.2998 | 4993.9958 | 665504.377 | 798959.1822
[17 empty] | 111 | 2024-11-05 | 209 | 4423.2998 | 4993.9958 | 669927.6768 | 803953.178
[17 empty] | 111 | 2024-11-06 | 210 | 4423.2998 | 4993.9958 | 674350.9767 | 808947.1739
[17 empty] | 111 | 2024-11-07 | 211 | 4423.2998 | 4993.9958 | 678774.2765 | 813941.1697
[17 empty] | 111 | 2024-11-08 | 212 | 4423.2998 | 4993.9958 | 683197.5763 | 818935.1655
[17 empty] | 111 | 2024-11-09 | 213 | 0 | 0 | 683197.5763 | 818935.1655
[17 empty] | 111 | 2024-11-10 | 214 | 0 | 0 | 683197.5763 | 818935.1655
[17 empty] | 111 | 2024-11-11 | 215 | 4423.2998 | 4993.9958 | 687620.8762 | 823929.1613
[17 empty] | 111 | 2024-11-12 | 216 | 4423.2998 | 4993.9958 | 692044.176 | 828923.1572
[17 empty] | 111 | 2024-11-13 | 217 | 4423.2998 | 4993.9958 | 696467.4759 | 833917.153
[17 empty] | 111 | 2024-11-14 | 218 | 4423.2998 | 4993.9958 | 700890.7757 | 838911.1488
[17 empty] | 111 | 2024-11-15 | 219 | 4423.2998 | 4993.9958 | 705314.0756 | 843905.1446
[17 empty] | 111 | 2024-11-16 | 220 | 0 | 0 | 705314.0756 | 843905.1446
[17 empty] | 111 | 2024-11-17 | 221 | 0 | 0 | 705314.0756 | 843905.1446
[17 empty] | 111 | 2024-11-18 | 222 | 4423.2998 | 4993.9958 | 709737.3754 | 848899.1405
[17 empty] | 111 | 2024-11-19 | 223 | 4423.2998 | 4993.9958 | 714160.6753 | 853893.1363
[17 empty] | 111 | 2024-11-20 | 224 | 4423.2998 | 4993.9958 | 718583.9751 | 858887.1321
[17 empty] | 111 | 2024-11-21 | 225 | 4423.2998 | 4993.9958 | 723007.2749 | 863881.1279
[17 empty] | 111 | 2024-11-22 | 226 | 4423.2998 | 4993.9958 | 727430.5748 | 868875.1238
[17 empty] | 111 | 2024-11-23 | 227 | 0 | 0 | 727430.5748 | 868875.1238
[17 empty] | 111 | 2024-11-24 | 228 | 0 | 0 | 727430.5748 | 868875.1238
[17 empty] | 111 | 2024-11-25 | 229 | 4423.2998 | 4993.9958 | 731853.8746 | 873869.1196
[17 empty] | 111 | 2024-11-26 | 230 | 4423.2998 | 4993.9958 | 736277.1745 | 878863.1154
[17 empty] | 111 | 2024-11-27 | 231 | 4423.2998 | 4993.9958 | 740700.4743 | 883857.1112
[17 empty] | 111 | 2024-11-28 | 232 | 4423.2998 | 4993.9958 | 745123.7742 | 888851.1071
[17 empty] | 111 | 2024-11-29 | 233 | 4423.2998 | 4993.9958 | 749547.074 | 893845.1029
[17 empty] | 111 | 2024-11-30 | 234 | 0 | 0 | 749547.074 | 893845.1029
[17 empty] | 111 | 2024-12-01 | 235 | 0 | 0 | 749547.074 | 893845.1029
[17 empty] | 111 | 2024-12-02 | 236 | 4423.2998 | 4993.9958 | 753970.3739 | 898839.0987
[17 empty] | 111 | 2024-12-03 | 237 | 4423.2998 | 4993.9958 | 758393.6737 | 903833.0945
[17 empty] | 111 | 2024-12-04 | 238 | 4423.2998 | 4993.9958 | 762816.9735 | 908827.0904
[17 empty] | 111 | 2024-12-05 | 239 | 4423.2998 | 4993.9958 | 767240.2734 | 913821.0862
[17 empty] | 111 | 2024-12-06 | 240 | 4423.2998 | 4993.9958 | 771663.5732 | 918815.082
[17 empty] | 111 | 2024-12-07 | 241 | 0 | 0 | 771663.5732 | 918815.082
[17 empty] | 111 | 2024-12-08 | 242 | 0 | 0 | 771663.5732 | 918815.082
[17 empty] | 111 | 2024-12-09 | 243 | 4423.2998 | 4993.9958 | 776086.8731 | 923809.0778
[17 empty] | 111 | 2024-12-10 | 244 | 4423.2998 | 4993.9958 | 780510.1729 | 928803.0737
[17 empty] | 111 | 2024-12-11 | 245 | 4423.2998 | 4993.9958 | 784933.4728 | 933797.0695
[17 empty] | 111 | 2024-12-12 | 246 | 4423.2998 | 4993.9958 | 789356.7726 | 938791.0653
[17 empty] | 111 | 2024-12-13 | 247 | 4423.2998 | 4993.9958 | 793780.0725 | 943785.0611
[17 empty] | 111 | 2024-12-14 | 248 | 0 | 0 | 793780.0725 | 943785.0611
[17 empty] | 111 | 2024-12-15 | 249 | 0 | 0 | 793780.0725 | 943785.0611
[17 empty] | 111 | 2024-12-16 | 250 | 4423.2998 | 4993.9958 | 798203.3723 | 948779.057
[17 empty] | 111 | 2024-12-17 | 251 | 4423.2998 | 4993.9958 | 802626.6721 | 953773.0528
[17 empty] | 111 | 2024-12-18 | 252 | 4423.2998 | 4993.9958 | 807049.972 | 958767.0486
[17 empty] | 111 | 2024-12-19 | 253 | 4423.2998 | 4993.9958 | 811473.2718 | 963761.0444
[17 empty] | 111 | 2024-12-20 | 254 | 4423.2998 | 4993.9958 | 815896.5717 | 968755.0403
[17 empty] | 111 | 2024-12-21 | 255 | 0 | 0 | 815896.5717 | 968755.0403
[17 empty] | 111 | 2024-12-22 | 256 | 0 | 0 | 815896.5717 | 968755.0403
[17 empty] | 111 | 2024-12-23 | 257 | 4423.2998 | 4993.9958 | 820319.8715 | 973749.0361
[17 empty] | 111 | 2024-12-24 | 258 | 4423.2998 | 4993.9958 | 824743.1714 | 978743.0319
[17 empty] | 111 | 2024-12-25 | 259 | 4423.2998 | 4993.9958 | 829166.4712 | 983737.0278
[17 empty] | 111 | 2024-12-26 | 260 | 4423.2998 | 4993.9958 | 833589.7711 | 988731.0236
[17 empty] | 111 | 2024-12-27 | 261 | 4423.2998 | 4993.9958 | 838013.0709 | 993725.0194
[17 empty] | 111 | 2024-12-28 | 262 | 0 | 0 | 838013.0709 | 993725.0194
[17 empty] | 111 | 2024-12-29 | 263 | 0 | 0 | 838013.0709 | 993725.0194
[17 empty] | 111 | 2024-12-30 | 264 | 4423.2998 | 4993.9958 | 842436.3707 | 998719.0152
[17 empty] | 111 | 2024-12-31 | 265 | 4423.2998 | 4993.9958 | 846859.6706 | 1003713.0111
[17 empty] | 111 | 2025-01-01 | 266 | 4423.2998 | 4993.9958 | 851282.9704 | 1008707.0069
[17 empty] | 111 | 2025-01-02 | 267 | 4423.2998 | 4993.9958 | 855706.2703 | 1013701.0027
[17 empty] | 111 | 2025-01-03 | 268 | 4423.2998 | 4993.9958 | 860129.5701 | 1018694.9985
[17 empty] | 111 | 2025-01-04 | 269 | 0 | 0 | 860129.5701 | 1018694.9985
[17 empty] | 111 | 2025-01-05 | 270 | 0 | 0 | 860129.5701 | 1018694.9985
[17 empty] | 111 | 2025-01-06 | 271 | 4423.2998 | 4993.9958 | 864552.87 | 1023688.9944
[17 empty] | 111 | 2025-01-07 | 272 | 4423.2998 | 4993.9958 | 868976.1698 | 1028682.9902
[17 empty] | 111 | 2025-01-08 | 273 | 4423.2998 | 4993.9958 | 873399.4696 | 1033676.986
[17 empty] | 111 | 2025-01-09 | 274 | 4423.2998 | 4993.9958 | 877822.7695 | 1038670.9818
[17 empty] | 111 | 2025-01-10 | 275 | 4423.2998 | 4993.9958 | 882246.0693 | 1043664.9777
[17 empty] | 111 | 2025-01-11 | 276 | 0 | 0 | 882246.0693 | 1043664.9777
[17 empty] | 111 | 2025-01-12 | 277 | 0 | 0 | 882246.0693 | 1043664.9777
[17 empty] | 111 | 2025-01-13 | 278 | 4423.2998 | 4993.9958 | 886669.3692 | 1048658.9735
[17 empty] | 111 | 2025-01-14 | 279 | 4423.2998 | 4993.9958 | 891092.669 | 1053652.9693
[17 empty] | 111 | 2025-01-15 | 280 | 4423.2998 | 4993.9958 | 895515.9689 | 1058646.9651
[17 empty] | 111 | 2025-01-16 | 281 | 4423.2998 | 4993.9958 | 899939.2687 | 1063640.961
[17 empty] | 111 | 2025-01-17 | 282 | 4423.2998 | 4993.9958 | 904362.5686 | 1068634.9568
[17 empty] | 111 | 2025-01-18 | 283 | 0 | 0 | 904362.5686 | 1068634.9568
[17 empty] | 111 | 2025-01-19 | 284 | 0 | 0 | 904362.5686 | 1068634.9568
[17 empty] | 111 | 2025-01-20 | 285 | 4423.2998 | 4993.9958 | 908785.8684 | 1073628.9526
[17 empty] | 111 | 2025-01-21 | 286 | 4423.2998 | 4993.9958 | 913209.1682 | 1078622.9484
[17 empty] | 111 | 2025-01-22 | 287 | 4423.2998 | 4993.9958 | 917632.4681 | 1083616.9443
[17 empty] | 111 | 2025-01-23 | 288 | 4423.2998 | 4993.9958 | 922055.7679 | 1088610.9401
[17 empty] | 111 | 2025-01-24 | 289 | 4423.2998 | 4993.9958 | 926479.0678 | 1093604.9359
[17 empty] | 111 | 2025-01-25 | 290 | 0 | 0 | 926479.0678 | 1093604.9359
[17 empty] | 111 | 2025-01-26 | 291 | 0 | 0 | 926479.0678 | 1093604.9359
[17 empty] | 111 | 2025-01-27 | 292 | 4423.2998 | 4993.9958 | 930902.3676 | 1098598.9317
[17 empty] | 111 | 2025-01-28 | 293 | 4423.2998 | 4993.9958 | 935325.6675 | 1103592.9276
[17 empty] | 111 | 2025-01-29 | 294 | 4423.2998 | 4993.9958 | 939748.9673 | 1108586.9234
[17 empty] | 111 | 2025-01-30 | 295 | 4423.2998 | 4993.9958 | 944172.2672 | 1113580.9192
[17 empty] | 111 | 2025-01-31 | 296 | 4423.2998 | 4993.9958 | 948595.567 | 1118574.915
[17 empty] | 111 | 2025-02-01 | 297 | 0 | 0 | 948595.567 | 1118574.915
[17 empty] | 111 | 2025-02-02 | 298 | 0 | 0 | 948595.567 | 1118574.915
[17 empty] | 111 | 2025-02-03 | 299 | 4423.2998 | 4993.9958 | 953018.8668 | 1123568.9109
[17 empty] | 111 | 2025-02-04 | 300 | 4423.2998 | 4993.9958 | 957442.1667 | 1128562.9067
[17 empty] | 111 | 2025-02-05 | 301 | 4423.2998 | 4993.9958 | 961865.4665 | 1133556.9025
[17 empty] | 111 | 2025-02-06 | 302 | 4423.2998 | 4993.9958 | 966288.7664 | 1138550.8983
[17 empty] | 111 | 2025-02-07 | 303 | 4423.2998 | 4993.9958 | 970712.0662 | 1143544.8942
[17 empty] | 111 | 2025-02-08 | 304 | 0 | 0 | 970712.0662 | 1143544.8942
[17 empty] | 111 | 2025-02-09 | 305 | 0 | 0 | 970712.0662 | 1143544.8942
[17 empty] | 111 | 2025-02-10 | 306 | 4423.2998 | 4993.9958 | 975135.3661 | 1148538.89
[17 empty] | 111 | 2025-02-11 | 307 | 4423.2998 | 4993.9958 | 979558.6659 | 1153532.8858
[17 empty] | 111 | 2025-02-12 | 308 | 4423.2998 | 4993.9958 | 983981.9658 | 1158526.8816
[17 empty] | 111 | 2025-02-13 | 309 | 4423.2998 | 4993.9958 | 988405.2656 | 1163520.8775
[17 empty] | 111 | 2025-02-14 | 310 | 4423.2998 | 4993.9958 | 992828.5654 | 1168514.8733
[17 empty] | 111 | 2025-02-15 | 311 | 0 | 0 | 992828.5654 | 1168514.8733
[17 empty] | 111 | 2025-02-16 | 312 | 0 | 0 | 992828.5654 | 1168514.8733
[17 empty] | 111 | 2025-02-17 | 313 | 4423.2998 | 4993.9958 | 997251.8653 | 1173508.8691
[17 empty] | 111 | 2025-02-18 | 314 | 4423.2998 | 4993.9958 | 1001675.1651 | 1178502.865
[17 empty] | 111 | 2025-02-19 | 315 | 4423.2998 | 4993.9958 | 1006098.465 | 1183496.8608
[17 empty] | 111 | 2025-02-20 | 316 | 4423.2998 | 4993.9958 | 1010521.7648 | 1188490.8566
[17 empty] | 111 | 2025-02-21 | 317 | 4423.2998 | 4993.9958 | 1014945.0647 | 1193484.8524
[17 empty] | 111 | 2025-02-22 | 318 | 0 | 0 | 1014945.0647 | 1193484.8524
[17 empty] | 111 | 2025-02-23 | 319 | 0 | 0 | 1014945.0647 | 1193484.8524
[17 empty] | 111 | 2025-02-24 | 320 | 4423.2998 | 4993.9958 | 1019368.3645 | 1198478.8483
[17 empty] | 111 | 2025-02-25 | 321 | 4423.2998 | 4993.9958 | 1023791.6644 | 1203472.8441
[17 empty] | 111 | 2025-02-26 | 322 | 4423.2998 | 4993.9958 | 1028214.9642 | 1208466.8399
[17 empty] | 111 | 2025-02-27 | 323 | 4423.2998 | 4993.9958 | 1032638.264 | 1213460.8357
[17 empty] | 111 | 2025-02-28 | 324 | 4423.2998 | 4993.9958 | 1037061.5639 | 1218454.8316
[17 empty] | 111 | 2025-03-01 | 325 | 0 | 0 | 1037061.5639 | 1218454.8316
[17 empty] | 111 | 2025-03-02 | 326 | 0 | 0 | 1037061.5639 | 1218454.8316
[17 empty] | 111 | 2025-03-03 | 327 | 4423.2998 | 4993.9958 | 1041484.8637 | 1223448.8274
[17 empty] | 111 | 2025-03-04 | 328 | 4423.2998 | 4993.9958 | 1045908.1636 | 1228442.8232
[17 empty] | 111 | 2025-03-05 | 329 | 4423.2998 | 4993.9958 | 1050331.4634 | 1233436.819
[17 empty] | 111 | 2025-03-06 | 330 | 4423.2998 | 4993.9958 | 1054754.7633 | 1238430.8149
[17 empty] | 111 | 2025-03-07 | 331 | 4423.2998 | 4993.9958 | 1059178.0631 | 1243424.8107
[17 empty] | 111 | 2025-03-08 | 332 | 0 | 0 | 1059178.0631 | 1243424.8107
[17 empty] | 111 | 2025-03-09 | 333 | 0 | 0 | 1059178.0631 | 1243424.8107
[17 empty] | 111 | 2025-03-10 | 334 | 4423.2998 | 4993.9958 | 1063601.363 | 1248418.8065
[17 empty] | 111 | 2025-03-11 | 335 | 4423.2998 | 4993.9958 | 1068024.6628 | 1253412.8023
[17 empty] | 111 | 2025-03-12 | 336 | 4423.2998 | 4993.9958 | 1072447.9626 | 1258406.7982
[17 empty] | 111 | 2025-03-13 | 337 | 4423.2998 | 4993.9958 | 1076871.2625 | 1263400.794
[17 empty] | 111 | 2025-03-14 | 338 | 4423.2998 | 4993.9958 | 1081294.5623 | 1268394.7898
[17 empty] | 111 | 2025-03-15 | 339 | 0 | 0 | 1081294.5623 | 1268394.7898
[17 empty] | 111 | 2025-03-16 | 340 | 0 | 0 | 1081294.5623 | 1268394.7898
[17 empty] | 111 | 2025-03-17 | 341 | 4423.2998 | 4993.9958 | 1085717.8622 | 1273388.7856
[17 empty] | 111 | 2025-03-18 | 342 | 4423.2998 | 4993.9958 | 1090141.162 | 1278382.7815
[17 empty] | 111 | 2025-03-19 | 343 | 4423.2998 | 4993.9958 | 1094564.4619 | 1283376.7773
[17 empty] | 111 | 2025-03-20 | 344 | 4423.2998 | 4993.9958 | 1098987.7617 | 1288370.7731
[17 empty] | 111 | 2025-03-21 | 345 | 4423.2998 | 4993.9958 | 1103411.0616 | 1293364.7689
[17 empty] | 111 | 2025-03-22 | 346 | 0 | 0 | 1103411.0616 | 1293364.7689
[17 empty] | 111 | 2025-03-23 | 347 | 0 | 0 | 1103411.0616 | 1293364.7689
[17 empty] | 111 | 2025-03-24 | 348 | 4423.2998 | 4993.9958 | 1107834.3614 | 1298358.7648
[17 empty] | 111 | 2025-03-25 | 349 | 4423.2998 | 4993.9958 | 1112257.6612 | 1303352.7606
[17 empty] | 111 | 2025-03-26 | 350 | 4423.2998 | 4993.9958 | 1116680.9611 | 1308346.7564
[17 empty] | 111 | 2025-03-27 | 351 | 4423.2998 | 4993.9958 | 1121104.2609 | 1313340.7522
[17 empty] | 111 | 2025-03-28 | 352 | 433.2998 | 485.2958 | 1121537.5608 | 1313826.0481
[17 empty] | 111 | 2025-03-29 | 353 | 0 | 0 | 1121537.5608 | 1313826.0481
[17 empty] | 111 | 2025-03-30 | 354 | 0 | 0 | 1121537.5608 | 1313826.0481
[17 empty] | 111 | 2025-03-31 | 355 | 433.2998 | 485.2958 | 1121970.8606 | 1314311.3439
[17 empty] | 111 | 2025-04-01 | 356 | 433.2998 | 485.2958 | 1122404.1605 | 1314796.6397
[17 empty] | 111 | 2025-04-02 | 357 | 433.2998 | 485.2958 | 1122837.4603 | 1315281.9355
[17 empty] | 111 | 2025-04-03 | 358 | 433.2998 | 485.2958 | 1123270.7602 | 1315767.2314
[17 empty] | 111 | 2025-04-04 | 359 | 433.2998 | 485.2958 | 1123704.06 | 1316252.5272
[17 empty] | 111 | 2025-04-05 | 360 | 0 | 0 | 1123704.06 | 1316252.5272
[17 empty] | 111 | 2025-04-06 | 361 | 0 | 0 | 1123704.06 | 1316252.5272
[17 empty] | 112 | 2024-05-01 | 1 | 490.3822 | 622.7854 | 490.3822 | 622.7854
[17 empty] | 112 | 2024-05-02 | 2 | 490.3822 | 622.7854 | 980.7644 | 1245.5708
[17 empty] | 112 | 2024-05-03 | 3 | 490.3822 | 622.7854 | 1471.1466 | 1868.3562
[17 empty] | 112 | 2024-05-04 | 4 | 0 | 0 | 1471.1466 | 1868.3562
[17 empty] | 112 | 2024-05-05 | 5 | 0 | 0 | 1471.1466 | 1868.3562
[17 empty] | 112 | 2024-05-06 | 6 | 5055.8267 | 6283.9365 | 6526.9733 | 8152.2927
[17 empty] | 112 | 2024-05-07 | 7 | 5055.8267 | 6283.9365 | 11582.7999 | 14436.2292
[17 empty] | 112 | 2024-05-08 | 8 | 5055.8267 | 6283.9365 | 16638.6266 | 20720.1658
[17 empty] | 112 | 2024-05-09 | 9 | 5055.8267 | 6283.9365 | 21694.4532 | 27004.1023
[17 empty] | 112 | 2024-05-10 | 10 | 5055.8267 | 6283.9365 | 26750.2799 | 33288.0388
[17 empty] | 112 | 2024-05-11 | 11 | 0 | 0 | 26750.2799 | 33288.0388
[17 empty] | 112 | 2024-05-12 | 12 | 0 | 0 | 26750.2799 | 33288.0388
[17 empty] | 112 | 2024-05-13 | 13 | 5055.8267 | 6283.9365 | 31806.1065 | 39571.9753
[17 empty] | 112 | 2024-05-14 | 14 | 5055.8267 | 6283.9365 | 36861.9332 | 45855.9118
[17 empty] | 112 | 2024-05-15 | 15 | 5055.8267 | 6283.9365 | 41917.7599 | 52139.8483
[17 empty] | 112 | 2024-05-16 | 16 | 5055.8267 | 6283.9365 | 46973.5865 | 58423.7849
[17 empty] | 112 | 2024-05-17 | 17 | 5055.8267 | 6283.9365 | 52029.4132 | 64707.7214
[17 empty] | 112 | 2024-05-18 | 18 | 0 | 0 | 52029.4132 | 64707.7214
[17 empty] | 112 | 2024-05-19 | 19 | 0 | 0 | 52029.4132 | 64707.7214
[17 empty] | 112 | 2024-05-20 | 20 | 5055.8267 | 6283.9365 | 57085.2398 | 70991.6579
[17 empty] | 112 | 2024-05-21 | 21 | 5055.8267 | 6283.9365 | 62141.0665 | 77275.5944
[17 empty] | 112 | 2024-05-22 | 22 | 5055.8267 | 6283.9365 | 67196.8931 | 83559.5309
[17 empty] | 112 | 2024-05-23 | 23 | 5055.8267 | 6283.9365 | 72252.7198 | 89843.4674
[17 empty] | 112 | 2024-05-24 | 24 | 5055.8267 | 6283.9365 | 77308.5464 | 96127.404
[17 empty] | 112 | 2024-05-25 | 25 | 0 | 0 | 77308.5464 | 96127.404
[17 empty] | 112 | 2024-05-26 | 26 | 0 | 0 | 77308.5464 | 96127.404
[17 empty] | 112 | 2024-05-27 | 27 | 5055.8267 | 6283.9365 | 82364.3731 | 102411.3405
[17 empty] | 112 | 2024-05-28 | 28 | 5055.8267 | 6283.9365 | 87420.1997 | 108695.277
[17 empty] | 112 | 2024-05-29 | 29 | 7632.8948 | 9170.2529 | 95053.0946 | 117865.5299
[17 empty] | 112 | 2024-05-30 | 30 | 3067.4504 | 3509.1018 | 98120.545 | 121374.6316
[17 empty] | 112 | 2024-05-31 | 31 | 3067.4504 | 3509.1018 | 101187.9953 | 124883.7334
[17 empty] | 112 | 2024-06-01 | 32 | 0 | 0 | 101187.9953 | 124883.7334
[17 empty] | 112 | 2024-06-02 | 33 | 0 | 0 | 101187.9953 | 124883.7334
[17 empty] | 112 | 2024-06-03 | 34 | 3067.4504 | 3509.1018 | 104255.4457 | 128392.8352
[17 empty] | 112 | 2024-06-04 | 35 | 3067.4504 | 3509.1018 | 107322.8961 | 131901.9369
[17 empty] | 112 | 2024-06-05 | 36 | 3067.4504 | 3509.1018 | 110390.3465 | 135411.0387
[17 empty] | 112 | 2024-06-06 | 37 | 3067.4504 | 3509.1018 | 113457.7969 | 138920.1405
[17 empty] | 112 | 2024-06-07 | 38 | 3067.4504 | 3509.1018 | 116525.2473 | 142429.2422
[17 empty] | 112 | 2024-06-08 | 39 | 0 | 0 | 116525.2473 | 142429.2422
[17 empty] | 112 | 2024-06-09 | 40 | 0 | 0 | 116525.2473 | 142429.2422
[17 empty] | 112 | 2024-06-10 | 41 | 3067.4504 | 3509.1018 | 119592.6977 | 145938.344
[17 empty] | 112 | 2024-06-11 | 42 | 3067.4504 | 3509.1018 | 122660.1481 | 149447.4458
[17 empty] | 112 | 2024-06-12 | 43 | 3067.4504 | 3509.1018 | 125727.5985 | 152956.5476
[17 empty] | 112 | 2024-06-13 | 44 | 3067.4504 | 3509.1018 | 128795.0489 | 156465.6493
[17 empty] | 112 | 2024-06-14 | 45 | 3067.4504 | 3509.1018 | 131862.4992 | 159974.7511
[17 empty] | 112 | 2024-06-15 | 46 | 0 | 0 | 131862.4992 | 159974.7511
[17 empty] | 112 | 2024-06-16 | 47 | 0 | 0 | 131862.4992 | 159974.7511
[17 empty] | 112 | 2024-06-17 | 48 | 3067.4504 | 3509.1018 | 134929.9496 | 163483.8529
[17 empty] | 112 | 2024-06-18 | 49 | 3067.4504 | 3509.1018 | 137997.4 | 166992.9546
[17 empty] | 112 | 2024-06-19 | 50 | 3067.4504 | 3509.1018 | 141064.8504 | 170502.0564
[17 empty] | 112 | 2024-06-20 | 51 | 3067.4504 | 3509.1018 | 144132.3008 | 174011.1582
[17 empty] | 112 | 2024-06-21 | 52 | 3067.4504 | 3509.1018 | 147199.7512 | 177520.2599
[17 empty] | 112 | 2024-06-22 | 53 | 0 | 0 | 147199.7512 | 177520.2599
[17 empty] | 112 | 2024-06-23 | 54 | 0 | 0 | 147199.7512 | 177520.2599
[17 empty] | 112 | 2024-06-24 | 55 | 3067.4504 | 3509.1018 | 150267.2016 | 181029.3617
[17 empty] | 112 | 2024-06-25 | 56 | 3067.4504 | 3509.1018 | 153334.652 | 184538.4635
[17 empty] | 112 | 2024-06-26 | 57 | 3067.4504 | 3509.1018 | 156402.1024 | 188047.5652
[17 empty] | 112 | 2024-06-27 | 58 | 3067.4504 | 3509.1018 | 159469.5528 | 191556.667
[17 empty] | 112 | 2024-06-28 | 59 | 3067.4504 | 3509.1018 | 162537.0032 | 195065.7688
[17 empty] | 112 | 2024-06-29 | 60 | 0 | 0 | 162537.0032 | 195065.7688
[17 empty] | 112 | 2024-06-30 | 61 | 0 | 0 | 162537.0032 | 195065.7688
[17 empty] | 112 | 2024-07-01 | 62 | 3067.4504 | 3509.1018 | 165604.4535 | 198574.8705
[17 empty] | 112 | 2024-07-02 | 63 | 3067.4504 | 3509.1018 | 168671.9039 | 202083.9723
[17 empty] | 112 | 2024-07-03 | 64 | 3067.4504 | 3509.1018 | 171739.3543 | 205593.0741
[17 empty] | 112 | 2024-07-04 | 65 | 3067.4504 | 3509.1018 | 174806.8047 | 209102.1758
[17 empty] | 112 | 2024-07-05 | 66 | 3067.4504 | 3509.1018 | 177874.2551 | 212611.2776
[17 empty] | 112 | 2024-07-06 | 67 | 0 | 0 | 177874.2551 | 212611.2776
[17 empty] | 112 | 2024-07-07 | 68 | 0 | 0 | 177874.2551 | 212611.2776
[17 empty] | 112 | 2024-07-08 | 69 | 3067.4504 | 3509.1018 | 180941.7055 | 216120.3794
[17 empty] | 112 | 2024-07-09 | 70 | 7714.1683 | 9131.6305 | 188655.8738 | 225252.0099
[17 empty] | 112 | 2024-07-10 | 71 | 7714.1683 | 9131.6305 | 196370.0422 | 234383.6404
[17 empty] | 112 | 2024-07-11 | 72 | 7714.1683 | 9131.6305 | 204084.2105 | 243515.2708
[17 empty] | 112 | 2024-07-12 | 73 | 7714.1683 | 9131.6305 | 211798.3789 | 252646.9013
[17 empty] | 112 | 2024-07-13 | 74 | 0 | 0 | 211798.3789 | 252646.9013
[17 empty] | 112 | 2024-07-14 | 75 | 0 | 0 | 211798.3789 | 252646.9013
[17 empty] | 112 | 2024-07-15 | 76 | 7714.1683 | 9131.6305 | 219512.5472 | 261778.5318
[17 empty] | 112 | 2024-07-16 | 77 | 7714.1683 | 9131.6305 | 227226.7155 | 270910.1623
[17 empty] | 112 | 2024-07-17 | 78 | 7714.1683 | 9131.6305 | 234940.8839 | 280041.7928
[17 empty] | 112 | 2024-07-18 | 79 | 7714.1683 | 9131.6305 | 242655.0522 | 289173.4233
[17 empty] | 112 | 2024-07-19 | 80 | 12025.7194 | 14305.4917 | 254680.7716 | 303478.915
[17 empty] | 112 | 2024-07-20 | 81 | 0 | 0 | 254680.7716 | 303478.915
[17 empty] | 112 | 2024-07-21 | 82 | 0 | 0 | 254680.7716 | 303478.915
[17 empty] | 112 | 2024-07-22 | 83 | 12025.7194 | 14305.4917 | 266706.4909 | 317784.4067
[17 empty] | 112 | 2024-07-23 | 84 | 12025.7194 | 14305.4917 | 278732.2103 | 332089.8984
[17 empty] | 112 | 2024-07-24 | 85 | 12025.7194 | 14305.4917 | 290757.9296 | 346395.3901
[17 empty] | 112 | 2024-07-25 | 86 | 12025.7194 | 14305.4917 | 302783.649 | 360700.8818
[17 empty] | 112 | 2024-07-26 | 87 | 12025.7194 | 14305.4917 | 314809.3684 | 375006.3735
[17 empty] | 112 | 2024-07-27 | 88 | 0 | 0 | 314809.3684 | 375006.3735
[17 empty] | 112 | 2024-07-28 | 89 | 0 | 0 | 314809.3684 | 375006.3735
[17 empty] | 112 | 2024-07-29 | 90 | 12025.7194 | 14305.4917 | 326835.0877 | 389311.8653
[17 empty] | 112 | 2024-07-30 | 91 | 9448.6512 | 11419.1753 | 336283.7389 | 400731.0406
[17 empty] | 112 | 2024-07-31 | 92 | 9448.6512 | 11419.1753 | 345732.3901 | 412150.2159
[17 empty] | 112 | 2024-08-01 | 93 | 9448.6512 | 11419.1753 | 355181.0413 | 423569.3913
[17 empty] | 112 | 2024-08-02 | 94 | 9448.6512 | 11419.1753 | 364629.6924 | 434988.5666
[17 empty] | 112 | 2024-08-03 | 95 | 0 | 0 | 364629.6924 | 434988.5666
[17 empty] | 112 | 2024-08-04 | 96 | 0 | 0 | 364629.6924 | 434988.5666
[17 empty] | 112 | 2024-08-05 | 97 | 9448.6512 | 11419.1753 | 374078.3436 | 446407.742
[17 empty] | 112 | 2024-08-06 | 98 | 9448.6512 | 11419.1753 | 383526.9948 | 457826.9173
[17 empty] | 112 | 2024-08-07 | 99 | 9448.6512 | 11419.1753 | 392975.646 | 469246.0927
[17 empty] | 112 | 2024-08-08 | 100 | 9448.6512 | 11419.1753 | 402424.2971 | 480665.268
[17 empty] | 112 | 2024-08-09 | 101 | 9448.6512 | 11419.1753 | 411872.9483 | 492084.4434
[17 empty] | 112 | 2024-08-10 | 102 | 0 | 0 | 411872.9483 | 492084.4434
[17 empty] | 112 | 2024-08-11 | 103 | 0 | 0 | 411872.9483 | 492084.4434
[17 empty] | 112 | 2024-08-12 | 104 | 9448.6512 | 11419.1753 | 421321.5995 | 503503.6187
[17 empty] | 112 | 2024-08-13 | 105 | 9448.6512 | 11419.1753 | 430770.2507 | 514922.7941
[17 empty] | 112 | 2024-08-14 | 106 | 9448.6512 | 11419.1753 | 440218.9019 | 526341.9694
[17 empty] | 112 | 2024-08-15 | 107 | 9448.6512 | 11419.1753 | 449667.553 | 537761.1448
[17 empty] | 112 | 2024-08-16 | 108 | 9448.6512 | 11419.1753 | 459116.2042 | 549180.3201
[17 empty] | 112 | 2024-08-17 | 109 | 0 | 0 | 459116.2042 | 549180.3201
[17 empty] | 112 | 2024-08-18 | 110 | 0 | 0 | 459116.2042 | 549180.3201
[17 empty] | 112 | 2024-08-19 | 111 | 9448.6512 | 11419.1753 | 468564.8554 | 560599.4955
[17 empty] | 112 | 2024-08-20 | 112 | 9448.6512 | 11419.1753 | 478013.5066 | 572018.6708
[17 empty] | 112 | 2024-08-21 | 113 | 9448.6512 | 11419.1753 | 487462.1577 | 583437.8462
[17 empty] | 112 | 2024-08-22 | 114 | 9448.6512 | 11419.1753 | 496910.8089 | 594857.0215
[17 empty] | 112 | 2024-08-23 | 115 | 9448.6512 | 11419.1753 | 506359.4601 | 606276.1969
[17 empty] | 112 | 2024-08-24 | 116 | 0 | 0 | 506359.4601 | 606276.1969
[17 empty] | 112 | 2024-08-25 | 117 | 0 | 0 | 506359.4601 | 606276.1969
[17 empty] | 112 | 2024-08-26 | 118 | 9448.6512 | 11419.1753 | 515808.1113 | 617695.3722
[17 empty] | 112 | 2024-08-27 | 119 | 9448.6512 | 11419.1753 | 525256.7625 | 629114.5475
[17 empty] | 112 | 2024-08-28 | 120 | 9448.6512 | 11419.1753 | 534705.4136 | 640533.7229
[17 empty] | 112 | 2024-08-29 | 121 | 9448.6512 | 11419.1753 | 544154.0648 | 651952.8982
[17 empty] | 112 | 2024-08-30 | 122 | 9448.6512 | 11419.1753 | 553602.716 | 663372.0736
[17 empty] | 112 | 2024-08-31 | 123 | 0 | 0 | 553602.716 | 663372.0736
[17 empty] | 112 | 2024-09-01 | 124 | 0 | 0 | 553602.716 | 663372.0736
[17 empty] | 112 | 2024-09-02 | 125 | 4801.9332 | 5796.6466 | 558404.6492 | 669168.7202
[17 empty] | 112 | 2024-09-03 | 126 | 4801.9332 | 5796.6466 | 563206.5824 | 674965.3668
[17 empty] | 112 | 2024-09-04 | 127 | 4801.9332 | 5796.6466 | 568008.5157 | 680762.0135
[17 empty] | 112 | 2024-09-05 | 128 | 4801.9332 | 5796.6466 | 572810.4489 | 686558.6601
[17 empty] | 112 | 2024-09-06 | 129 | 4801.9332 | 5796.6466 | 577612.3821 | 692355.3067
[17 empty] | 112 | 2024-09-07 | 130 | 0 | 0 | 577612.3821 | 692355.3067
[17 empty] | 112 | 2024-09-08 | 131 | 0 | 0 | 577612.3821 | 692355.3067
[17 empty] | 112 | 2024-09-09 | 132 | 4801.9332 | 5796.6466 | 582414.3154 | 698151.9534
[17 empty] | 112 | 2024-09-10 | 133 | 4801.9332 | 5796.6466 | 587216.2486 | 703948.6
[17 empty] | 112 | 2024-09-11 | 134 | 4801.9332 | 5796.6466 | 592018.1818 | 709745.2466
[17 empty] | 112 | 2024-09-12 | 135 | 4801.9332 | 5796.6466 | 596820.115 | 715541.8933
[17 empty] | 112 | 2024-09-13 | 136 | 4801.9332 | 5796.6466 | 601622.0483 | 721338.5399
[17 empty] | 112 | 2024-09-14 | 137 | 0 | 0 | 601622.0483 | 721338.5399
[17 empty] | 112 | 2024-09-15 | 138 | 0 | 0 | 601622.0483 | 721338.5399
[17 empty] | 112 | 2024-09-16 | 139 | 4801.9332 | 5796.6466 | 606423.9815 | 727135.1865
[17 empty] | 112 | 2024-09-17 | 140 | 4801.9332 | 5796.6466 | 611225.9147 | 732931.8331
[17 empty] | 112 | 2024-09-18 | 141 | 4801.9332 | 5796.6466 | 616027.848 | 738728.4798
[17 empty] | 112 | 2024-09-19 | 142 | 4801.9332 | 5796.6466 | 620829.7812 | 744525.1264
[17 empty] | 112 | 2024-09-20 | 143 | 4801.9332 | 5796.6466 | 625631.7144 | 750321.773
[17 empty] | 112 | 2024-09-21 | 144 | 0 | 0 | 625631.7144 | 750321.773
[17 empty] | 112 | 2024-09-22 | 145 | 0 | 0 | 625631.7144 | 750321.773
[17 empty] | 112 | 2024-09-23 | 146 | 4801.9332 | 5796.6466 | 630433.6477 | 756118.4197
[17 empty] | 112 | 2024-09-24 | 147 | 4801.9332 | 5796.6466 | 635235.5809 | 761915.0663
[17 empty] | 112 | 2024-09-25 | 148 | 4801.9332 | 5796.6466 | 640037.5141 | 767711.7129
[17 empty] | 112 | 2024-09-26 | 149 | 4801.9332 | 5796.6466 | 644839.4473 | 773508.3595
[17 empty] | 112 | 2024-09-27 | 150 | 4801.9332 | 5796.6466 | 649641.3806 | 779305.0062
[17 empty] | 112 | 2024-09-28 | 151 | 0 | 0 | 649641.3806 | 779305.0062
[17 empty] | 112 | 2024-09-29 | 152 | 0 | 0 | 649641.3806 | 779305.0062
[17 empty] | 112 | 2024-09-30 | 153 | 4801.9332 | 5796.6466 | 654443.3138 | 785101.6528
[17 empty] | 112 | 2024-10-01 | 154 | 4801.9332 | 5796.6466 | 659245.247 | 790898.2994
[17 empty] | 112 | 2024-10-02 | 155 | 4801.9332 | 5796.6466 | 664047.1803 | 796694.9461
[17 empty] | 112 | 2024-10-03 | 156 | 4801.9332 | 5796.6466 | 668849.1135 | 802491.5927
[17 empty] | 112 | 2024-10-04 | 157 | 4801.9332 | 5796.6466 | 673651.0467 | 808288.2393
[17 empty] | 112 | 2024-10-05 | 158 | 0 | 0 | 673651.0467 | 808288.2393
[17 empty] | 112 | 2024-10-06 | 159 | 0 | 0 | 673651.0467 | 808288.2393
[17 empty] | 112 | 2024-10-07 | 160 | 4801.9332 | 5796.6466 | 678452.9799 | 814084.886
[17 empty] | 112 | 2024-10-08 | 161 | 4801.9332 | 5796.6466 | 683254.9132 | 819881.5326
[17 empty] | 112 | 2024-10-09 | 162 | 4801.9332 | 5796.6466 | 688056.8464 | 825678.1792
[17 empty] | 112 | 2024-10-10 | 163 | 4801.9332 | 5796.6466 | 692858.7796 | 831474.8258
[17 empty] | 112 | 2024-10-11 | 164 | 4801.9332 | 5796.6466 | 697660.7129 | 837271.4725
[17 empty] | 112 | 2024-10-12 | 165 | 0 | 0 | 697660.7129 | 837271.4725
[17 empty] | 112 | 2024-10-13 | 166 | 0 | 0 | 697660.7129 | 837271.4725
[17 empty] | 112 | 2024-10-14 | 167 | 4801.9332 | 5796.6466 | 702462.6461 | 843068.1191
[17 empty] | 112 | 2024-10-15 | 168 | 4801.9332 | 5796.6466 | 707264.5793 | 848864.7657
[17 empty] | 112 | 2024-10-16 | 169 | 4801.9332 | 5796.6466 | 712066.5125 | 854661.4124
[17 empty] | 112 | 2024-10-17 | 170 | 4801.9332 | 5796.6466 | 716868.4458 | 860458.059
[17 empty] | 112 | 2024-10-18 | 171 | 4801.9332 | 5796.6466 | 721670.379 | 866254.7056
[17 empty] | 112 | 2024-10-19 | 172 | 0 | 0 | 721670.379 | 866254.7056
[17 empty] | 112 | 2024-10-20 | 173 | 0 | 0 | 721670.379 | 866254.7056
[17 empty] | 112 | 2024-10-21 | 174 | 4801.9332 | 5796.6466 | 726472.3122 | 872051.3522
[17 empty] | 112 | 2024-10-22 | 175 | 4801.9332 | 5796.6466 | 731274.2455 | 877847.9989
[17 empty] | 112 | 2024-10-23 | 176 | 4801.9332 | 5796.6466 | 736076.1787 | 883644.6455
[17 empty] | 112 | 2024-10-24 | 177 | 4801.9332 | 5796.6466 | 740878.1119 | 889441.2921
[17 empty] | 112 | 2024-10-25 | 178 | 4801.9332 | 5796.6466 | 745680.0451 | 895237.9388
[17 empty] | 112 | 2024-10-26 | 179 | 0 | 0 | 745680.0451 | 895237.9388
[17 empty] | 112 | 2024-10-27 | 180 | 0 | 0 | 745680.0451 | 895237.9388
[17 empty] | 112 | 2024-10-28 | 181 | 4801.9332 | 5796.6466 | 750481.9784 | 901034.5854
[17 empty] | 112 | 2024-10-29 | 182 | 4801.9332 | 5796.6466 | 755283.9116 | 906831.232
[17 empty] | 112 | 2024-10-30 | 183 | 4801.9332 | 5796.6466 | 760085.8448 | 912627.8787
[17 empty] | 112 | 2024-10-31 | 184 | 4801.9332 | 5796.6466 | 764887.7781 | 918424.5253
[17 empty] | 112 | 2024-11-01 | 185 | 4801.9332 | 5796.6466 | 769689.7113 | 924221.1719
[17 empty] | 112 | 2024-11-02 | 186 | 0 | 0 | 769689.7113 | 924221.1719
[17 empty] | 112 | 2024-11-03 | 187 | 0 | 0 | 769689.7113 | 924221.1719
[17 empty] | 112 | 2024-11-04 | 188 | 4801.9332 | 5796.6466 | 774491.6445 | 930017.8185
[17 empty] | 112 | 2024-11-05 | 189 | 4801.9332 | 5796.6466 | 779293.5778 | 935814.4652
[17 empty] | 112 | 2024-11-06 | 190 | 4801.9332 | 5796.6466 | 784095.511 | 941611.1118
[17 empty] | 112 | 2024-11-07 | 191 | 4801.9332 | 5796.6466 | 788897.4442 | 947407.7584
[17 empty] | 112 | 2024-11-08 | 192 | 4801.9332 | 5796.6466 | 793699.3774 | 953204.4051
[17 empty] | 112 | 2024-11-09 | 193 | 0 | 0 | 793699.3774 | 953204.4051
[17 empty] | 112 | 2024-11-10 | 194 | 0 | 0 | 793699.3774 | 953204.4051
[17 empty] | 112 | 2024-11-11 | 195 | 4801.9332 | 5796.6466 | 798501.3107 | 959001.0517
[17 empty] | 112 | 2024-11-12 | 196 | 4801.9332 | 5796.6466 | 803303.2439 | 964797.6983
[17 empty] | 112 | 2024-11-13 | 197 | 4801.9332 | 5796.6466 | 808105.1771 | 970594.3449
[17 empty] | 112 | 2024-11-14 | 198 | 4801.9332 | 5796.6466 | 812907.1104 | 976390.9916
[17 empty] | 112 | 2024-11-15 | 199 | 4801.9332 | 5796.6466 | 817709.0436 | 982187.6382
[17 empty] | 112 | 2024-11-16 | 200 | 0 | 0 | 817709.0436 | 982187.6382
[17 empty] | 112 | 2024-11-17 | 201 | 0 | 0 | 817709.0436 | 982187.6382
[17 empty] | 112 | 2024-11-18 | 202 | 4801.9332 | 5796.6466 | 822510.9768 | 987984.2848
[17 empty] | 112 | 2024-11-19 | 203 | 4801.9332 | 5796.6466 | 827312.91 | 993780.9315
[17 empty] | 112 | 2024-11-20 | 204 | 4801.9332 | 5796.6466 | 832114.8433 | 999577.5781
[17 empty] | 112 | 2024-11-21 | 205 | 4801.9332 | 5796.6466 | 836916.7765 | 1005374.2247
[17 empty] | 112 | 2024-11-22 | 206 | 4801.9332 | 5796.6466 | 841718.7097 | 1011170.8714
[17 empty] | 112 | 2024-11-23 | 207 | 0 | 0 | 841718.7097 | 1011170.8714
[17 empty] | 112 | 2024-11-24 | 208 | 0 | 0 | 841718.7097 | 1011170.8714
[17 empty] | 112 | 2024-11-25 | 209 | 4801.9332 | 5796.6466 | 846520.643 | 1016967.518
[17 empty] | 112 | 2024-11-26 | 210 | 4801.9332 | 5796.6466 | 851322.5762 | 1022764.1646
[17 empty] | 112 | 2024-11-27 | 211 | 4801.9332 | 5796.6466 | 856124.5094 | 1028560.8112
[17 empty] | 112 | 2024-11-28 | 212 | 4801.9332 | 5796.6466 | 860926.4426 | 1034357.4579
[17 empty] | 112 | 2024-11-29 | 213 | 4801.9332 | 5796.6466 | 865728.3759 | 1040154.1045
[17 empty] | 112 | 2024-11-30 | 214 | 0 | 0 | 865728.3759 | 1040154.1045
[17 empty] | 112 | 2024-12-01 | 215 | 0 | 0 | 865728.3759 | 1040154.1045
[17 empty] | 112 | 2024-12-02 | 216 | 4801.9332 | 5796.6466 | 870530.3091 | 1045950.7511
[17 empty] | 112 | 2024-12-03 | 217 | 4801.9332 | 5796.6466 | 875332.2423 | 1051747.3978
[17 empty] | 112 | 2024-12-04 | 218 | 490.3822 | 622.7854 | 875822.6245 | 1052370.1832
[17 empty] | 112 | 2024-12-05 | 219 | 490.3822 | 622.7854 | 876313.0067 | 1052992.9686
[17 empty] | 112 | 2024-12-06 | 220 | 490.3822 | 622.7854 | 876803.389 | 1053615.754
[17 empty] | 112 | 2024-12-07 | 221 | 0 | 0 | 876803.389 | 1053615.754
[17 empty] | 112 | 2024-12-08 | 222 | 0 | 0 | 876803.389 | 1053615.754
[17 empty] | 112 | 2024-12-09 | 223 | 490.3822 | 622.7854 | 877293.7712 | 1054238.5394
[17 empty] | 112 | 2024-12-10 | 224 | 490.3822 | 622.7854 | 877784.1534 | 1054861.3248
[17 empty] | 112 | 2024-12-11 | 225 | 490.3822 | 622.7854 | 878274.5356 | 1055484.1102
[17 empty] | 112 | 2024-12-12 | 226 | 490.3822 | 622.7854 | 878764.9178 | 1056106.8956
[17 empty] | 112 | 2024-12-13 | 227 | 490.3822 | 622.7854 | 879255.3 | 1056729.681
[17 empty] | 113 | 2024-04-16 | 1 | 441.5264 | 556.3233 | 441.5264 | 556.3233
[17 empty] | 113 | 2024-04-17 | 2 | 441.5264 | 556.3233 | 883.0528 | 1112.6465
[17 empty] | 113 | 2024-04-18 | 3 | 441.5264 | 556.3233 | 1324.5792 | 1668.9698
[17 empty] | 113 | 2024-04-19 | 4 | 441.5264 | 556.3233 | 1766.1056 | 2225.293
[17 empty] | 113 | 2024-04-20 | 5 | 0 | 0 | 1766.1056 | 2225.293
[17 empty] | 113 | 2024-04-21 | 6 | 0 | 0 | 1766.1056 | 2225.293
[17 empty] | 113 | 2024-04-22 | 7 | 3601.5264 | 4348.3233 | 5367.6319 | 6573.6163
[17 empty] | 113 | 2024-04-23 | 8 | 3601.5264 | 4348.3233 | 8969.1583 | 10921.9395
[17 empty] | 113 | 2024-04-24 | 9 | 3601.5264 | 4348.3233 | 12570.6847 | 15270.2628
[17 empty] | 113 | 2024-04-25 | 10 | 3601.5264 | 4348.3233 | 16172.2111 | 19618.586
[17 empty] | 113 | 2024-04-26 | 11 | 3601.5264 | 4348.3233 | 19773.7375 | 23966.9093
[17 empty] | 113 | 2024-04-27 | 12 | 0 | 0 | 19773.7375 | 23966.9093
[17 empty] | 113 | 2024-04-28 | 13 | 0 | 0 | 19773.7375 | 23966.9093
[17 empty] | 113 | 2024-04-29 | 14 | 3601.5264 | 4348.3233 | 23375.2639 | 28315.2325
[17 empty] | 113 | 2024-04-30 | 15 | 3601.5264 | 4348.3233 | 26976.7903 | 32663.5558
[17 empty] | 113 | 2024-05-01 | 16 | 3601.5264 | 4348.3233 | 30578.3167 | 37011.879
[17 empty] | 113 | 2024-05-02 | 17 | 3601.5264 | 4348.3233 | 34179.8431 | 41360.2023
[17 empty] | 113 | 2024-05-03 | 18 | 3601.5264 | 4348.3233 | 37781.3694 | 45708.5255
[17 empty] | 113 | 2024-05-04 | 19 | 0 | 0 | 37781.3694 | 45708.5255
[17 empty] | 113 | 2024-05-05 | 20 | 0 | 0 | 37781.3694 | 45708.5255
[17 empty] | 113 | 2024-05-06 | 21 | 3601.5264 | 4348.3233 | 41382.8958 | 50056.8488
[17 empty] | 113 | 2024-05-07 | 22 | 3601.5264 | 4348.3233 | 44984.4222 | 54405.172
[17 empty] | 113 | 2024-05-08 | 23 | 3601.5264 | 4348.3233 | 48585.9486 | 58753.4953
[17 empty] | 113 | 2024-05-09 | 24 | 6673.9742 | 8127.434 | 55259.9228 | 66880.9292
[17 empty] | 113 | 2024-05-10 | 25 | 3513.9742 | 4335.434 | 58773.8969 | 71216.3632
[17 empty] | 113 | 2024-05-11 | 26 | 0 | 0 | 58773.8969 | 71216.3632
[17 empty] | 113 | 2024-05-12 | 27 | 0 | 0 | 58773.8969 | 71216.3632
[17 empty] | 113 | 2024-05-13 | 28 | 3513.9742 | 4335.434 | 62287.8711 | 75551.7972
[17 empty] | 113 | 2024-05-14 | 29 | 3513.9742 | 4335.434 | 65801.8452 | 79887.2312
[17 empty] | 113 | 2024-05-15 | 30 | 3513.9742 | 4335.434 | 69315.8194 | 84222.6652
[17 empty] | 113 | 2024-05-16 | 31 | 3513.9742 | 4335.434 | 72829.7935 | 88558.0992
[17 empty] | 113 | 2024-05-17 | 32 | 3513.9742 | 4335.434 | 76343.7677 | 92893.5332
[17 empty] | 113 | 2024-05-18 | 33 | 0 | 0 | 76343.7677 | 92893.5332
[17 empty] | 113 | 2024-05-19 | 34 | 0 | 0 | 76343.7677 | 92893.5332
[17 empty] | 113 | 2024-05-20 | 35 | 3513.9742 | 4335.434 | 79857.7418 | 97228.9672
[17 empty] | 113 | 2024-05-21 | 36 | 3513.9742 | 4335.434 | 83371.716 | 101564.4012
[17 empty] | 113 | 2024-05-22 | 37 | 3513.9742 | 4335.434 | 86885.6901 | 105899.8352
[17 empty] | 113 | 2024-05-23 | 38 | 3513.9742 | 4335.434 | 90399.6643 | 110235.2692
[17 empty] | 113 | 2024-05-24 | 39 | 3513.9742 | 4335.434 | 93913.6384 | 114570.7032
[17 empty] | 113 | 2024-05-25 | 40 | 0 | 0 | 93913.6384 | 114570.7032
[17 empty] | 113 | 2024-05-26 | 41 | 0 | 0 | 93913.6384 | 114570.7032
[17 empty] | 113 | 2024-05-27 | 42 | 3513.9742 | 4335.434 | 97427.6126 | 118906.1372
[17 empty] | 113 | 2024-05-28 | 43 | 3513.9742 | 4335.434 | 100941.5867 | 123241.5712
[17 empty] | 113 | 2024-05-29 | 44 | 3513.9742 | 4335.434 | 104455.5609 | 127577.0052
[17 empty] | 113 | 2024-05-30 | 45 | 3513.9742 | 4335.434 | 107969.535 | 131912.4392
[17 empty] | 113 | 2024-05-31 | 46 | 3513.9742 | 4335.434 | 111483.5092 | 136247.8732
[17 empty] | 113 | 2024-06-01 | 47 | 0 | 0 | 111483.5092 | 136247.8732
[17 empty] | 113 | 2024-06-02 | 48 | 0 | 0 | 111483.5092 | 136247.8732
[17 empty] | 113 | 2024-06-03 | 49 | 3513.9742 | 4335.434 | 114997.4833 | 140583.3072
[17 empty] | 113 | 2024-06-04 | 50 | 3513.9742 | 4335.434 | 118511.4575 | 144918.7412
[17 empty] | 113 | 2024-06-05 | 51 | 3513.9742 | 4335.434 | 122025.4316 | 149254.1752
[17 empty] | 113 | 2024-06-06 | 52 | 3513.9742 | 4335.434 | 125539.4058 | 153589.6092
[17 empty] | 113 | 2024-06-07 | 53 | 3513.9742 | 4335.434 | 129053.3799 | 157925.0432
[17 empty] | 113 | 2024-06-08 | 54 | 0 | 0 | 129053.3799 | 157925.0432
[17 empty] | 113 | 2024-06-09 | 55 | 0 | 0 | 129053.3799 | 157925.0432
[17 empty] | 113 | 2024-06-10 | 56 | 3513.9742 | 4335.434 | 132567.3541 | 162260.4772
[17 empty] | 113 | 2024-06-11 | 57 | 3513.9742 | 4335.434 | 136081.3282 | 166595.9112
[17 empty] | 113 | 2024-06-12 | 58 | 3513.9742 | 4335.434 | 139595.3024 | 170931.3452
[17 empty] | 113 | 2024-06-13 | 59 | 3513.9742 | 4335.434 | 143109.2765 | 175266.7792
[17 empty] | 113 | 2024-06-14 | 60 | 3513.9742 | 4335.434 | 146623.2507 | 179602.2131
[17 empty] | 113 | 2024-06-15 | 61 | 0 | 0 | 146623.2507 | 179602.2131
[17 empty] | 113 | 2024-06-16 | 62 | 0 | 0 | 146623.2507 | 179602.2131
[17 empty] | 113 | 2024-06-17 | 63 | 3513.9742 | 4335.434 | 150137.2248 | 183937.6471
[17 empty] | 113 | 2024-06-18 | 64 | 3513.9742 | 4335.434 | 153651.199 | 188273.0811
[17 empty] | 113 | 2024-06-19 | 65 | 3513.9742 | 4335.434 | 157165.1731 | 192608.5151
[17 empty] | 113 | 2024-06-20 | 66 | 3513.9742 | 4335.434 | 160679.1473 | 196943.9491
[17 empty] | 113 | 2024-06-21 | 67 | 3513.9742 | 4335.434 | 164193.1214 | 201279.3831
[17 empty] | 113 | 2024-06-22 | 68 | 0 | 0 | 164193.1214 | 201279.3831
[17 empty] | 113 | 2024-06-23 | 69 | 0 | 0 | 164193.1214 | 201279.3831
[17 empty] | 113 | 2024-06-24 | 70 | 3513.9742 | 4335.434 | 167707.0956 | 205614.8171
[17 empty] | 113 | 2024-06-25 | 71 | 3513.9742 | 4335.434 | 171221.0697 | 209950.2511
[17 empty] | 113 | 2024-06-26 | 72 | 3513.9742 | 4335.434 | 174735.0439 | 214285.6851
[17 empty] | 113 | 2024-06-27 | 73 | 3513.9742 | 4335.434 | 178249.018 | 218621.1191
[17 empty] | 113 | 2024-06-28 | 74 | 3513.9742 | 4335.434 | 181762.9922 | 222956.5531
[17 empty] | 113 | 2024-06-29 | 75 | 0 | 0 | 181762.9922 | 222956.5531
[17 empty] | 113 | 2024-06-30 | 76 | 0 | 0 | 181762.9922 | 222956.5531
[17 empty] | 113 | 2024-07-01 | 77 | 3513.9742 | 4335.434 | 185276.9663 | 227291.9871
[17 empty] | 113 | 2024-07-02 | 78 | 3513.9742 | 4335.434 | 188790.9405 | 231627.4211
[17 empty] | 113 | 2024-07-03 | 79 | 3513.9742 | 4335.434 | 192304.9146 | 235962.8551
[17 empty] | 113 | 2024-07-04 | 80 | 3513.9742 | 4335.434 | 195818.8888 | 240298.2891
[17 empty] | 113 | 2024-07-05 | 81 | 3513.9742 | 4335.434 | 199332.8629 | 244633.7231
[17 empty] | 113 | 2024-07-06 | 82 | 0 | 0 | 199332.8629 | 244633.7231
[17 empty] | 113 | 2024-07-07 | 83 | 0 | 0 | 199332.8629 | 244633.7231
[17 empty] | 113 | 2024-07-08 | 84 | 3513.9742 | 4335.434 | 202846.8371 | 248969.1571
[17 empty] | 113 | 2024-07-09 | 85 | 3513.9742 | 4335.434 | 206360.8112 | 253304.5911
[17 empty] | 113 | 2024-07-10 | 86 | 3513.9742 | 4335.434 | 209874.7854 | 257640.0251
[17 empty] | 113 | 2024-07-11 | 87 | 3513.9742 | 4335.434 | 213388.7595 | 261975.4591
[17 empty] | 113 | 2024-07-12 | 88 | 3513.9742 | 4335.434 | 216902.7337 | 266310.8931
[17 empty] | 113 | 2024-07-13 | 89 | 0 | 0 | 216902.7337 | 266310.8931
[17 empty] | 113 | 2024-07-14 | 90 | 0 | 0 | 216902.7337 | 266310.8931
[17 empty] | 113 | 2024-07-15 | 91 | 3513.9742 | 4335.434 | 220416.7078 | 270646.3271
[17 empty] | 113 | 2024-07-16 | 92 | 3513.9742 | 4335.434 | 223930.682 | 274981.7611
[17 empty] | 113 | 2024-07-17 | 93 | 3513.9742 | 4335.434 | 227444.6561 | 279317.1951
[17 empty] | 113 | 2024-07-18 | 94 | 3513.9742 | 4335.434 | 230958.6303 | 283652.6291
[17 empty] | 113 | 2024-07-19 | 95 | 3513.9742 | 4335.434 | 234472.6044 | 287988.0631
[17 empty] | 113 | 2024-07-20 | 96 | 0 | 0 | 234472.6044 | 287988.0631
[17 empty] | 113 | 2024-07-21 | 97 | 0 | 0 | 234472.6044 | 287988.0631
[17 empty] | 113 | 2024-07-22 | 98 | 7417.9742 | 9293.514 | 241890.5786 | 297281.5771
[17 empty] | 113 | 2024-07-23 | 99 | 7417.9742 | 9293.514 | 249308.5527 | 306575.091
[17 empty] | 113 | 2024-07-24 | 100 | 7417.9742 | 9293.514 | 256726.5269 | 315868.605
[17 empty] | 113 | 2024-07-25 | 101 | 7417.9742 | 9293.514 | 264144.501 | 325162.119
[17 empty] | 113 | 2024-07-26 | 102 | 7417.9742 | 9293.514 | 271562.4752 | 334455.633
[17 empty] | 113 | 2024-07-27 | 103 | 0 | 0 | 271562.4752 | 334455.633
[17 empty] | 113 | 2024-07-28 | 104 | 0 | 0 | 271562.4752 | 334455.633
[17 empty] | 113 | 2024-07-29 | 105 | 7417.9742 | 9293.514 | 278980.4493 | 343749.147
[17 empty] | 113 | 2024-07-30 | 106 | 12396.9905 | 15467.4943 | 291377.4399 | 359216.6414
[17 empty] | 113 | 2024-07-31 | 107 | 12396.9905 | 15467.4943 | 303774.4304 | 374684.1357
[17 empty] | 113 | 2024-08-01 | 108 | 12396.9905 | 15467.4943 | 316171.4209 | 390151.63
[17 empty] | 113 | 2024-08-02 | 109 | 12396.9905 | 15467.4943 | 328568.4115 | 405619.1243
[17 empty] | 113 | 2024-08-03 | 110 | 0 | 0 | 328568.4115 | 405619.1243
[17 empty] | 113 | 2024-08-04 | 111 | 0 | 0 | 328568.4115 | 405619.1243
[17 empty] | 113 | 2024-08-05 | 112 | 12396.9905 | 15467.4943 | 340965.402 | 421086.6187
[17 empty] | 113 | 2024-08-06 | 113 | 12396.9905 | 15467.4943 | 353362.3926 | 436554.113
[17 empty] | 113 | 2024-08-07 | 114 | 12396.9905 | 15467.4943 | 365759.3831 | 452021.6073
[17 empty] | 113 | 2024-08-08 | 115 | 12396.9905 | 15467.4943 | 378156.3737 | 467489.1016
[17 empty] | 113 | 2024-08-09 | 116 | 12396.9905 | 15467.4943 | 390553.3642 | 482956.596
[17 empty] | 113 | 2024-08-10 | 117 | 0 | 0 | 390553.3642 | 482956.596
[17 empty] | 113 | 2024-08-11 | 118 | 0 | 0 | 390553.3642 | 482956.596
[17 empty] | 113 | 2024-08-12 | 119 | 9324.5428 | 11688.3836 | 399877.907 | 494644.9795
[17 empty] | 113 | 2024-08-13 | 120 | 9324.5428 | 11688.3836 | 409202.4498 | 506333.3631
[17 empty] | 113 | 2024-08-14 | 121 | 9324.5428 | 11688.3836 | 418526.9926 | 518021.7467
[17 empty] | 113 | 2024-08-15 | 122 | 9324.5428 | 11688.3836 | 427851.5353 | 529710.1303
[17 empty] | 113 | 2024-08-16 | 123 | 9324.5428 | 11688.3836 | 437176.0781 | 541398.5138
[17 empty] | 113 | 2024-08-17 | 124 | 0 | 0 | 437176.0781 | 541398.5138
[17 empty] | 113 | 2024-08-18 | 125 | 0 | 0 | 437176.0781 | 541398.5138
[17 empty] | 113 | 2024-08-19 | 126 | 9324.5428 | 11688.3836 | 446500.6209 | 553086.8974
[17 empty] | 113 | 2024-08-20 | 127 | 5420.5428 | 6730.3036 | 451921.1637 | 559817.201
[17 empty] | 113 | 2024-08-21 | 128 | 5420.5428 | 6730.3036 | 457341.7065 | 566547.5046
[17 empty] | 113 | 2024-08-22 | 129 | 5420.5428 | 6730.3036 | 462762.2492 | 573277.8082
[17 empty] | 113 | 2024-08-23 | 130 | 5420.5428 | 6730.3036 | 468182.792 | 580008.1117
[17 empty] | 113 | 2024-08-24 | 131 | 0 | 0 | 468182.792 | 580008.1117
[17 empty] | 113 | 2024-08-25 | 132 | 0 | 0 | 468182.792 | 580008.1117
[17 empty] | 113 | 2024-08-26 | 133 | 5420.5428 | 6730.3036 | 473603.3348 | 586738.4153
[17 empty] | 113 | 2024-08-27 | 134 | 5420.5428 | 6730.3036 | 479023.8776 | 593468.7189
[17 empty] | 113 | 2024-08-28 | 135 | 5420.5428 | 6730.3036 | 484444.4204 | 600199.0225
[17 empty] | 113 | 2024-08-29 | 136 | 5420.5428 | 6730.3036 | 489864.9632 | 606929.326
[17 empty] | 113 | 2024-08-30 | 137 | 5420.5428 | 6730.3036 | 495285.5059 | 613659.6296
[17 empty] | 113 | 2024-08-31 | 138 | 0 | 0 | 495285.5059 | 613659.6296
[17 empty] | 113 | 2024-09-01 | 139 | 0 | 0 | 495285.5059 | 613659.6296
[17 empty] | 113 | 2024-09-02 | 140 | 5420.5428 | 6730.3036 | 500706.0487 | 620389.9332
[17 empty] | 113 | 2024-09-03 | 141 | 5420.5428 | 6730.3036 | 506126.5915 | 627120.2368
[17 empty] | 113 | 2024-09-04 | 142 | 5420.5428 | 6730.3036 | 511547.1343 | 633850.5404
[17 empty] | 113 | 2024-09-05 | 143 | 5420.5428 | 6730.3036 | 516967.6771 | 640580.8439
[17 empty] | 113 | 2024-09-06 | 144 | 5420.5428 | 6730.3036 | 522388.2199 | 647311.1475
[17 empty] | 113 | 2024-09-07 | 145 | 0 | 0 | 522388.2199 | 647311.1475
[17 empty] | 113 | 2024-09-08 | 146 | 0 | 0 | 522388.2199 | 647311.1475
[17 empty] | 113 | 2024-09-09 | 147 | 5420.5428 | 6730.3036 | 527808.7626 | 654041.4511
[17 empty] | 113 | 2024-09-10 | 148 | 5420.5428 | 6730.3036 | 533229.3054 | 660771.7547
[17 empty] | 113 | 2024-09-11 | 149 | 5420.5428 | 6730.3036 | 538649.8482 | 667502.0582
[17 empty] | 113 | 2024-09-12 | 150 | 5420.5428 | 6730.3036 | 544070.391 | 674232.3618
[17 empty] | 113 | 2024-09-13 | 151 | 5420.5428 | 6730.3036 | 549490.9338 | 680962.6654
[17 empty] | 113 | 2024-09-14 | 152 | 0 | 0 | 549490.9338 | 680962.6654
[17 empty] | 113 | 2024-09-15 | 153 | 0 | 0 | 549490.9338 | 680962.6654
[17 empty] | 113 | 2024-09-16 | 154 | 5420.5428 | 6730.3036 | 554911.4765 | 687692.969
[17 empty] | 113 | 2024-09-17 | 155 | 5420.5428 | 6730.3036 | 560332.0193 | 694423.2726
[17 empty] | 113 | 2024-09-18 | 156 | 5420.5428 | 6730.3036 | 565752.5621 | 701153.5761
[17 empty] | 113 | 2024-09-19 | 157 | 5420.5428 | 6730.3036 | 571173.1049 | 707883.8797
[17 empty] | 113 | 2024-09-20 | 158 | 5420.5428 | 6730.3036 | 576593.6477 | 714614.1833
[17 empty] | 113 | 2024-09-21 | 159 | 0 | 0 | 576593.6477 | 714614.1833
[17 empty] | 113 | 2024-09-22 | 160 | 0 | 0 | 576593.6477 | 714614.1833
[17 empty] | 113 | 2024-09-23 | 161 | 5420.5428 | 6730.3036 | 582014.1905 | 721344.4869
[17 empty] | 113 | 2024-09-24 | 162 | 5420.5428 | 6730.3036 | 587434.7332 | 728074.7904
[17 empty] | 113 | 2024-09-25 | 163 | 5420.5428 | 6730.3036 | 592855.276 | 734805.094
[17 empty] | 113 | 2024-09-26 | 164 | 5420.5428 | 6730.3036 | 598275.8188 | 741535.3976
[17 empty] | 113 | 2024-09-27 | 165 | 5420.5428 | 6730.3036 | 603696.3616 | 748265.7012
[17 empty] | 113 | 2024-09-28 | 166 | 0 | 0 | 603696.3616 | 748265.7012
[17 empty] | 113 | 2024-09-29 | 167 | 0 | 0 | 603696.3616 | 748265.7012
[17 empty] | 113 | 2024-09-30 | 168 | 5420.5428 | 6730.3036 | 609116.9044 | 754996.0048
[17 empty] | 113 | 2024-10-01 | 169 | 5420.5428 | 6730.3036 | 614537.4472 | 761726.3083
[17 empty] | 113 | 2024-10-02 | 170 | 5420.5428 | 6730.3036 | 619957.9899 | 768456.6119
[17 empty] | 113 | 2024-10-03 | 171 | 5420.5428 | 6730.3036 | 625378.5327 | 775186.9155
[17 empty] | 113 | 2024-10-04 | 172 | 5420.5428 | 6730.3036 | 630799.0755 | 781917.2191
[17 empty] | 113 | 2024-10-05 | 173 | 0 | 0 | 630799.0755 | 781917.2191
[17 empty] | 113 | 2024-10-06 | 174 | 0 | 0 | 630799.0755 | 781917.2191
[17 empty] | 113 | 2024-10-07 | 175 | 5420.5428 | 6730.3036 | 636219.6183 | 788647.5226
[17 empty] | 113 | 2024-10-08 | 176 | 5420.5428 | 6730.3036 | 641640.1611 | 795377.8262
[17 empty] | 113 | 2024-10-09 | 177 | 5420.5428 | 6730.3036 | 647060.7038 | 802108.1298
[17 empty] | 113 | 2024-10-10 | 178 | 5420.5428 | 6730.3036 | 652481.2466 | 808838.4334
[17 empty] | 113 | 2024-10-11 | 179 | 5420.5428 | 6730.3036 | 657901.7894 | 815568.737
[17 empty] | 113 | 2024-10-12 | 180 | 0 | 0 | 657901.7894 | 815568.737
[17 empty] | 113 | 2024-10-13 | 181 | 0 | 0 | 657901.7894 | 815568.737
[17 empty] | 113 | 2024-10-14 | 182 | 5420.5428 | 6730.3036 | 663322.3322 | 822299.0405
[17 empty] | 113 | 2024-10-15 | 183 | 5420.5428 | 6730.3036 | 668742.875 | 829029.3441
[17 empty] | 113 | 2024-10-16 | 184 | 5420.5428 | 6730.3036 | 674163.4178 | 835759.6477
[17 empty] | 113 | 2024-10-17 | 185 | 5420.5428 | 6730.3036 | 679583.9605 | 842489.9513
[17 empty] | 113 | 2024-10-18 | 186 | 5420.5428 | 6730.3036 | 685004.5033 | 849220.2548
[17 empty] | 113 | 2024-10-19 | 187 | 0 | 0 | 685004.5033 | 849220.2548
[17 empty] | 113 | 2024-10-20 | 188 | 0 | 0 | 685004.5033 | 849220.2548
[17 empty] | 113 | 2024-10-21 | 189 | 5420.5428 | 6730.3036 | 690425.0461 | 855950.5584
[17 empty] | 113 | 2024-10-22 | 190 | 5420.5428 | 6730.3036 | 695845.5889 | 862680.862
[17 empty] | 113 | 2024-10-23 | 191 | 441.5264 | 556.3233 | 696287.1153 | 863237.1853
[17 empty] | 113 | 2024-10-24 | 192 | 441.5264 | 556.3233 | 696728.6417 | 863793.5085
[17 empty] | 113 | 2024-10-25 | 193 | 441.5264 | 556.3233 | 697170.1681 | 864349.8318
[17 empty] | 113 | 2024-10-26 | 194 | 0 | 0 | 697170.1681 | 864349.8318
[17 empty] | 113 | 2024-10-27 | 195 | 0 | 0 | 697170.1681 | 864349.8318
[17 empty] | 113 | 2024-10-28 | 196 | 441.5264 | 556.3233 | 697611.6944 | 864906.155
[17 empty] | 113 | 2024-10-29 | 197 | 441.5264 | 556.3233 | 698053.2208 | 865462.4783
[17 empty] | 113 | 2024-10-30 | 198 | 441.5264 | 556.3233 | 698494.7472 | 866018.8015
[17 empty] | 113 | 2024-10-31 | 199 | 441.5264 | 556.3233 | 698936.2736 | 866575.1248
[17 empty] | 113 | 2024-11-01 | 200 | 441.5264 | 556.3233 | 699377.8 | 867131.448
[17 empty] | 114 | 2024-05-30 | 1 | 255.1748 | 306.2097 | 255.1748 | 306.2097
[17 empty] | 114 | 2024-05-31 | 2 | 255.1748 | 306.2097 | 510.3495 | 612.4195
[17 empty] | 114 | 2024-06-01 | 3 | 0 | 0 | 510.3495 | 612.4195
[17 empty] | 114 | 2024-06-02 | 4 | 0 | 0 | 510.3495 | 612.4195
[17 empty] | 114 | 2024-06-03 | 5 | 255.1748 | 306.2097 | 765.5243 | 918.6292
[17 empty] | 114 | 2024-06-04 | 6 | 1689.7202 | 2042.0097 | 2455.2446 | 2960.6389
[17 empty] | 114 | 2024-06-05 | 7 | 1689.7202 | 2042.0097 | 4144.9648 | 5002.6486
[17 empty] | 114 | 2024-06-06 | 8 | 1689.7202 | 2042.0097 | 5834.685 | 7044.6584
[17 empty] | 114 | 2024-06-07 | 9 | 1689.7202 | 2042.0097 | 7524.4052 | 9086.6681
[17 empty] | 114 | 2024-06-08 | 10 | 0 | 0 | 7524.4052 | 9086.6681
[17 empty] | 114 | 2024-06-09 | 11 | 0 | 0 | 7524.4052 | 9086.6681
[17 empty] | 114 | 2024-06-10 | 12 | 1689.7202 | 2042.0097 | 9214.1255 | 11128.6778
[17 empty] | 114 | 2024-06-11 | 13 | 1689.7202 | 2042.0097 | 10903.8457 | 13170.6876
[17 empty] | 114 | 2024-06-12 | 14 | 1689.7202 | 2042.0097 | 12593.5659 | 15212.6973
[17 empty] | 114 | 2024-06-13 | 15 | 1689.7202 | 2042.0097 | 14283.2862 | 17254.707
[17 empty] | 114 | 2024-06-14 | 16 | 1689.7202 | 2042.0097 | 15973.0064 | 19296.7168
[17 empty] | 114 | 2024-06-15 | 17 | 0 | 0 | 15973.0064 | 19296.7168
[17 empty] | 114 | 2024-06-16 | 18 | 0 | 0 | 15973.0064 | 19296.7168
[17 empty] | 114 | 2024-06-17 | 19 | 1689.7202 | 2042.0097 | 17662.7266 | 21338.7265
[17 empty] | 114 | 2024-06-18 | 20 | 4036.2149 | 4670.0837 | 21698.9415 | 26008.8102
[17 empty] | 114 | 2024-06-19 | 21 | 2601.6694 | 2934.2837 | 24300.6109 | 28943.0939
[17 empty] | 114 | 2024-06-20 | 22 | 2601.6694 | 2934.2837 | 26902.2803 | 31877.3776
[17 empty] | 114 | 2024-06-21 | 23 | 2601.6694 | 2934.2837 | 29503.9497 | 34811.6613
[17 empty] | 114 | 2024-06-22 | 24 | 0 | 0 | 29503.9497 | 34811.6613
[17 empty] | 114 | 2024-06-23 | 25 | 0 | 0 | 29503.9497 | 34811.6613
[17 empty] | 114 | 2024-06-24 | 26 | 2601.6694 | 2934.2837 | 32105.6191 | 37745.945
[17 empty] | 114 | 2024-06-25 | 27 | 2601.6694 | 2934.2837 | 34707.2885 | 40680.2287
[17 empty] | 114 | 2024-06-26 | 28 | 2601.6694 | 2934.2837 | 37308.9579 | 43614.5124
[17 empty] | 114 | 2024-06-27 | 29 | 2601.6694 | 2934.2837 | 39910.6273 | 46548.7962
[17 empty] | 114 | 2024-06-28 | 30 | 2601.6694 | 2934.2837 | 42512.2967 | 49483.0799
[17 empty] | 114 | 2024-06-29 | 31 | 0 | 0 | 42512.2967 | 49483.0799
[17 empty] | 114 | 2024-06-30 | 32 | 0 | 0 | 42512.2967 | 49483.0799
[17 empty] | 114 | 2024-07-01 | 33 | 2601.6694 | 2934.2837 | 45113.9661 | 52417.3636
[17 empty] | 114 | 2024-07-02 | 34 | 2601.6694 | 2934.2837 | 47715.6355 | 55351.6473
[17 empty] | 114 | 2024-07-03 | 35 | 2601.6694 | 2934.2837 | 50317.3049 | 58285.931
[17 empty] | 114 | 2024-07-04 | 36 | 2601.6694 | 2934.2837 | 52918.9743 | 61220.2147
[17 empty] | 114 | 2024-07-05 | 37 | 2601.6694 | 2934.2837 | 55520.6437 | 64154.4984
[17 empty] | 114 | 2024-07-06 | 38 | 0 | 0 | 55520.6437 | 64154.4984
[17 empty] | 114 | 2024-07-07 | 39 | 0 | 0 | 55520.6437 | 64154.4984
[17 empty] | 114 | 2024-07-08 | 40 | 2601.6694 | 2934.2837 | 58122.313 | 67088.7821
[17 empty] | 114 | 2024-07-09 | 41 | 2601.6694 | 2934.2837 | 60723.9824 | 70023.0658
[17 empty] | 114 | 2024-07-10 | 42 | 2601.6694 | 2934.2837 | 63325.6518 | 72957.3495
[17 empty] | 114 | 2024-07-11 | 43 | 2601.6694 | 2934.2837 | 65927.3212 | 75891.6332
[17 empty] | 114 | 2024-07-12 | 44 | 2601.6694 | 2934.2837 | 68528.9906 | 78825.9169
[17 empty] | 114 | 2024-07-13 | 45 | 0 | 0 | 68528.9906 | 78825.9169
[17 empty] | 114 | 2024-07-14 | 46 | 0 | 0 | 68528.9906 | 78825.9169
[17 empty] | 114 | 2024-07-15 | 47 | 2601.6694 | 2934.2837 | 71130.66 | 81760.2007
[17 empty] | 114 | 2024-07-16 | 48 | 2601.6694 | 2934.2837 | 73732.3294 | 84694.4844
[17 empty] | 114 | 2024-07-17 | 49 | 2601.6694 | 2934.2837 | 76333.9988 | 87628.7681
[17 empty] | 114 | 2024-07-18 | 50 | 2601.6694 | 2934.2837 | 78935.6682 | 90563.0518
[17 empty] | 114 | 2024-07-19 | 51 | 2601.6694 | 2934.2837 | 81537.3376 | 93497.3355
[17 empty] | 114 | 2024-07-20 | 52 | 0 | 0 | 81537.3376 | 93497.3355
[17 empty] | 114 | 2024-07-21 | 53 | 0 | 0 | 81537.3376 | 93497.3355
[17 empty] | 114 | 2024-07-22 | 54 | 2601.6694 | 2934.2837 | 84139.007 | 96431.6192
[17 empty] | 114 | 2024-07-23 | 55 | 2601.6694 | 2934.2837 | 86740.6764 | 99365.9029
[17 empty] | 114 | 2024-07-24 | 56 | 2601.6694 | 2934.2837 | 89342.3458 | 102300.1866
[17 empty] | 114 | 2024-07-25 | 57 | 2601.6694 | 2934.2837 | 91944.0152 | 105234.4703
[17 empty] | 114 | 2024-07-26 | 58 | 2601.6694 | 2934.2837 | 94545.6846 | 108168.754
[17 empty] | 114 | 2024-07-27 | 59 | 0 | 0 | 94545.6846 | 108168.754
[17 empty] | 114 | 2024-07-28 | 60 | 0 | 0 | 94545.6846 | 108168.754
[17 empty] | 114 | 2024-07-29 | 61 | 2601.6694 | 2934.2837 | 97147.354 | 111103.0377
[17 empty] | 114 | 2024-07-30 | 62 | 2601.6694 | 2934.2837 | 99749.0234 | 114037.3214
[17 empty] | 114 | 2024-07-31 | 63 | 2601.6694 | 2934.2837 | 102350.6928 | 116971.6051
[17 empty] | 114 | 2024-08-01 | 64 | 2601.6694 | 2934.2837 | 104952.3622 | 119905.8889
[17 empty] | 114 | 2024-08-02 | 65 | 2601.6694 | 2934.2837 | 107554.0316 | 122840.1726
[17 empty] | 114 | 2024-08-03 | 66 | 0 | 0 | 107554.0316 | 122840.1726
[17 empty] | 114 | 2024-08-04 | 67 | 0 | 0 | 107554.0316 | 122840.1726
[17 empty] | 114 | 2024-08-05 | 68 | 2601.6694 | 2934.2837 | 110155.701 | 125774.4563
[17 empty] | 114 | 2024-08-06 | 69 | 2601.6694 | 2934.2837 | 112757.3704 | 128708.74
[17 empty] | 114 | 2024-08-07 | 70 | 2601.6694 | 2934.2837 | 115359.0398 | 131643.0237
[17 empty] | 114 | 2024-08-08 | 71 | 2601.6694 | 2934.2837 | 117960.7092 | 134577.3074
[17 empty] | 114 | 2024-08-09 | 72 | 2601.6694 | 2934.2837 | 120562.3786 | 137511.5911
[17 empty] | 114 | 2024-08-10 | 73 | 0 | 0 | 120562.3786 | 137511.5911
[17 empty] | 114 | 2024-08-11 | 74 | 0 | 0 | 120562.3786 | 137511.5911
[17 empty] | 114 | 2024-08-12 | 75 | 2601.6694 | 2934.2837 | 123164.048 | 140445.8748
[17 empty] | 114 | 2024-08-13 | 76 | 2601.6694 | 2934.2837 | 125765.7174 | 143380.1585
[17 empty] | 114 | 2024-08-14 | 77 | 2601.6694 | 2934.2837 | 128367.3868 | 146314.4422
[17 empty] | 114 | 2024-08-15 | 78 | 2601.6694 | 2934.2837 | 130969.0562 | 149248.7259
[17 empty] | 114 | 2024-08-16 | 79 | 2601.6694 | 2934.2837 | 133570.7256 | 152183.0096
[17 empty] | 114 | 2024-08-17 | 80 | 0 | 0 | 133570.7256 | 152183.0096
[17 empty] | 114 | 2024-08-18 | 81 | 0 | 0 | 133570.7256 | 152183.0096
[17 empty] | 114 | 2024-08-19 | 82 | 2601.6694 | 2934.2837 | 136172.395 | 155117.2934
[17 empty] | 114 | 2024-08-20 | 83 | 2601.6694 | 2934.2837 | 138774.0644 | 158051.5771
[17 empty] | 114 | 2024-08-21 | 84 | 2601.6694 | 2934.2837 | 141375.7338 | 160985.8608
[17 empty] | 114 | 2024-08-22 | 85 | 2601.6694 | 2934.2837 | 143977.4032 | 163920.1445
[17 empty] | 114 | 2024-08-23 | 86 | 2601.6694 | 2934.2837 | 146579.0726 | 166854.4282
[17 empty] | 114 | 2024-08-24 | 87 | 0 | 0 | 146579.0726 | 166854.4282
[17 empty] | 114 | 2024-08-25 | 88 | 0 | 0 | 146579.0726 | 166854.4282
[17 empty] | 114 | 2024-08-26 | 89 | 2601.6694 | 2934.2837 | 149180.742 | 169788.7119
[17 empty] | 114 | 2024-08-27 | 90 | 2601.6694 | 2934.2837 | 151782.4114 | 172722.9956
[17 empty] | 114 | 2024-08-28 | 91 | 2601.6694 | 2934.2837 | 154384.0808 | 175657.2793
[17 empty] | 114 | 2024-08-29 | 92 | 2601.6694 | 2934.2837 | 156985.7502 | 178591.563
[17 empty] | 114 | 2024-08-30 | 93 | 2601.6694 | 2934.2837 | 159587.4196 | 181525.8467
[17 empty] | 114 | 2024-08-31 | 94 | 0 | 0 | 159587.4196 | 181525.8467
[17 empty] | 114 | 2024-09-01 | 95 | 0 | 0 | 159587.4196 | 181525.8467
[17 empty] | 114 | 2024-09-02 | 96 | 2601.6694 | 2934.2837 | 162189.089 | 184460.1304
[17 empty] | 114 | 2024-09-03 | 97 | 2601.6694 | 2934.2837 | 164790.7584 | 187394.4141
[17 empty] | 114 | 2024-09-04 | 98 | 2601.6694 | 2934.2837 | 167392.4278 | 190328.6979
[17 empty] | 114 | 2024-09-05 | 99 | 2601.6694 | 2934.2837 | 169994.0972 | 193262.9816
[17 empty] | 114 | 2024-09-06 | 100 | 2601.6694 | 2934.2837 | 172595.7666 | 196197.2653
[17 empty] | 114 | 2024-09-07 | 101 | 0 | 0 | 172595.7666 | 196197.2653
[17 empty] | 114 | 2024-09-08 | 102 | 0 | 0 | 172595.7666 | 196197.2653
[17 empty] | 114 | 2024-09-09 | 103 | 2601.6694 | 2934.2837 | 175197.436 | 199131.549
[17 empty] | 114 | 2024-09-10 | 104 | 2601.6694 | 2934.2837 | 177799.1054 | 202065.8327
[17 empty] | 114 | 2024-09-11 | 105 | 2601.6694 | 2934.2837 | 180400.7748 | 205000.1164
[17 empty] | 114 | 2024-09-12 | 106 | 2601.6694 | 2934.2837 | 183002.4442 | 207934.4001
[17 empty] | 114 | 2024-09-13 | 107 | 2601.6694 | 2934.2837 | 185604.1136 | 210868.6838
[17 empty] | 114 | 2024-09-14 | 108 | 0 | 0 | 185604.1136 | 210868.6838
[17 empty] | 114 | 2024-09-15 | 109 | 0 | 0 | 185604.1136 | 210868.6838
[17 empty] | 114 | 2024-09-16 | 110 | 2601.6694 | 2934.2837 | 188205.783 | 213802.9675
[17 empty] | 114 | 2024-09-17 | 111 | 2601.6694 | 2934.2837 | 190807.4524 | 216737.2512
[17 empty] | 114 | 2024-09-18 | 112 | 2601.6694 | 2934.2837 | 193409.1218 | 219671.5349
[17 empty] | 114 | 2024-09-19 | 113 | 2601.6694 | 2934.2837 | 196010.7912 | 222605.8186
[17 empty] | 114 | 2024-09-20 | 114 | 2601.6694 | 2934.2837 | 198612.4606 | 225540.1024
[17 empty] | 114 | 2024-09-21 | 115 | 0 | 0 | 198612.4606 | 225540.1024
[17 empty] | 114 | 2024-09-22 | 116 | 0 | 0 | 198612.4606 | 225540.1024
[17 empty] | 114 | 2024-09-23 | 117 | 2601.6694 | 2934.2837 | 201214.13 | 228474.3861
[17 empty] | 114 | 2024-09-24 | 118 | 2601.6694 | 2934.2837 | 203815.7994 | 231408.6698
[17 empty] | 114 | 2024-09-25 | 119 | 2601.6694 | 2934.2837 | 206417.4688 | 234342.9535
[17 empty] | 114 | 2024-09-26 | 120 | 2601.6694 | 2934.2837 | 209019.1382 | 237277.2372
[17 empty] | 114 | 2024-09-27 | 121 | 2601.6694 | 2934.2837 | 211620.8076 | 240211.5209
[17 empty] | 114 | 2024-09-28 | 122 | 0 | 0 | 211620.8076 | 240211.5209
[17 empty] | 114 | 2024-09-29 | 123 | 0 | 0 | 211620.8076 | 240211.5209
[17 empty] | 114 | 2024-09-30 | 124 | 2601.6694 | 2934.2837 | 214222.477 | 243145.8046
[17 empty] | 114 | 2024-10-01 | 125 | 2601.6694 | 2934.2837 | 216824.1464 | 246080.0883
[17 empty] | 114 | 2024-10-02 | 126 | 2601.6694 | 2934.2837 | 219425.8158 | 249014.372
[17 empty] | 114 | 2024-10-03 | 127 | 2601.6694 | 2934.2837 | 222027.4851 | 251948.6557
[17 empty] | 114 | 2024-10-04 | 128 | 5633.787 | 6360.5766 | 227661.2722 | 258309.2324
[17 empty] | 114 | 2024-10-05 | 129 | 0 | 0 | 227661.2722 | 258309.2324
[17 empty] | 114 | 2024-10-06 | 130 | 0 | 0 | 227661.2722 | 258309.2324
[17 empty] | 114 | 2024-10-07 | 131 | 5633.787 | 6360.5766 | 233295.0592 | 264669.809
[17 empty] | 114 | 2024-10-08 | 132 | 5633.787 | 6360.5766 | 238928.8463 | 271030.3857
[17 empty] | 114 | 2024-10-09 | 133 | 5633.787 | 6360.5766 | 244562.6333 | 277390.9623
[17 empty] | 114 | 2024-10-10 | 134 | 5633.787 | 6360.5766 | 250196.4204 | 283751.539
[17 empty] | 114 | 2024-10-11 | 135 | 5633.787 | 6360.5766 | 255830.2074 | 290112.1156
[17 empty] | 114 | 2024-10-12 | 136 | 0 | 0 | 255830.2074 | 290112.1156
[17 empty] | 114 | 2024-10-13 | 137 | 0 | 0 | 255830.2074 | 290112.1156
[17 empty] | 114 | 2024-10-14 | 138 | 7561.4509 | 8635.22 | 263391.6583 | 298747.3356
[17 empty] | 114 | 2024-10-15 | 139 | 7561.4509 | 8635.22 | 270953.1092 | 307382.5556
[17 empty] | 114 | 2024-10-16 | 140 | 7561.4509 | 8635.22 | 278514.5602 | 316017.7757
[17 empty] | 114 | 2024-10-17 | 141 | 7561.4509 | 8635.22 | 286076.0111 | 324652.9957
[17 empty] | 114 | 2024-10-18 | 142 | 7561.4509 | 8635.22 | 293637.462 | 333288.2157
[17 empty] | 114 | 2024-10-19 | 143 | 0 | 0 | 293637.462 | 333288.2157
[17 empty] | 114 | 2024-10-20 | 144 | 0 | 0 | 293637.462 | 333288.2157
[17 empty] | 114 | 2024-10-21 | 145 | 7561.4509 | 8635.22 | 301198.9129 | 341923.4357
[17 empty] | 114 | 2024-10-22 | 146 | 7561.4509 | 8635.22 | 308760.3638 | 350558.6557
[17 empty] | 114 | 2024-10-23 | 147 | 7561.4509 | 8635.22 | 316321.8147 | 359193.8757
[17 empty] | 114 | 2024-10-24 | 148 | 7561.4509 | 8635.22 | 323883.2656 | 367829.0957
[17 empty] | 114 | 2024-10-25 | 149 | 5214.9563 | 6007.146 | 329098.2219 | 373836.2418
[17 empty] | 114 | 2024-10-26 | 150 | 0 | 0 | 329098.2219 | 373836.2418
[17 empty] | 114 | 2024-10-27 | 151 | 0 | 0 | 329098.2219 | 373836.2418
[17 empty] | 114 | 2024-10-28 | 152 | 5214.9563 | 6007.146 | 334313.1782 | 379843.3878
[17 empty] | 114 | 2024-10-29 | 153 | 5214.9563 | 6007.146 | 339528.1345 | 385850.5338
[17 empty] | 114 | 2024-10-30 | 154 | 5214.9563 | 6007.146 | 344743.0908 | 391857.6799
[17 empty] | 114 | 2024-10-31 | 155 | 5214.9563 | 6007.146 | 349958.0471 | 397864.8259
[17 empty] | 114 | 2024-11-01 | 156 | 5214.9563 | 6007.146 | 355173.0033 | 403871.9719
[17 empty] | 114 | 2024-11-02 | 157 | 0 | 0 | 355173.0033 | 403871.9719
[17 empty] | 114 | 2024-11-03 | 158 | 0 | 0 | 355173.0033 | 403871.9719
[17 empty] | 114 | 2024-11-04 | 159 | 5214.9563 | 6007.146 | 360387.9596 | 409879.1179
[17 empty] | 114 | 2024-11-05 | 160 | 5214.9563 | 6007.146 | 365602.9159 | 415886.264
[17 empty] | 114 | 2024-11-06 | 161 | 5214.9563 | 6007.146 | 370817.8722 | 421893.41
[17 empty] | 114 | 2024-11-07 | 162 | 5214.9563 | 6007.146 | 376032.8285 | 427900.556
[17 empty] | 114 | 2024-11-08 | 163 | 5214.9563 | 6007.146 | 381247.7848 | 433907.7021
[17 empty] | 114 | 2024-11-09 | 164 | 0 | 0 | 381247.7848 | 433907.7021
[17 empty] | 114 | 2024-11-10 | 165 | 0 | 0 | 381247.7848 | 433907.7021
[17 empty] | 114 | 2024-11-11 | 166 | 5214.9563 | 6007.146 | 386462.7411 | 439914.8481
[17 empty] | 114 | 2024-11-12 | 167 | 5214.9563 | 6007.146 | 391677.6974 | 445921.9941
[17 empty] | 114 | 2024-11-13 | 168 | 5214.9563 | 6007.146 | 396892.6536 | 451929.1402
[17 empty] | 114 | 2024-11-14 | 169 | 5214.9563 | 6007.146 | 402107.6099 | 457936.2862
[17 empty] | 114 | 2024-11-15 | 170 | 5214.9563 | 6007.146 | 407322.5662 | 463943.4322
[17 empty] | 114 | 2024-11-16 | 171 | 0 | 0 | 407322.5662 | 463943.4322
[17 empty] | 114 | 2024-11-17 | 172 | 0 | 0 | 407322.5662 | 463943.4322
[17 empty] | 114 | 2024-11-18 | 173 | 5214.9563 | 6007.146 | 412537.5225 | 469950.5783
[17 empty] | 114 | 2024-11-19 | 174 | 5214.9563 | 6007.146 | 417752.4788 | 475957.7243
[17 empty] | 114 | 2024-11-20 | 175 | 5214.9563 | 6007.146 | 422967.4351 | 481964.8703
[17 empty] | 114 | 2024-11-21 | 176 | 2182.8386 | 2580.8531 | 425150.2737 | 484545.7234
[17 empty] | 114 | 2024-11-22 | 177 | 2182.8386 | 2580.8531 | 427333.1124 | 487126.5765
[17 empty] | 114 | 2024-11-23 | 178 | 0 | 0 | 427333.1124 | 487126.5765
[17 empty] | 114 | 2024-11-24 | 179 | 0 | 0 | 427333.1124 | 487126.5765
[17 empty] | 114 | 2024-11-25 | 180 | 2182.8386 | 2580.8531 | 429515.951 | 489707.4296
[17 empty] | 114 | 2024-11-26 | 181 | 2182.8386 | 2580.8531 | 431698.7896 | 492288.2827
[17 empty] | 114 | 2024-11-27 | 182 | 2182.8386 | 2580.8531 | 433881.6283 | 494869.1358
[17 empty] | 114 | 2024-11-28 | 183 | 2182.8386 | 2580.8531 | 436064.4669 | 497449.9889
[17 empty] | 114 | 2024-11-29 | 184 | 2182.8386 | 2580.8531 | 438247.3056 | 500030.842
[17 empty] | 114 | 2024-11-30 | 185 | 0 | 0 | 438247.3056 | 500030.842
[17 empty] | 114 | 2024-12-01 | 186 | 0 | 0 | 438247.3056 | 500030.842
[17 empty] | 114 | 2024-12-02 | 187 | 2182.8386 | 2580.8531 | 440430.1442 | 502611.6951
[17 empty] | 114 | 2024-12-03 | 188 | 2182.8386 | 2580.8531 | 442612.9828 | 505192.5482
[17 empty] | 114 | 2024-12-04 | 189 | 2182.8386 | 2580.8531 | 444795.8215 | 507773.4012
[17 empty] | 114 | 2024-12-05 | 190 | 2182.8386 | 2580.8531 | 446978.6601 | 510354.2543
[17 empty] | 114 | 2024-12-06 | 191 | 2182.8386 | 2580.8531 | 449161.4988 | 512935.1074
[17 empty] | 114 | 2024-12-07 | 192 | 0 | 0 | 449161.4988 | 512935.1074
[17 empty] | 114 | 2024-12-08 | 193 | 0 | 0 | 449161.4988 | 512935.1074
[17 empty] | 114 | 2024-12-09 | 194 | 2182.8386 | 2580.8531 | 451344.3374 | 515515.9605
[17 empty] | 114 | 2024-12-10 | 195 | 2182.8386 | 2580.8531 | 453527.176 | 518096.8136
[17 empty] | 114 | 2024-12-11 | 196 | 2182.8386 | 2580.8531 | 455710.0147 | 520677.6667
[17 empty] | 114 | 2024-12-12 | 197 | 2182.8386 | 2580.8531 | 457892.8533 | 523258.5198
[17 empty] | 114 | 2024-12-13 | 198 | 2182.8386 | 2580.8531 | 460075.692 | 525839.3729
[17 empty] | 114 | 2024-12-14 | 199 | 0 | 0 | 460075.692 | 525839.3729
[17 empty] | 114 | 2024-12-15 | 200 | 0 | 0 | 460075.692 | 525839.3729
[17 empty] | 114 | 2024-12-16 | 201 | 2182.8386 | 2580.8531 | 462258.5306 | 528420.226
[17 empty] | 114 | 2024-12-17 | 202 | 2182.8386 | 2580.8531 | 464441.3692 | 531001.0791
[17 empty] | 114 | 2024-12-18 | 203 | 2182.8386 | 2580.8531 | 466624.2079 | 533581.9322
[17 empty] | 114 | 2024-12-19 | 204 | 2182.8386 | 2580.8531 | 468807.0465 | 536162.7852
[17 empty] | 114 | 2024-12-20 | 205 | 2182.8386 | 2580.8531 | 470989.8852 | 538743.6383
[17 empty] | 114 | 2024-12-21 | 206 | 0 | 0 | 470989.8852 | 538743.6383
[17 empty] | 114 | 2024-12-22 | 207 | 0 | 0 | 470989.8852 | 538743.6383
[17 empty] | 114 | 2024-12-23 | 208 | 2182.8386 | 2580.8531 | 473172.7238 | 541324.4914
[17 empty] | 114 | 2024-12-24 | 209 | 2182.8386 | 2580.8531 | 475355.5624 | 543905.3445
[17 empty] | 114 | 2024-12-25 | 210 | 2182.8386 | 2580.8531 | 477538.4011 | 546486.1976
[17 empty] | 114 | 2024-12-26 | 211 | 2182.8386 | 2580.8531 | 479721.2397 | 549067.0507
[17 empty] | 114 | 2024-12-27 | 212 | 2182.8386 | 2580.8531 | 481904.0784 | 551647.9038
[17 empty] | 114 | 2024-12-28 | 213 | 0 | 0 | 481904.0784 | 551647.9038
[17 empty] | 114 | 2024-12-29 | 214 | 0 | 0 | 481904.0784 | 551647.9038
[17 empty] | 114 | 2024-12-30 | 215 | 2182.8386 | 2580.8531 | 484086.917 | 554228.7569
[17 empty] | 114 | 2024-12-31 | 216 | 2182.8386 | 2580.8531 | 486269.7557 | 556809.61
[17 empty] | 114 | 2025-01-01 | 217 | 2182.8386 | 2580.8531 | 488452.5943 | 559390.4631
[17 empty] | 114 | 2025-01-02 | 218 | 2182.8386 | 2580.8531 | 490635.4329 | 561971.3162
[17 empty] | 114 | 2025-01-03 | 219 | 2182.8386 | 2580.8531 | 492818.2716 | 564552.1692
[17 empty] | 114 | 2025-01-04 | 220 | 0 | 0 | 492818.2716 | 564552.1692
[17 empty] | 114 | 2025-01-05 | 221 | 0 | 0 | 492818.2716 | 564552.1692
[17 empty] | 114 | 2025-01-06 | 222 | 2182.8386 | 2580.8531 | 495001.1102 | 567133.0223
[17 empty] | 114 | 2025-01-07 | 223 | 2182.8386 | 2580.8531 | 497183.9489 | 569713.8754
[17 empty] | 114 | 2025-01-08 | 224 | 2182.8386 | 2580.8531 | 499366.7875 | 572294.7285
[17 empty] | 114 | 2025-01-09 | 225 | 2182.8386 | 2580.8531 | 501549.6261 | 574875.5816
[17 empty] | 114 | 2025-01-10 | 226 | 2182.8386 | 2580.8531 | 503732.4648 | 577456.4347
[17 empty] | 114 | 2025-01-11 | 227 | 0 | 0 | 503732.4648 | 577456.4347
[17 empty] | 114 | 2025-01-12 | 228 | 0 | 0 | 503732.4648 | 577456.4347
[17 empty] | 114 | 2025-01-13 | 229 | 2182.8386 | 2580.8531 | 505915.3034 | 580037.2878
[17 empty] | 114 | 2025-01-14 | 230 | 2182.8386 | 2580.8531 | 508098.1421 | 582618.1409
[17 empty] | 114 | 2025-01-15 | 231 | 2182.8386 | 2580.8531 | 510280.9807 | 585198.994
[17 empty] | 114 | 2025-01-16 | 232 | 2182.8386 | 2580.8531 | 512463.8193 | 587779.8471
[17 empty] | 114 | 2025-01-17 | 233 | 2182.8386 | 2580.8531 | 514646.658 | 590360.7002
[17 empty] | 114 | 2025-01-18 | 234 | 0 | 0 | 514646.658 | 590360.7002
[17 empty] | 114 | 2025-01-19 | 235 | 0 | 0 | 514646.658 | 590360.7002
[17 empty] | 114 | 2025-01-20 | 236 | 2182.8386 | 2580.8531 | 516829.4966 | 592941.5533
[17 empty] | 114 | 2025-01-21 | 237 | 2182.8386 | 2580.8531 | 519012.3353 | 595522.4063
[17 empty] | 114 | 2025-01-22 | 238 | 2182.8386 | 2580.8531 | 521195.1739 | 598103.2594
[17 empty] | 114 | 2025-01-23 | 239 | 2182.8386 | 2580.8531 | 523378.0125 | 600684.1125
[17 empty] | 114 | 2025-01-24 | 240 | 2182.8386 | 2580.8531 | 525560.8512 | 603264.9656
[17 empty] | 114 | 2025-01-25 | 241 | 0 | 0 | 525560.8512 | 603264.9656
[17 empty] | 114 | 2025-01-26 | 242 | 0 | 0 | 525560.8512 | 603264.9656
[17 empty] | 114 | 2025-01-27 | 243 | 2182.8386 | 2580.8531 | 527743.6898 | 605845.8187
[17 empty] | 114 | 2025-01-28 | 244 | 2182.8386 | 2580.8531 | 529926.5285 | 608426.6718
[17 empty] | 114 | 2025-01-29 | 245 | 2182.8386 | 2580.8531 | 532109.3671 | 611007.5249
[17 empty] | 114 | 2025-01-30 | 246 | 2182.8386 | 2580.8531 | 534292.2057 | 613588.378
[17 empty] | 114 | 2025-01-31 | 247 | 2182.8386 | 2580.8531 | 536475.0444 | 616169.2311
[17 empty] | 114 | 2025-02-01 | 248 | 0 | 0 | 536475.0444 | 616169.2311
[17 empty] | 114 | 2025-02-02 | 249 | 0 | 0 | 536475.0444 | 616169.2311
[17 empty] | 114 | 2025-02-03 | 250 | 2182.8386 | 2580.8531 | 538657.883 | 618750.0842
[17 empty] | 114 | 2025-02-04 | 251 | 2182.8386 | 2580.8531 | 540840.7217 | 621330.9373
[17 empty] | 114 | 2025-02-05 | 252 | 2182.8386 | 2580.8531 | 543023.5603 | 623911.7903
[17 empty] | 114 | 2025-02-06 | 253 | 2182.8386 | 2580.8531 | 545206.3989 | 626492.6434
[17 empty] | 114 | 2025-02-07 | 254 | 2182.8386 | 2580.8531 | 547389.2376 | 629073.4965
[17 empty] | 114 | 2025-02-08 | 255 | 0 | 0 | 547389.2376 | 629073.4965
[17 empty] | 114 | 2025-02-09 | 256 | 0 | 0 | 547389.2376 | 629073.4965
[17 empty] | 114 | 2025-02-10 | 257 | 2182.8386 | 2580.8531 | 549572.0762 | 631654.3496
[17 empty] | 114 | 2025-02-11 | 258 | 2182.8386 | 2580.8531 | 551754.9149 | 634235.2027
[17 empty] | 114 | 2025-02-12 | 259 | 2182.8386 | 2580.8531 | 553937.7535 | 636816.0558
[17 empty] | 114 | 2025-02-13 | 260 | 2182.8386 | 2580.8531 | 556120.5921 | 639396.9089
[17 empty] | 114 | 2025-02-14 | 261 | 2182.8386 | 2580.8531 | 558303.4308 | 641977.762
[17 empty] | 114 | 2025-02-15 | 262 | 0 | 0 | 558303.4308 | 641977.762
[17 empty] | 114 | 2025-02-16 | 263 | 0 | 0 | 558303.4308 | 641977.762
[17 empty] | 114 | 2025-02-17 | 264 | 2182.8386 | 2580.8531 | 560486.2694 | 644558.6151
[17 empty] | 114 | 2025-02-18 | 265 | 2182.8386 | 2580.8531 | 562669.1081 | 647139.4682
[17 empty] | 114 | 2025-02-19 | 266 | 2182.8386 | 2580.8531 | 564851.9467 | 649720.3213
[17 empty] | 114 | 2025-02-20 | 267 | 2182.8386 | 2580.8531 | 567034.7853 | 652301.1743
[17 empty] | 114 | 2025-02-21 | 268 | 2182.8386 | 2580.8531 | 569217.624 | 654882.0274
[17 empty] | 114 | 2025-02-22 | 269 | 0 | 0 | 569217.624 | 654882.0274
[17 empty] | 114 | 2025-02-23 | 270 | 0 | 0 | 569217.624 | 654882.0274
[17 empty] | 114 | 2025-02-24 | 271 | 2182.8386 | 2580.8531 | 571400.4626 | 657462.8805
[17 empty] | 114 | 2025-02-25 | 272 | 2182.8386 | 2580.8531 | 573583.3013 | 660043.7336
[17 empty] | 114 | 2025-02-26 | 273 | 2182.8386 | 2580.8531 | 575766.1399 | 662624.5867
[17 empty] | 114 | 2025-02-27 | 274 | 2182.8386 | 2580.8531 | 577948.9785 | 665205.4398
[17 empty] | 114 | 2025-02-28 | 275 | 2182.8386 | 2580.8531 | 580131.8172 | 667786.2929
[17 empty] | 114 | 2025-03-01 | 276 | 0 | 0 | 580131.8172 | 667786.2929
[17 empty] | 114 | 2025-03-02 | 277 | 0 | 0 | 580131.8172 | 667786.2929
[17 empty] | 114 | 2025-03-03 | 278 | 2182.8386 | 2580.8531 | 582314.6558 | 670367.146
[17 empty] | 114 | 2025-03-04 | 279 | 2182.8386 | 2580.8531 | 584497.4945 | 672947.9991
[17 empty] | 114 | 2025-03-05 | 280 | 2182.8386 | 2580.8531 | 586680.3331 | 675528.8522
[17 empty] | 114 | 2025-03-06 | 281 | 2182.8386 | 2580.8531 | 588863.1717 | 678109.7053
[17 empty] | 114 | 2025-03-07 | 282 | 2182.8386 | 2580.8531 | 591046.0104 | 680690.5583
[17 empty] | 114 | 2025-03-08 | 283 | 0 | 0 | 591046.0104 | 680690.5583
[17 empty] | 114 | 2025-03-09 | 284 | 0 | 0 | 591046.0104 | 680690.5583
[17 empty] | 114 | 2025-03-10 | 285 | 2182.8386 | 2580.8531 | 593228.849 | 683271.4114
[17 empty] | 114 | 2025-03-11 | 286 | 2182.8386 | 2580.8531 | 595411.6877 | 685852.2645
[17 empty] | 114 | 2025-03-12 | 287 | 2182.8386 | 2580.8531 | 597594.5263 | 688433.1176
[17 empty] | 114 | 2025-03-13 | 288 | 2182.8386 | 2580.8531 | 599777.3649 | 691013.9707
[17 empty] | 114 | 2025-03-14 | 289 | 2182.8386 | 2580.8531 | 601960.2036 | 693594.8238
[17 empty] | 114 | 2025-03-15 | 290 | 0 | 0 | 601960.2036 | 693594.8238
[17 empty] | 114 | 2025-03-16 | 291 | 0 | 0 | 601960.2036 | 693594.8238
[17 empty] | 114 | 2025-03-17 | 292 | 2182.8386 | 2580.8531 | 604143.0422 | 696175.6769
[17 empty] | 114 | 2025-03-18 | 293 | 2182.8386 | 2580.8531 | 606325.8809 | 698756.53
[17 empty] | 114 | 2025-03-19 | 294 | 2182.8386 | 2580.8531 | 608508.7195 | 701337.3831
[17 empty] | 114 | 2025-03-20 | 295 | 2182.8386 | 2580.8531 | 610691.5581 | 703918.2362
[17 empty] | 114 | 2025-03-21 | 296 | 2182.8386 | 2580.8531 | 612874.3968 | 706499.0893
[17 empty] | 114 | 2025-03-22 | 297 | 0 | 0 | 612874.3968 | 706499.0893
[17 empty] | 114 | 2025-03-23 | 298 | 0 | 0 | 612874.3968 | 706499.0893
[17 empty] | 114 | 2025-03-24 | 299 | 2182.8386 | 2580.8531 | 615057.2354 | 709079.9423
[17 empty] | 114 | 2025-03-25 | 300 | 2182.8386 | 2580.8531 | 617240.0741 | 711660.7954
[17 empty] | 114 | 2025-03-26 | 301 | 2182.8386 | 2580.8531 | 619422.9127 | 714241.6485
[17 empty] | 114 | 2025-03-27 | 302 | 2182.8386 | 2580.8531 | 621605.7514 | 716822.5016
[17 empty] | 114 | 2025-03-28 | 303 | 255.1748 | 306.2097 | 621860.9261 | 717128.7114
[17 empty] | 114 | 2025-03-29 | 304 | 0 | 0 | 621860.9261 | 717128.7114
[17 empty] | 114 | 2025-03-30 | 305 | 0 | 0 | 621860.9261 | 717128.7114
[17 empty] | 114 | 2025-03-31 | 306 | 255.1748 | 306.2097 | 622116.1009 | 717434.9211
[17 empty] | 114 | 2025-04-01 | 307 | 255.1748 | 306.2097 | 622371.2757 | 717741.1308
[17 empty] | 114 | 2025-04-02 | 308 | 255.1748 | 306.2097 | 622626.4505 | 718047.3405
[17 empty] | 114 | 2025-04-03 | 309 | 255.1748 | 306.2097 | 622881.6252 | 718353.5503
[17 empty] | 114 | 2025-04-04 | 310 | 255.1748 | 306.2097 | 623136.8 | 718659.76
[17 empty] | 114 | 2025-04-05 | 311 | 0 | 0 | 623136.8 | 718659.76
[17 empty] | 114 | 2025-04-06 | 312 | 0 | 0 | 623136.8 | 718659.76
[17 empty] | 115 | 2024-06-05 | 1 | 349.103 | 429.3967 | 349.103 | 429.3967
[17 empty] | 115 | 2024-06-06 | 2 | 349.103 | 429.3967 | 698.206 | 858.7933
[17 empty] | 115 | 2024-06-07 | 3 | 349.103 | 429.3967 | 1047.3089 | 1288.19
[17 empty] | 115 | 2024-06-08 | 4 | 0 | 0 | 1047.3089 | 1288.19
[17 empty] | 115 | 2024-06-09 | 5 | 0 | 0 | 1047.3089 | 1288.19
[17 empty] | 115 | 2024-06-10 | 6 | 3438.9666 | 4322.6248 | 4486.2756 | 5610.8148
[17 empty] | 115 | 2024-06-11 | 7 | 3438.9666 | 4322.6248 | 7925.2422 | 9933.4397
[17 empty] | 115 | 2024-06-12 | 8 | 3438.9666 | 4322.6248 | 11364.2088 | 14256.0645
[17 empty] | 115 | 2024-06-13 | 9 | 3438.9666 | 4322.6248 | 14803.1754 | 18578.6894
[17 empty] | 115 | 2024-06-14 | 10 | 3438.9666 | 4322.6248 | 18242.142 | 22901.3142
[17 empty] | 115 | 2024-06-15 | 11 | 0 | 0 | 18242.142 | 22901.3142
[17 empty] | 115 | 2024-06-16 | 12 | 0 | 0 | 18242.142 | 22901.3142
[17 empty] | 115 | 2024-06-17 | 13 | 3438.9666 | 4322.6248 | 21681.1086 | 27223.9391
[17 empty] | 115 | 2024-06-18 | 14 | 3438.9666 | 4322.6248 | 25120.0753 | 31546.5639
[17 empty] | 115 | 2024-06-19 | 15 | 3438.9666 | 4322.6248 | 28559.0419 | 35869.1888
[17 empty] | 115 | 2024-06-20 | 16 | 3438.9666 | 4322.6248 | 31998.0085 | 40191.8136
[17 empty] | 115 | 2024-06-21 | 17 | 3438.9666 | 4322.6248 | 35436.9751 | 44514.4385
[17 empty] | 115 | 2024-06-22 | 18 | 0 | 0 | 35436.9751 | 44514.4385
[17 empty] | 115 | 2024-06-23 | 19 | 0 | 0 | 35436.9751 | 44514.4385
[17 empty] | 115 | 2024-06-24 | 20 | 3438.9666 | 4322.6248 | 38875.9417 | 48837.0633
[17 empty] | 115 | 2024-06-25 | 21 | 3438.9666 | 4322.6248 | 42314.9083 | 53159.6882
[17 empty] | 115 | 2024-06-26 | 22 | 3438.9666 | 4322.6248 | 45753.875 | 57482.313
[17 empty] | 115 | 2024-06-27 | 23 | 3438.9666 | 4322.6248 | 49192.8416 | 61804.9379
[17 empty] | 115 | 2024-06-28 | 24 | 3438.9666 | 4322.6248 | 52631.8082 | 66127.5627
[17 empty] | 115 | 2024-06-29 | 25 | 0 | 0 | 52631.8082 | 66127.5627
[17 empty] | 115 | 2024-06-30 | 26 | 0 | 0 | 52631.8082 | 66127.5627
[17 empty] | 115 | 2024-07-01 | 27 | 3438.9666 | 4322.6248 | 56070.7748 | 70450.1876
[17 empty] | 115 | 2024-07-02 | 28 | 3438.9666 | 4322.6248 | 59509.7414 | 74772.8124
[17 empty] | 115 | 2024-07-03 | 29 | 3438.9666 | 4322.6248 | 62948.7081 | 79095.4373
[17 empty] | 115 | 2024-07-04 | 30 | 3438.9666 | 4322.6248 | 66387.6747 | 83418.0621
[17 empty] | 115 | 2024-07-05 | 31 | 3438.9666 | 4322.6248 | 69826.6413 | 87740.687
[17 empty] | 115 | 2024-07-06 | 32 | 0 | 0 | 69826.6413 | 87740.687
[17 empty] | 115 | 2024-07-07 | 33 | 0 | 0 | 69826.6413 | 87740.687
[17 empty] | 115 | 2024-07-08 | 34 | 3438.9666 | 4322.6248 | 73265.6079 | 92063.3118
[17 empty] | 115 | 2024-07-09 | 35 | 5672.3337 | 7159.0011 | 78937.9416 | 99222.3129
[17 empty] | 115 | 2024-07-10 | 36 | 2582.4701 | 3265.7729 | 81520.4117 | 102488.0857
[17 empty] | 115 | 2024-07-11 | 37 | 2582.4701 | 3265.7729 | 84102.8817 | 105753.8586
[17 empty] | 115 | 2024-07-12 | 38 | 2582.4701 | 3265.7729 | 86685.3518 | 109019.6315
[17 empty] | 115 | 2024-07-13 | 39 | 0 | 0 | 86685.3518 | 109019.6315
[17 empty] | 115 | 2024-07-14 | 40 | 0 | 0 | 86685.3518 | 109019.6315
[17 empty] | 115 | 2024-07-15 | 41 | 2582.4701 | 3265.7729 | 89267.8219 | 112285.4043
[17 empty] | 115 | 2024-07-16 | 42 | 2582.4701 | 3265.7729 | 91850.292 | 115551.1772
[17 empty] | 115 | 2024-07-17 | 43 | 2582.4701 | 3265.7729 | 94432.762 | 118816.9501
[17 empty] | 115 | 2024-07-18 | 44 | 2582.4701 | 3265.7729 | 97015.2321 | 122082.7229
[17 empty] | 115 | 2024-07-19 | 45 | 2582.4701 | 3265.7729 | 99597.7022 | 125348.4958
[17 empty] | 115 | 2024-07-20 | 46 | 0 | 0 | 99597.7022 | 125348.4958
[17 empty] | 115 | 2024-07-21 | 47 | 0 | 0 | 99597.7022 | 125348.4958
[17 empty] | 115 | 2024-07-22 | 48 | 2582.4701 | 3265.7729 | 102180.1722 | 128614.2687
[17 empty] | 115 | 2024-07-23 | 49 | 2582.4701 | 3265.7729 | 104762.6423 | 131880.0415
[17 empty] | 115 | 2024-07-24 | 50 | 2582.4701 | 3265.7729 | 107345.1124 | 135145.8144
[17 empty] | 115 | 2024-07-25 | 51 | 2582.4701 | 3265.7729 | 109927.5824 | 138411.5873
[17 empty] | 115 | 2024-07-26 | 52 | 2582.4701 | 3265.7729 | 112510.0525 | 141677.3602
[17 empty] | 115 | 2024-07-27 | 53 | 0 | 0 | 112510.0525 | 141677.3602
[17 empty] | 115 | 2024-07-28 | 54 | 0 | 0 | 112510.0525 | 141677.3602
[17 empty] | 115 | 2024-07-29 | 55 | 2582.4701 | 3265.7729 | 115092.5226 | 144943.133
[17 empty] | 115 | 2024-07-30 | 56 | 2582.4701 | 3265.7729 | 117674.9926 | 148208.9059
[17 empty] | 115 | 2024-07-31 | 57 | 2582.4701 | 3265.7729 | 120257.4627 | 151474.6788
[17 empty] | 115 | 2024-08-01 | 58 | 2582.4701 | 3265.7729 | 122839.9328 | 154740.4516
[17 empty] | 115 | 2024-08-02 | 59 | 2582.4701 | 3265.7729 | 125422.4029 | 158006.2245
[17 empty] | 115 | 2024-08-03 | 60 | 0 | 0 | 125422.4029 | 158006.2245
[17 empty] | 115 | 2024-08-04 | 61 | 0 | 0 | 125422.4029 | 158006.2245
[17 empty] | 115 | 2024-08-05 | 62 | 2582.4701 | 3265.7729 | 128004.8729 | 161271.9974
[17 empty] | 115 | 2024-08-06 | 63 | 2582.4701 | 3265.7729 | 130587.343 | 164537.7702
[17 empty] | 115 | 2024-08-07 | 64 | 2582.4701 | 3265.7729 | 133169.8131 | 167803.5431
[17 empty] | 115 | 2024-08-08 | 65 | 2582.4701 | 3265.7729 | 135752.2831 | 171069.316
[17 empty] | 115 | 2024-08-09 | 66 | 2582.4701 | 3265.7729 | 138334.7532 | 174335.0888
[17 empty] | 115 | 2024-08-10 | 67 | 0 | 0 | 138334.7532 | 174335.0888
[17 empty] | 115 | 2024-08-11 | 68 | 0 | 0 | 138334.7532 | 174335.0888
[17 empty] | 115 | 2024-08-12 | 69 | 2582.4701 | 3265.7729 | 140917.2233 | 177600.8617
[17 empty] | 115 | 2024-08-13 | 70 | 2582.4701 | 3265.7729 | 143499.6933 | 180866.6346
[17 empty] | 115 | 2024-08-14 | 71 | 2582.4701 | 3265.7729 | 146082.1634 | 184132.4075
[17 empty] | 115 | 2024-08-15 | 72 | 2582.4701 | 3265.7729 | 148664.6335 | 187398.1803
[17 empty] | 115 | 2024-08-16 | 73 | 2582.4701 | 3265.7729 | 151247.1036 | 190663.9532
[17 empty] | 115 | 2024-08-17 | 74 | 0 | 0 | 151247.1036 | 190663.9532
[17 empty] | 115 | 2024-08-18 | 75 | 0 | 0 | 151247.1036 | 190663.9532
[17 empty] | 115 | 2024-08-19 | 76 | 2582.4701 | 3265.7729 | 153829.5736 | 193929.7261
[17 empty] | 115 | 2024-08-20 | 77 | 2582.4701 | 3265.7729 | 156412.0437 | 197195.4989
[17 empty] | 115 | 2024-08-21 | 78 | 2582.4701 | 3265.7729 | 158994.5138 | 200461.2718
[17 empty] | 115 | 2024-08-22 | 79 | 2582.4701 | 3265.7729 | 161576.9838 | 203727.0447
[17 empty] | 115 | 2024-08-23 | 80 | 2582.4701 | 3265.7729 | 164159.4539 | 206992.8175
[17 empty] | 115 | 2024-08-24 | 81 | 0 | 0 | 164159.4539 | 206992.8175
[17 empty] | 115 | 2024-08-25 | 82 | 0 | 0 | 164159.4539 | 206992.8175
[17 empty] | 115 | 2024-08-26 | 83 | 2582.4701 | 3265.7729 | 166741.924 | 210258.5904
[17 empty] | 115 | 2024-08-27 | 84 | 2582.4701 | 3265.7729 | 169324.394 | 213524.3633
[17 empty] | 115 | 2024-08-28 | 85 | 2582.4701 | 3265.7729 | 171906.8641 | 216790.1361
[17 empty] | 115 | 2024-08-29 | 86 | 2582.4701 | 3265.7729 | 174489.3342 | 220055.909
[17 empty] | 115 | 2024-08-30 | 87 | 2582.4701 | 3265.7729 | 177071.8042 | 223321.6819
[17 empty] | 115 | 2024-08-31 | 88 | 0 | 0 | 177071.8042 | 223321.6819
[17 empty] | 115 | 2024-09-01 | 89 | 0 | 0 | 177071.8042 | 223321.6819
[17 empty] | 115 | 2024-09-02 | 90 | 2582.4701 | 3265.7729 | 179654.2743 | 226587.4547
[17 empty] | 115 | 2024-09-03 | 91 | 2582.4701 | 3265.7729 | 182236.7444 | 229853.2276
[17 empty] | 115 | 2024-09-04 | 92 | 2582.4701 | 3265.7729 | 184819.2145 | 233119.0005
[17 empty] | 115 | 2024-09-05 | 93 | 2582.4701 | 3265.7729 | 187401.6845 | 236384.7734
[17 empty] | 115 | 2024-09-06 | 94 | 2582.4701 | 3265.7729 | 189984.1546 | 239650.5462
[17 empty] | 115 | 2024-09-07 | 95 | 0 | 0 | 189984.1546 | 239650.5462
[17 empty] | 115 | 2024-09-08 | 96 | 0 | 0 | 189984.1546 | 239650.5462
[17 empty] | 115 | 2024-09-09 | 97 | 2582.4701 | 3265.7729 | 192566.6247 | 242916.3191
[17 empty] | 115 | 2024-09-10 | 98 | 2582.4701 | 3265.7729 | 195149.0947 | 246182.092
[17 empty] | 115 | 2024-09-11 | 99 | 2582.4701 | 3265.7729 | 197731.5648 | 249447.8648
[17 empty] | 115 | 2024-09-12 | 100 | 2582.4701 | 3265.7729 | 200314.0349 | 252713.6377
[17 empty] | 115 | 2024-09-13 | 101 | 2582.4701 | 3265.7729 | 202896.5049 | 255979.4106
[17 empty] | 115 | 2024-09-14 | 102 | 0 | 0 | 202896.5049 | 255979.4106
[17 empty] | 115 | 2024-09-15 | 103 | 0 | 0 | 202896.5049 | 255979.4106
[17 empty] | 115 | 2024-09-16 | 104 | 2582.4701 | 3265.7729 | 205478.975 | 259245.1834
[17 empty] | 115 | 2024-09-17 | 105 | 2582.4701 | 3265.7729 | 208061.4451 | 262510.9563
[17 empty] | 115 | 2024-09-18 | 106 | 2582.4701 | 3265.7729 | 210643.9151 | 265776.7292
[17 empty] | 115 | 2024-09-19 | 107 | 2582.4701 | 3265.7729 | 213226.3852 | 269042.502
[17 empty] | 115 | 2024-09-20 | 108 | 2582.4701 | 3265.7729 | 215808.8553 | 272308.2749
[17 empty] | 115 | 2024-09-21 | 109 | 0 | 0 | 215808.8553 | 272308.2749
[17 empty] | 115 | 2024-09-22 | 110 | 0 | 0 | 215808.8553 | 272308.2749
[17 empty] | 115 | 2024-09-23 | 111 | 2582.4701 | 3265.7729 | 218391.3254 | 275574.0478
[17 empty] | 115 | 2024-09-24 | 112 | 2582.4701 | 3265.7729 | 220973.7954 | 278839.8206
[17 empty] | 115 | 2024-09-25 | 113 | 2582.4701 | 3265.7729 | 223556.2655 | 282105.5935
[17 empty] | 115 | 2024-09-26 | 114 | 2582.4701 | 3265.7729 | 226138.7356 | 285371.3664
[17 empty] | 115 | 2024-09-27 | 115 | 2582.4701 | 3265.7729 | 228721.2056 | 288637.1393
[17 empty] | 115 | 2024-09-28 | 116 | 0 | 0 | 228721.2056 | 288637.1393
[17 empty] | 115 | 2024-09-29 | 117 | 0 | 0 | 228721.2056 | 288637.1393
[17 empty] | 115 | 2024-09-30 | 118 | 2582.4701 | 3265.7729 | 231303.6757 | 291902.9121
[17 empty] | 115 | 2024-10-01 | 119 | 2582.4701 | 3265.7729 | 233886.1458 | 295168.685
[17 empty] | 115 | 2024-10-02 | 120 | 2582.4701 | 3265.7729 | 236468.6158 | 298434.4579
[17 empty] | 115 | 2024-10-03 | 121 | 2582.4701 | 3265.7729 | 239051.0859 | 301700.2307
[17 empty] | 115 | 2024-10-04 | 122 | 2582.4701 | 3265.7729 | 241633.556 | 304966.0036
[17 empty] | 115 | 2024-10-05 | 123 | 0 | 0 | 241633.556 | 304966.0036
[17 empty] | 115 | 2024-10-06 | 124 | 0 | 0 | 241633.556 | 304966.0036
[17 empty] | 115 | 2024-10-07 | 125 | 6675.4701 | 8177.3729 | 248309.026 | 313143.3765
[17 empty] | 115 | 2024-10-08 | 126 | 6675.4701 | 8177.3729 | 254984.4961 | 321320.7493
[17 empty] | 115 | 2024-10-09 | 127 | 6675.4701 | 8177.3729 | 261659.9662 | 329498.1222
[17 empty] | 115 | 2024-10-10 | 128 | 6675.4701 | 8177.3729 | 268335.4363 | 337675.4951
[17 empty] | 115 | 2024-10-11 | 129 | 6675.4701 | 8177.3729 | 275010.9063 | 345852.8679
[17 empty] | 115 | 2024-10-12 | 130 | 0 | 0 | 275010.9063 | 345852.8679
[17 empty] | 115 | 2024-10-13 | 131 | 0 | 0 | 275010.9063 | 345852.8679
[17 empty] | 115 | 2024-10-14 | 132 | 6675.4701 | 8177.3729 | 281686.3764 | 354030.2408
[17 empty] | 115 | 2024-10-15 | 133 | 9451.2832 | 11230.7673 | 291137.6595 | 365261.0081
[17 empty] | 115 | 2024-10-16 | 134 | 9451.2832 | 11230.7673 | 300588.9427 | 376491.7753
[17 empty] | 115 | 2024-10-17 | 135 | 9451.2832 | 11230.7673 | 310040.2259 | 387722.5426
[17 empty] | 115 | 2024-10-18 | 136 | 9451.2832 | 11230.7673 | 319491.509 | 398953.3099
[17 empty] | 115 | 2024-10-19 | 137 | 0 | 0 | 319491.509 | 398953.3099
[17 empty] | 115 | 2024-10-20 | 138 | 0 | 0 | 319491.509 | 398953.3099
[17 empty] | 115 | 2024-10-21 | 139 | 9451.2832 | 11230.7673 | 328942.7922 | 410184.0771
[17 empty] | 115 | 2024-10-22 | 140 | 9451.2832 | 11230.7673 | 338394.0753 | 421414.8444
[17 empty] | 115 | 2024-10-23 | 141 | 9451.2832 | 11230.7673 | 347845.3585 | 432645.6116
[17 empty] | 115 | 2024-10-24 | 142 | 9451.2832 | 11230.7673 | 357296.6416 | 443876.3789
[17 empty] | 115 | 2024-10-25 | 143 | 9451.2832 | 11230.7673 | 366747.9248 | 455107.1462
[17 empty] | 115 | 2024-10-26 | 144 | 0 | 0 | 366747.9248 | 455107.1462
[17 empty] | 115 | 2024-10-27 | 145 | 0 | 0 | 366747.9248 | 455107.1462
[17 empty] | 115 | 2024-10-28 | 146 | 7217.9161 | 8394.3911 | 373965.8408 | 463501.5372
[17 empty] | 115 | 2024-10-29 | 147 | 7217.9161 | 8394.3911 | 381183.7569 | 471895.9283
[17 empty] | 115 | 2024-10-30 | 148 | 7217.9161 | 8394.3911 | 388401.673 | 480290.3193
[17 empty] | 115 | 2024-10-31 | 149 | 7217.9161 | 8394.3911 | 395619.589 | 488684.7104
[17 empty] | 115 | 2024-11-01 | 150 | 7217.9161 | 8394.3911 | 402837.5051 | 497079.1015
[17 empty] | 115 | 2024-11-02 | 151 | 0 | 0 | 402837.5051 | 497079.1015
[17 empty] | 115 | 2024-11-03 | 152 | 0 | 0 | 402837.5051 | 497079.1015
[17 empty] | 115 | 2024-11-04 | 153 | 7217.9161 | 8394.3911 | 410055.4212 | 505473.4925
[17 empty] | 115 | 2024-11-05 | 154 | 7217.9161 | 8394.3911 | 417273.3372 | 513867.8836
[17 empty] | 115 | 2024-11-06 | 155 | 7217.9161 | 8394.3911 | 424491.2533 | 522262.2746
[17 empty] | 115 | 2024-11-07 | 156 | 7217.9161 | 8394.3911 | 431709.1694 | 530656.6657
[17 empty] | 115 | 2024-11-08 | 157 | 7217.9161 | 8394.3911 | 438927.0854 | 539051.0568
[17 empty] | 115 | 2024-11-09 | 158 | 0 | 0 | 438927.0854 | 539051.0568
[17 empty] | 115 | 2024-11-10 | 159 | 0 | 0 | 438927.0854 | 539051.0568
[17 empty] | 115 | 2024-11-11 | 160 | 7217.9161 | 8394.3911 | 446145.0015 | 547445.4478
[17 empty] | 115 | 2024-11-12 | 161 | 7217.9161 | 8394.3911 | 453362.9176 | 555839.8389
[17 empty] | 115 | 2024-11-13 | 162 | 7217.9161 | 8394.3911 | 460580.8336 | 564234.2299
[17 empty] | 115 | 2024-11-14 | 163 | 7217.9161 | 8394.3911 | 467798.7497 | 572628.621
[17 empty] | 115 | 2024-11-15 | 164 | 3124.9161 | 3482.7911 | 470923.6657 | 576111.412
[17 empty] | 115 | 2024-11-16 | 165 | 0 | 0 | 470923.6657 | 576111.412
[17 empty] | 115 | 2024-11-17 | 166 | 0 | 0 | 470923.6657 | 576111.412
[17 empty] | 115 | 2024-11-18 | 167 | 3124.9161 | 3482.7911 | 474048.5818 | 579594.2031
[17 empty] | 115 | 2024-11-19 | 168 | 3124.9161 | 3482.7911 | 477173.4979 | 583076.9942
[17 empty] | 115 | 2024-11-20 | 169 | 3124.9161 | 3482.7911 | 480298.4139 | 586559.7852
[17 empty] | 115 | 2024-11-21 | 170 | 3124.9161 | 3482.7911 | 483423.33 | 590042.5763
[17 empty] | 115 | 2024-11-22 | 171 | 3124.9161 | 3482.7911 | 486548.2461 | 593525.3673
[17 empty] | 115 | 2024-11-23 | 172 | 0 | 0 | 486548.2461 | 593525.3673
[17 empty] | 115 | 2024-11-24 | 173 | 0 | 0 | 486548.2461 | 593525.3673
[17 empty] | 115 | 2024-11-25 | 174 | 3124.9161 | 3482.7911 | 489673.1621 | 597008.1584
[17 empty] | 115 | 2024-11-26 | 175 | 3124.9161 | 3482.7911 | 492798.0782 | 600490.9495
[17 empty] | 115 | 2024-11-27 | 176 | 3124.9161 | 3482.7911 | 495922.9943 | 603973.7405
[17 empty] | 115 | 2024-11-28 | 177 | 3124.9161 | 3482.7911 | 499047.9103 | 607456.5316
[17 empty] | 115 | 2024-11-29 | 178 | 3124.9161 | 3482.7911 | 502172.8264 | 610939.3226
[17 empty] | 115 | 2024-11-30 | 179 | 0 | 0 | 502172.8264 | 610939.3226
[17 empty] | 115 | 2024-12-01 | 180 | 0 | 0 | 502172.8264 | 610939.3226
[17 empty] | 115 | 2024-12-02 | 181 | 3124.9161 | 3482.7911 | 505297.7425 | 614422.1137
[17 empty] | 115 | 2024-12-03 | 182 | 3124.9161 | 3482.7911 | 508422.6585 | 617904.9048
[17 empty] | 115 | 2024-12-04 | 183 | 3124.9161 | 3482.7911 | 511547.5746 | 621387.6958
[17 empty] | 115 | 2024-12-05 | 184 | 3124.9161 | 3482.7911 | 514672.4907 | 624870.4869
[17 empty] | 115 | 2024-12-06 | 185 | 3124.9161 | 3482.7911 | 517797.4067 | 628353.2779
[17 empty] | 115 | 2024-12-07 | 186 | 0 | 0 | 517797.4067 | 628353.2779
[17 empty] | 115 | 2024-12-08 | 187 | 0 | 0 | 517797.4067 | 628353.2779
[17 empty] | 115 | 2024-12-09 | 188 | 3124.9161 | 3482.7911 | 520922.3228 | 631836.069
[17 empty] | 115 | 2024-12-10 | 189 | 3124.9161 | 3482.7911 | 524047.2389 | 635318.8601
[17 empty] | 115 | 2024-12-11 | 190 | 3124.9161 | 3482.7911 | 527172.1549 | 638801.6511
[17 empty] | 115 | 2024-12-12 | 191 | 3124.9161 | 3482.7911 | 530297.071 | 642284.4422
[17 empty] | 115 | 2024-12-13 | 192 | 3124.9161 | 3482.7911 | 533421.987 | 645767.2332
[17 empty] | 115 | 2024-12-14 | 193 | 0 | 0 | 533421.987 | 645767.2332
[17 empty] | 115 | 2024-12-15 | 194 | 0 | 0 | 533421.987 | 645767.2332
[17 empty] | 115 | 2024-12-16 | 195 | 3124.9161 | 3482.7911 | 536546.9031 | 649250.0243
[17 empty] | 115 | 2024-12-17 | 196 | 3124.9161 | 3482.7911 | 539671.8192 | 652732.8153
[17 empty] | 115 | 2024-12-18 | 197 | 3124.9161 | 3482.7911 | 542796.7352 | 656215.6064
[17 empty] | 115 | 2024-12-19 | 198 | 3124.9161 | 3482.7911 | 545921.6513 | 659698.3975
[17 empty] | 115 | 2024-12-20 | 199 | 3124.9161 | 3482.7911 | 549046.5674 | 663181.1885
[17 empty] | 115 | 2024-12-21 | 200 | 0 | 0 | 549046.5674 | 663181.1885
[17 empty] | 115 | 2024-12-22 | 201 | 0 | 0 | 549046.5674 | 663181.1885
[17 empty] | 115 | 2024-12-23 | 202 | 3124.9161 | 3482.7911 | 552171.4834 | 666663.9796
[17 empty] | 115 | 2024-12-24 | 203 | 3124.9161 | 3482.7911 | 555296.3995 | 670146.7706
[17 empty] | 115 | 2024-12-25 | 204 | 3124.9161 | 3482.7911 | 558421.3156 | 673629.5617
[17 empty] | 115 | 2024-12-26 | 205 | 3124.9161 | 3482.7911 | 561546.2316 | 677112.3528
[17 empty] | 115 | 2024-12-27 | 206 | 3124.9161 | 3482.7911 | 564671.1477 | 680595.1438
[17 empty] | 115 | 2024-12-28 | 207 | 0 | 0 | 564671.1477 | 680595.1438
[17 empty] | 115 | 2024-12-29 | 208 | 0 | 0 | 564671.1477 | 680595.1438
[17 empty] | 115 | 2024-12-30 | 209 | 3124.9161 | 3482.7911 | 567796.0638 | 684077.9349
[17 empty] | 115 | 2024-12-31 | 210 | 3124.9161 | 3482.7911 | 570920.9798 | 687560.7259
[17 empty] | 115 | 2025-01-01 | 211 | 3124.9161 | 3482.7911 | 574045.8959 | 691043.517
[17 empty] | 115 | 2025-01-02 | 212 | 3124.9161 | 3482.7911 | 577170.812 | 694526.3081
[17 empty] | 115 | 2025-01-03 | 213 | 3124.9161 | 3482.7911 | 580295.728 | 698009.0991
[17 empty] | 115 | 2025-01-04 | 214 | 0 | 0 | 580295.728 | 698009.0991
[17 empty] | 115 | 2025-01-05 | 215 | 0 | 0 | 580295.728 | 698009.0991
[17 empty] | 115 | 2025-01-06 | 216 | 3124.9161 | 3482.7911 | 583420.6441 | 701491.8902
[17 empty] | 115 | 2025-01-07 | 217 | 3124.9161 | 3482.7911 | 586545.5602 | 704974.6812
[17 empty] | 115 | 2025-01-08 | 218 | 3124.9161 | 3482.7911 | 589670.4762 | 708457.4723
[17 empty] | 115 | 2025-01-09 | 219 | 3124.9161 | 3482.7911 | 592795.3923 | 711940.2633
[17 empty] | 115 | 2025-01-10 | 220 | 3124.9161 | 3482.7911 | 595920.3083 | 715423.0544
[17 empty] | 115 | 2025-01-11 | 221 | 0 | 0 | 595920.3083 | 715423.0544
[17 empty] | 115 | 2025-01-12 | 222 | 0 | 0 | 595920.3083 | 715423.0544
[17 empty] | 115 | 2025-01-13 | 223 | 3124.9161 | 3482.7911 | 599045.2244 | 718905.8455
[17 empty] | 115 | 2025-01-14 | 224 | 3124.9161 | 3482.7911 | 602170.1405 | 722388.6365
[17 empty] | 115 | 2025-01-15 | 225 | 3124.9161 | 3482.7911 | 605295.0565 | 725871.4276
[17 empty] | 115 | 2025-01-16 | 226 | 3124.9161 | 3482.7911 | 608419.9726 | 729354.2186
[17 empty] | 115 | 2025-01-17 | 227 | 3124.9161 | 3482.7911 | 611544.8887 | 732837.0097
[17 empty] | 115 | 2025-01-18 | 228 | 0 | 0 | 611544.8887 | 732837.0097
[17 empty] | 115 | 2025-01-19 | 229 | 0 | 0 | 611544.8887 | 732837.0097
[17 empty] | 115 | 2025-01-20 | 230 | 3124.9161 | 3482.7911 | 614669.8047 | 736319.8008
[17 empty] | 115 | 2025-01-21 | 231 | 3124.9161 | 3482.7911 | 617794.7208 | 739802.5918
[17 empty] | 115 | 2025-01-22 | 232 | 3124.9161 | 3482.7911 | 620919.6369 | 743285.3829
[17 empty] | 115 | 2025-01-23 | 233 | 3124.9161 | 3482.7911 | 624044.5529 | 746768.1739
[17 empty] | 115 | 2025-01-24 | 234 | 3124.9161 | 3482.7911 | 627169.469 | 750250.965
[17 empty] | 115 | 2025-01-25 | 235 | 0 | 0 | 627169.469 | 750250.965
[17 empty] | 115 | 2025-01-26 | 236 | 0 | 0 | 627169.469 | 750250.965
[17 empty] | 115 | 2025-01-27 | 237 | 3124.9161 | 3482.7911 | 630294.3851 | 753733.7561
[17 empty] | 115 | 2025-01-28 | 238 | 3124.9161 | 3482.7911 | 633419.3011 | 757216.5471
[17 empty] | 115 | 2025-01-29 | 239 | 3124.9161 | 3482.7911 | 636544.2172 | 760699.3382
[17 empty] | 115 | 2025-01-30 | 240 | 3124.9161 | 3482.7911 | 639669.1333 | 764182.1292
[17 empty] | 115 | 2025-01-31 | 241 | 3124.9161 | 3482.7911 | 642794.0493 | 767664.9203
[17 empty] | 115 | 2025-02-01 | 242 | 0 | 0 | 642794.0493 | 767664.9203
[17 empty] | 115 | 2025-02-02 | 243 | 0 | 0 | 642794.0493 | 767664.9203
[17 empty] | 115 | 2025-02-03 | 244 | 3124.9161 | 3482.7911 | 645918.9654 | 771147.7113
[17 empty] | 115 | 2025-02-04 | 245 | 3124.9161 | 3482.7911 | 649043.8814 | 774630.5024
[17 empty] | 115 | 2025-02-05 | 246 | 3124.9161 | 3482.7911 | 652168.7975 | 778113.2935
[17 empty] | 115 | 2025-02-06 | 247 | 3124.9161 | 3482.7911 | 655293.7136 | 781596.0845
[17 empty] | 115 | 2025-02-07 | 248 | 3124.9161 | 3482.7911 | 658418.6296 | 785078.8756
[17 empty] | 115 | 2025-02-08 | 249 | 0 | 0 | 658418.6296 | 785078.8756
[17 empty] | 115 | 2025-02-09 | 250 | 0 | 0 | 658418.6296 | 785078.8756
[17 empty] | 115 | 2025-02-10 | 251 | 3124.9161 | 3482.7911 | 661543.5457 | 788561.6666
[17 empty] | 115 | 2025-02-11 | 252 | 3124.9161 | 3482.7911 | 664668.4618 | 792044.4577
[17 empty] | 115 | 2025-02-12 | 253 | 3124.9161 | 3482.7911 | 667793.3778 | 795527.2488
[17 empty] | 115 | 2025-02-13 | 254 | 3124.9161 | 3482.7911 | 670918.2939 | 799010.0398
[17 empty] | 115 | 2025-02-14 | 255 | 3124.9161 | 3482.7911 | 674043.21 | 802492.8309
[17 empty] | 115 | 2025-02-15 | 256 | 0 | 0 | 674043.21 | 802492.8309
[17 empty] | 115 | 2025-02-16 | 257 | 0 | 0 | 674043.21 | 802492.8309
[17 empty] | 115 | 2025-02-17 | 258 | 3124.9161 | 3482.7911 | 677168.126 | 805975.6219
[17 empty] | 115 | 2025-02-18 | 259 | 3124.9161 | 3482.7911 | 680293.0421 | 809458.413
[17 empty] | 115 | 2025-02-19 | 260 | 3124.9161 | 3482.7911 | 683417.9582 | 812941.2041
[17 empty] | 115 | 2025-02-20 | 261 | 3124.9161 | 3482.7911 | 686542.8742 | 816423.9951
[17 empty] | 115 | 2025-02-21 | 262 | 3124.9161 | 3482.7911 | 689667.7903 | 819906.7862
[17 empty] | 115 | 2025-02-22 | 263 | 0 | 0 | 689667.7903 | 819906.7862
[17 empty] | 115 | 2025-02-23 | 264 | 0 | 0 | 689667.7903 | 819906.7862
[17 empty] | 115 | 2025-02-24 | 265 | 3124.9161 | 3482.7911 | 692792.7064 | 823389.5772
[17 empty] | 115 | 2025-02-25 | 266 | 3124.9161 | 3482.7911 | 695917.6224 | 826872.3683
[17 empty] | 115 | 2025-02-26 | 267 | 3124.9161 | 3482.7911 | 699042.5385 | 830355.1593
[17 empty] | 115 | 2025-02-27 | 268 | 3124.9161 | 3482.7911 | 702167.4546 | 833837.9504
[17 empty] | 115 | 2025-02-28 | 269 | 3124.9161 | 3482.7911 | 705292.3706 | 837320.7415
[17 empty] | 115 | 2025-03-01 | 270 | 0 | 0 | 705292.3706 | 837320.7415
[17 empty] | 115 | 2025-03-02 | 271 | 0 | 0 | 705292.3706 | 837320.7415
[17 empty] | 115 | 2025-03-03 | 272 | 3124.9161 | 3482.7911 | 708417.2867 | 840803.5325
[17 empty] | 115 | 2025-03-04 | 273 | 3124.9161 | 3482.7911 | 711542.2027 | 844286.3236
[17 empty] | 115 | 2025-03-05 | 274 | 3124.9161 | 3482.7911 | 714667.1188 | 847769.1146
[17 empty] | 115 | 2025-03-06 | 275 | 3124.9161 | 3482.7911 | 717792.0349 | 851251.9057
[17 empty] | 115 | 2025-03-07 | 276 | 3124.9161 | 3482.7911 | 720916.9509 | 854734.6968
[17 empty] | 115 | 2025-03-08 | 277 | 0 | 0 | 720916.9509 | 854734.6968
[17 empty] | 115 | 2025-03-09 | 278 | 0 | 0 | 720916.9509 | 854734.6968
[17 empty] | 115 | 2025-03-10 | 279 | 3124.9161 | 3482.7911 | 724041.867 | 858217.4878
[17 empty] | 115 | 2025-03-11 | 280 | 3124.9161 | 3482.7911 | 727166.7831 | 861700.2789
[17 empty] | 115 | 2025-03-12 | 281 | 3124.9161 | 3482.7911 | 730291.6991 | 865183.0699
[17 empty] | 115 | 2025-03-13 | 282 | 349.103 | 429.3967 | 730640.8021 | 865612.4666
[17 empty] | 115 | 2025-03-14 | 283 | 349.103 | 429.3967 | 730989.9051 | 866041.8633
[17 empty] | 115 | 2025-03-15 | 284 | 0 | 0 | 730989.9051 | 866041.8633
[17 empty] | 115 | 2025-03-16 | 285 | 0 | 0 | 730989.9051 | 866041.8633
[17 empty] | 115 | 2025-03-17 | 286 | 349.103 | 429.3967 | 731339.0081 | 866471.2599
[17 empty] | 115 | 2025-03-18 | 287 | 349.103 | 429.3967 | 731688.1111 | 866900.6566
[17 empty] | 115 | 2025-03-19 | 288 | 349.103 | 429.3967 | 732037.214 | 867330.0533
[17 empty] | 115 | 2025-03-20 | 289 | 349.103 | 429.3967 | 732386.317 | 867759.4499
[17 empty] | 115 | 2025-03-21 | 290 | 349.103 | 429.3967 | 732735.42 | 868188.8466
[17 empty] | 115 | 2025-03-22 | 291 | 0 | 0 | 732735.42 | 868188.8466
[17 empty] | 116 | 2024-06-10 | 1 | 400.3784 | 448.4238 | 400.3784 | 448.4238
[17 empty] | 116 | 2024-06-11 | 2 | 400.3784 | 448.4238 | 800.7568 | 896.8476
[17 empty] | 116 | 2024-06-12 | 3 | 400.3784 | 448.4238 | 1201.1352 | 1345.2714
[17 empty] | 116 | 2024-06-13 | 4 | 400.3784 | 448.4238 | 1601.5136 | 1793.6952
[17 empty] | 116 | 2024-06-14 | 5 | 400.3784 | 448.4238 | 2001.892 | 2242.119
[17 empty] | 116 | 2024-06-15 | 6 | 0 | 0 | 2001.892 | 2242.119
[17 empty] | 116 | 2024-06-16 | 7 | 0 | 0 | 2001.892 | 2242.119
[17 empty] | 116 | 2024-06-17 | 8 | 4186.3784 | 5218.7838 | 6188.2704 | 7460.9028
[17 empty] | 116 | 2024-06-18 | 9 | 4186.3784 | 5218.7838 | 10374.6488 | 12679.6867
[17 empty] | 116 | 2024-06-19 | 10 | 4186.3784 | 5218.7838 | 14561.0272 | 17898.4705
[17 empty] | 116 | 2024-06-20 | 11 | 4186.3784 | 5218.7838 | 18747.4056 | 23117.2543
[17 empty] | 116 | 2024-06-21 | 12 | 4186.3784 | 5218.7838 | 22933.784 | 28336.0381
[17 empty] | 116 | 2024-06-22 | 13 | 0 | 0 | 22933.784 | 28336.0381
[17 empty] | 116 | 2024-06-23 | 14 | 0 | 0 | 22933.784 | 28336.0381
[17 empty] | 116 | 2024-06-24 | 15 | 4186.3784 | 5218.7838 | 27120.1624 | 33554.8219
[17 empty] | 116 | 2024-06-25 | 16 | 4186.3784 | 5218.7838 | 31306.5408 | 38773.6057
[17 empty] | 116 | 2024-06-26 | 17 | 4186.3784 | 5218.7838 | 35492.9192 | 43992.3895
[17 empty] | 116 | 2024-06-27 | 18 | 4186.3784 | 5218.7838 | 39679.2976 | 49211.1733
[17 empty] | 116 | 2024-06-28 | 19 | 4186.3784 | 5218.7838 | 43865.676 | 54429.9571
[17 empty] | 116 | 2024-06-29 | 20 | 0 | 0 | 43865.676 | 54429.9571
[17 empty] | 116 | 2024-06-30 | 21 | 0 | 0 | 43865.676 | 54429.9571
[17 empty] | 116 | 2024-07-01 | 22 | 4186.3784 | 5218.7838 | 48052.0544 | 59648.7409
[17 empty] | 116 | 2024-07-02 | 23 | 4186.3784 | 5218.7838 | 52238.4328 | 64867.5247
[17 empty] | 116 | 2024-07-03 | 24 | 4186.3784 | 5218.7838 | 56424.8112 | 70086.3085
[17 empty] | 116 | 2024-07-04 | 25 | 4186.3784 | 5218.7838 | 60611.1896 | 75305.0924
[17 empty] | 116 | 2024-07-05 | 26 | 4186.3784 | 5218.7838 | 64797.568 | 80523.8762
[17 empty] | 116 | 2024-07-06 | 27 | 0 | 0 | 64797.568 | 80523.8762
[17 empty] | 116 | 2024-07-07 | 28 | 0 | 0 | 64797.568 | 80523.8762
[17 empty] | 116 | 2024-07-08 | 29 | 4186.3784 | 5218.7838 | 68983.9464 | 85742.66
[17 empty] | 116 | 2024-07-09 | 30 | 4186.3784 | 5218.7838 | 73170.3248 | 90961.4438
[17 empty] | 116 | 2024-07-10 | 31 | 4186.3784 | 5218.7838 | 77356.7032 | 96180.2276
[17 empty] | 116 | 2024-07-11 | 32 | 7616.3784 | 9060.3838 | 84973.0816 | 105240.6114
[17 empty] | 116 | 2024-07-12 | 33 | 3830.3784 | 4290.0238 | 88803.46 | 109530.6352
[17 empty] | 116 | 2024-07-13 | 34 | 0 | 0 | 88803.46 | 109530.6352
[17 empty] | 116 | 2024-07-14 | 35 | 0 | 0 | 88803.46 | 109530.6352
[17 empty] | 116 | 2024-07-15 | 36 | 3830.3784 | 4290.0238 | 92633.8384 | 113820.659
[17 empty] | 116 | 2024-07-16 | 37 | 3830.3784 | 4290.0238 | 96464.2168 | 118110.6828
[17 empty] | 116 | 2024-07-17 | 38 | 3830.3784 | 4290.0238 | 100294.5952 | 122400.7066
[17 empty] | 116 | 2024-07-18 | 39 | 3830.3784 | 4290.0238 | 104124.9736 | 126690.7304
[17 empty] | 116 | 2024-07-19 | 40 | 3830.3784 | 4290.0238 | 107955.352 | 130980.7542
[17 empty] | 116 | 2024-07-20 | 41 | 0 | 0 | 107955.352 | 130980.7542
[17 empty] | 116 | 2024-07-21 | 42 | 0 | 0 | 107955.352 | 130980.7542
[17 empty] | 116 | 2024-07-22 | 43 | 3830.3784 | 4290.0238 | 111785.7304 | 135270.778
[17 empty] | 116 | 2024-07-23 | 44 | 3830.3784 | 4290.0238 | 115616.1088 | 139560.8019
[17 empty] | 116 | 2024-07-24 | 45 | 3830.3784 | 4290.0238 | 119446.4872 | 143850.8257
[17 empty] | 116 | 2024-07-25 | 46 | 3830.3784 | 4290.0238 | 123276.8656 | 148140.8495
[17 empty] | 116 | 2024-07-26 | 47 | 3830.3784 | 4290.0238 | 127107.244 | 152430.8733
[17 empty] | 116 | 2024-07-27 | 48 | 0 | 0 | 127107.244 | 152430.8733
[17 empty] | 116 | 2024-07-28 | 49 | 0 | 0 | 127107.244 | 152430.8733
[17 empty] | 116 | 2024-07-29 | 50 | 3830.3784 | 4290.0238 | 130937.6224 | 156720.8971
[17 empty] | 116 | 2024-07-30 | 51 | 3830.3784 | 4290.0238 | 134768.0008 | 161010.9209
[17 empty] | 116 | 2024-07-31 | 52 | 3830.3784 | 4290.0238 | 138598.3792 | 165300.9447
[17 empty] | 116 | 2024-08-01 | 53 | 3830.3784 | 4290.0238 | 142428.7576 | 169590.9685
[17 empty] | 116 | 2024-08-02 | 54 | 3830.3784 | 4290.0238 | 146259.136 | 173880.9923
[17 empty] | 116 | 2024-08-03 | 55 | 0 | 0 | 146259.136 | 173880.9923
[17 empty] | 116 | 2024-08-04 | 56 | 0 | 0 | 146259.136 | 173880.9923
[17 empty] | 116 | 2024-08-05 | 57 | 3830.3784 | 4290.0238 | 150089.5144 | 178171.0161
[17 empty] | 116 | 2024-08-06 | 58 | 3830.3784 | 4290.0238 | 153919.8928 | 182461.0399
[17 empty] | 116 | 2024-08-07 | 59 | 3830.3784 | 4290.0238 | 157750.2712 | 186751.0637
[17 empty] | 116 | 2024-08-08 | 60 | 3830.3784 | 4290.0238 | 161580.6496 | 191041.0876
[17 empty] | 116 | 2024-08-09 | 61 | 3830.3784 | 4290.0238 | 165411.028 | 195331.1114
[17 empty] | 116 | 2024-08-10 | 62 | 0 | 0 | 165411.028 | 195331.1114
[17 empty] | 116 | 2024-08-11 | 63 | 0 | 0 | 165411.028 | 195331.1114
[17 empty] | 116 | 2024-08-12 | 64 | 3830.3784 | 4290.0238 | 169241.4064 | 199621.1352
[17 empty] | 116 | 2024-08-13 | 65 | 3830.3784 | 4290.0238 | 173071.7848 | 203911.159
[17 empty] | 116 | 2024-08-14 | 66 | 3830.3784 | 4290.0238 | 176902.1632 | 208201.1828
[17 empty] | 116 | 2024-08-15 | 67 | 3830.3784 | 4290.0238 | 180732.5416 | 212491.2066
[17 empty] | 116 | 2024-08-16 | 68 | 3830.3784 | 4290.0238 | 184562.92 | 216781.2304
[17 empty] | 116 | 2024-08-17 | 69 | 0 | 0 | 184562.92 | 216781.2304
[17 empty] | 116 | 2024-08-18 | 70 | 0 | 0 | 184562.92 | 216781.2304
[17 empty] | 116 | 2024-08-19 | 71 | 3830.3784 | 4290.0238 | 188393.2984 | 221071.2542
[17 empty] | 116 | 2024-08-20 | 72 | 3830.3784 | 4290.0238 | 192223.6768 | 225361.278
[17 empty] | 116 | 2024-08-21 | 73 | 3830.3784 | 4290.0238 | 196054.0552 | 229651.3018
[17 empty] | 116 | 2024-08-22 | 74 | 3830.3784 | 4290.0238 | 199884.4336 | 233941.3256
[17 empty] | 116 | 2024-08-23 | 75 | 3830.3784 | 4290.0238 | 203714.812 | 238231.3494
[17 empty] | 116 | 2024-08-24 | 76 | 0 | 0 | 203714.812 | 238231.3494
[17 empty] | 116 | 2024-08-25 | 77 | 0 | 0 | 203714.812 | 238231.3494
[17 empty] | 116 | 2024-08-26 | 78 | 3830.3784 | 4290.0238 | 207545.1904 | 242521.3732
[17 empty] | 116 | 2024-08-27 | 79 | 3830.3784 | 4290.0238 | 211375.5688 | 246811.3971
[17 empty] | 116 | 2024-08-28 | 80 | 3830.3784 | 4290.0238 | 215205.9472 | 251101.4209
[17 empty] | 116 | 2024-08-29 | 81 | 3830.3784 | 4290.0238 | 219036.3256 | 255391.4447
[17 empty] | 116 | 2024-08-30 | 82 | 3830.3784 | 4290.0238 | 222866.704 | 259681.4685
[17 empty] | 116 | 2024-08-31 | 83 | 0 | 0 | 222866.704 | 259681.4685
[17 empty] | 116 | 2024-09-01 | 84 | 0 | 0 | 222866.704 | 259681.4685
[17 empty] | 116 | 2024-09-02 | 85 | 3830.3784 | 4290.0238 | 226697.0824 | 263971.4923
[17 empty] | 116 | 2024-09-03 | 86 | 3830.3784 | 4290.0238 | 230527.4608 | 268261.5161
[17 empty] | 116 | 2024-09-04 | 87 | 3830.3784 | 4290.0238 | 234357.8392 | 272551.5399
[17 empty] | 116 | 2024-09-05 | 88 | 3830.3784 | 4290.0238 | 238188.2176 | 276841.5637
[17 empty] | 116 | 2024-09-06 | 89 | 3830.3784 | 4290.0238 | 242018.596 | 281131.5875
[17 empty] | 116 | 2024-09-07 | 90 | 0 | 0 | 242018.596 | 281131.5875
[17 empty] | 116 | 2024-09-08 | 91 | 0 | 0 | 242018.596 | 281131.5875
[17 empty] | 116 | 2024-09-09 | 92 | 3830.3784 | 4290.0238 | 245848.9744 | 285421.6113
[17 empty] | 116 | 2024-09-10 | 93 | 3830.3784 | 4290.0238 | 249679.3528 | 289711.6351
[17 empty] | 116 | 2024-09-11 | 94 | 3830.3784 | 4290.0238 | 253509.7312 | 294001.6589
[17 empty] | 116 | 2024-09-12 | 95 | 3830.3784 | 4290.0238 | 257340.1096 | 298291.6828
[17 empty] | 116 | 2024-09-13 | 96 | 3830.3784 | 4290.0238 | 261170.488 | 302581.7066
[17 empty] | 116 | 2024-09-14 | 97 | 0 | 0 | 261170.488 | 302581.7066
[17 empty] | 116 | 2024-09-15 | 98 | 0 | 0 | 261170.488 | 302581.7066
[17 empty] | 116 | 2024-09-16 | 99 | 3830.3784 | 4290.0238 | 265000.8664 | 306871.7304
[17 empty] | 116 | 2024-09-17 | 100 | 3830.3784 | 4290.0238 | 268831.2448 | 311161.7542
[17 empty] | 116 | 2024-09-18 | 101 | 3830.3784 | 4290.0238 | 272661.6232 | 315451.778
[17 empty] | 116 | 2024-09-19 | 102 | 3830.3784 | 4290.0238 | 276492.0016 | 319741.8018
[17 empty] | 116 | 2024-09-20 | 103 | 3830.3784 | 4290.0238 | 280322.38 | 324031.8256
[17 empty] | 116 | 2024-09-21 | 104 | 0 | 0 | 280322.38 | 324031.8256
[17 empty] | 116 | 2024-09-22 | 105 | 0 | 0 | 280322.38 | 324031.8256
[17 empty] | 116 | 2024-09-23 | 106 | 3830.3784 | 4290.0238 | 284152.7584 | 328321.8494
[17 empty] | 116 | 2024-09-24 | 107 | 3830.3784 | 4290.0238 | 287983.1368 | 332611.8732
[17 empty] | 116 | 2024-09-25 | 108 | 3830.3784 | 4290.0238 | 291813.5152 | 336901.897
[17 empty] | 116 | 2024-09-26 | 109 | 3830.3784 | 4290.0238 | 295643.8936 | 341191.9208
[17 empty] | 116 | 2024-09-27 | 110 | 3830.3784 | 4290.0238 | 299474.272 | 345481.9446
[17 empty] | 116 | 2024-09-28 | 111 | 0 | 0 | 299474.272 | 345481.9446
[17 empty] | 116 | 2024-09-29 | 112 | 0 | 0 | 299474.272 | 345481.9446
[17 empty] | 116 | 2024-09-30 | 113 | 3830.3784 | 4290.0238 | 303304.6504 | 349771.9684
[17 empty] | 116 | 2024-10-01 | 114 | 3830.3784 | 4290.0238 | 307135.0288 | 354061.9923
[17 empty] | 116 | 2024-10-02 | 115 | 3830.3784 | 4290.0238 | 310965.4072 | 358352.0161
[17 empty] | 116 | 2024-10-03 | 116 | 3830.3784 | 4290.0238 | 314795.7856 | 362642.0399
[17 empty] | 116 | 2024-10-04 | 117 | 3830.3784 | 4290.0238 | 318626.164 | 366932.0637
[17 empty] | 116 | 2024-10-05 | 118 | 0 | 0 | 318626.164 | 366932.0637
[17 empty] | 116 | 2024-10-06 | 119 | 0 | 0 | 318626.164 | 366932.0637
[17 empty] | 116 | 2024-10-07 | 120 | 3830.3784 | 4290.0238 | 322456.5424 | 371222.0875
[17 empty] | 116 | 2024-10-08 | 121 | 3830.3784 | 4290.0238 | 326286.9208 | 375512.1113
[17 empty] | 116 | 2024-10-09 | 122 | 3830.3784 | 4290.0238 | 330117.2992 | 379802.1351
[17 empty] | 116 | 2024-10-10 | 123 | 3830.3784 | 4290.0238 | 333947.6776 | 384092.1589
[17 empty] | 116 | 2024-10-11 | 124 | 3830.3784 | 4290.0238 | 337778.056 | 388382.1827
[17 empty] | 116 | 2024-10-12 | 125 | 0 | 0 | 337778.056 | 388382.1827
[17 empty] | 116 | 2024-10-13 | 126 | 0 | 0 | 337778.056 | 388382.1827
[17 empty] | 116 | 2024-10-14 | 127 | 3830.3784 | 4290.0238 | 341608.4344 | 392672.2065
[17 empty] | 116 | 2024-10-15 | 128 | 3830.3784 | 4290.0238 | 345438.8128 | 396962.2303
[17 empty] | 116 | 2024-10-16 | 129 | 3830.3784 | 4290.0238 | 349269.1912 | 401252.2541
[17 empty] | 116 | 2024-10-17 | 130 | 3830.3784 | 4290.0238 | 353099.5696 | 405542.278
[17 empty] | 116 | 2024-10-18 | 131 | 3830.3784 | 4290.0238 | 356929.948 | 409832.3018
[17 empty] | 116 | 2024-10-19 | 132 | 0 | 0 | 356929.948 | 409832.3018
[17 empty] | 116 | 2024-10-20 | 133 | 0 | 0 | 356929.948 | 409832.3018
[17 empty] | 116 | 2024-10-21 | 134 | 3830.3784 | 4290.0238 | 360760.3264 | 414122.3256
[17 empty] | 116 | 2024-10-22 | 135 | 3830.3784 | 4290.0238 | 364590.7048 | 418412.3494
[17 empty] | 116 | 2024-10-23 | 136 | 3830.3784 | 4290.0238 | 368421.0832 | 422702.3732
[17 empty] | 116 | 2024-10-24 | 137 | 3830.3784 | 4290.0238 | 372251.4616 | 426992.397
[17 empty] | 116 | 2024-10-25 | 138 | 3830.3784 | 4290.0238 | 376081.84 | 431282.4208
[17 empty] | 116 | 2024-10-26 | 139 | 0 | 0 | 376081.84 | 431282.4208
[17 empty] | 116 | 2024-10-27 | 140 | 0 | 0 | 376081.84 | 431282.4208
[17 empty] | 116 | 2024-10-28 | 141 | 3830.3784 | 4290.0238 | 379912.2184 | 435572.4446
[17 empty] | 116 | 2024-10-29 | 142 | 3830.3784 | 4290.0238 | 383742.5968 | 439862.4684
[17 empty] | 116 | 2024-10-30 | 143 | 3830.3784 | 4290.0238 | 387572.9752 | 444152.4922
[17 empty] | 116 | 2024-10-31 | 144 | 3830.3784 | 4290.0238 | 391403.3536 | 448442.516
[17 empty] | 116 | 2024-11-01 | 145 | 3830.3784 | 4290.0238 | 395233.732 | 452732.5398
[17 empty] | 116 | 2024-11-02 | 146 | 0 | 0 | 395233.732 | 452732.5398
[17 empty] | 116 | 2024-11-03 | 147 | 0 | 0 | 395233.732 | 452732.5398
[17 empty] | 116 | 2024-11-04 | 148 | 3830.3784 | 4290.0238 | 399064.1104 | 457022.5636
[17 empty] | 116 | 2024-11-05 | 149 | 3830.3784 | 4290.0238 | 402894.4888 | 461312.5875
[17 empty] | 116 | 2024-11-06 | 150 | 7755.0451 | 8960.3771 | 410649.5339 | 470272.9646
[17 empty] | 116 | 2024-11-07 | 151 | 7755.0451 | 8960.3771 | 418404.5789 | 479233.3417
[17 empty] | 116 | 2024-11-08 | 152 | 7755.0451 | 8960.3771 | 426159.624 | 488193.7189
[17 empty] | 116 | 2024-11-09 | 153 | 0 | 0 | 426159.624 | 488193.7189
[17 empty] | 116 | 2024-11-10 | 154 | 0 | 0 | 426159.624 | 488193.7189
[17 empty] | 116 | 2024-11-11 | 155 | 7755.0451 | 8960.3771 | 433914.6691 | 497154.096
[17 empty] | 116 | 2024-11-12 | 156 | 7755.0451 | 8960.3771 | 441669.7141 | 506114.4732
[17 empty] | 116 | 2024-11-13 | 157 | 7755.0451 | 8960.3771 | 449424.7592 | 515074.8503
[17 empty] | 116 | 2024-11-14 | 158 | 7755.0451 | 8960.3771 | 457179.8043 | 524035.2274
[17 empty] | 116 | 2024-11-15 | 159 | 7755.0451 | 8960.3771 | 464934.8493 | 532995.6046
[17 empty] | 116 | 2024-11-16 | 160 | 0 | 0 | 464934.8493 | 532995.6046
[17 empty] | 116 | 2024-11-17 | 161 | 0 | 0 | 464934.8493 | 532995.6046
[17 empty] | 116 | 2024-11-18 | 162 | 10818.0451 | 12390.9371 | 475752.8944 | 545386.5417
[17 empty] | 116 | 2024-11-19 | 163 | 10818.0451 | 12390.9371 | 486570.9395 | 557777.4789
[17 empty] | 116 | 2024-11-20 | 164 | 10818.0451 | 12390.9371 | 497388.9845 | 570168.416
[17 empty] | 116 | 2024-11-21 | 165 | 10818.0451 | 12390.9371 | 508207.0296 | 582559.3532
[17 empty] | 116 | 2024-11-22 | 166 | 10818.0451 | 12390.9371 | 519025.0747 | 594950.2903
[17 empty] | 116 | 2024-11-23 | 167 | 0 | 0 | 519025.0747 | 594950.2903
[17 empty] | 116 | 2024-11-24 | 168 | 0 | 0 | 519025.0747 | 594950.2903
[17 empty] | 116 | 2024-11-25 | 169 | 10818.0451 | 12390.9371 | 529843.1197 | 607341.2274
[17 empty] | 116 | 2024-11-26 | 170 | 10818.0451 | 12390.9371 | 540661.1648 | 619732.1646
[17 empty] | 116 | 2024-11-27 | 171 | 7388.0451 | 8549.3371 | 548049.2099 | 628281.5017
[17 empty] | 116 | 2024-11-28 | 172 | 7388.0451 | 8549.3371 | 555437.2549 | 636830.8389
[17 empty] | 116 | 2024-11-29 | 173 | 7388.0451 | 8549.3371 | 562825.3 | 645380.176
[17 empty] | 116 | 2024-11-30 | 174 | 0 | 0 | 562825.3 | 645380.176
[17 empty] | 116 | 2024-12-01 | 175 | 0 | 0 | 562825.3 | 645380.176
[17 empty] | 116 | 2024-12-02 | 176 | 7388.0451 | 8549.3371 | 570213.3451 | 653929.5131
[17 empty] | 116 | 2024-12-03 | 177 | 7388.0451 | 8549.3371 | 577601.3901 | 662478.8503
[17 empty] | 116 | 2024-12-04 | 178 | 7388.0451 | 8549.3371 | 584989.4352 | 671028.1874
[17 empty] | 116 | 2024-12-05 | 179 | 7388.0451 | 8549.3371 | 592377.4803 | 679577.5246
[17 empty] | 116 | 2024-12-06 | 180 | 7388.0451 | 8549.3371 | 599765.5253 | 688126.8617
[17 empty] | 116 | 2024-12-07 | 181 | 0 | 0 | 599765.5253 | 688126.8617
[17 empty] | 116 | 2024-12-08 | 182 | 0 | 0 | 599765.5253 | 688126.8617
[17 empty] | 116 | 2024-12-09 | 183 | 7388.0451 | 8549.3371 | 607153.5704 | 696676.1988
[17 empty] | 116 | 2024-12-10 | 184 | 7388.0451 | 8549.3371 | 614541.6155 | 705225.536
[17 empty] | 116 | 2024-12-11 | 185 | 7388.0451 | 8549.3371 | 621929.6605 | 713774.8731
[17 empty] | 116 | 2024-12-12 | 186 | 7388.0451 | 8549.3371 | 629317.7056 | 722324.2103
[17 empty] | 116 | 2024-12-13 | 187 | 7388.0451 | 8549.3371 | 636705.7507 | 730873.5474
[17 empty] | 116 | 2024-12-14 | 188 | 0 | 0 | 636705.7507 | 730873.5474
[17 empty] | 116 | 2024-12-15 | 189 | 0 | 0 | 636705.7507 | 730873.5474
[17 empty] | 116 | 2024-12-16 | 190 | 7388.0451 | 8549.3371 | 644093.7957 | 739422.8846
[17 empty] | 116 | 2024-12-17 | 191 | 7388.0451 | 8549.3371 | 651481.8408 | 747972.2217
[17 empty] | 116 | 2024-12-18 | 192 | 3463.3784 | 3878.9838 | 654945.2192 | 751851.2055
[17 empty] | 116 | 2024-12-19 | 193 | 3463.3784 | 3878.9838 | 658408.5976 | 755730.1893
[17 empty] | 116 | 2024-12-20 | 194 | 3463.3784 | 3878.9838 | 661871.976 | 759609.1731
[17 empty] | 116 | 2024-12-21 | 195 | 0 | 0 | 661871.976 | 759609.1731
[17 empty] | 116 | 2024-12-22 | 196 | 0 | 0 | 661871.976 | 759609.1731
[17 empty] | 116 | 2024-12-23 | 197 | 3463.3784 | 3878.9838 | 665335.3544 | 763488.1569
[17 empty] | 116 | 2024-12-24 | 198 | 3463.3784 | 3878.9838 | 668798.7328 | 767367.1407
[17 empty] | 116 | 2024-12-25 | 199 | 3463.3784 | 3878.9838 | 672262.1112 | 771246.1245
[17 empty] | 116 | 2024-12-26 | 200 | 3463.3784 | 3878.9838 | 675725.4896 | 775125.1084
[17 empty] | 116 | 2024-12-27 | 201 | 3463.3784 | 3878.9838 | 679188.868 | 779004.0922
[17 empty] | 116 | 2024-12-28 | 202 | 0 | 0 | 679188.868 | 779004.0922
[17 empty] | 116 | 2024-12-29 | 203 | 0 | 0 | 679188.868 | 779004.0922
[17 empty] | 116 | 2024-12-30 | 204 | 3463.3784 | 3878.9838 | 682652.2464 | 782883.076
[17 empty] | 116 | 2024-12-31 | 205 | 3463.3784 | 3878.9838 | 686115.6248 | 786762.0598
[17 empty] | 116 | 2025-01-01 | 206 | 3463.3784 | 3878.9838 | 689579.0032 | 790641.0436
[17 empty] | 116 | 2025-01-02 | 207 | 3463.3784 | 3878.9838 | 693042.3816 | 794520.0274
[17 empty] | 116 | 2025-01-03 | 208 | 3463.3784 | 3878.9838 | 696505.76 | 798399.0112
[17 empty] | 116 | 2025-01-04 | 209 | 0 | 0 | 696505.76 | 798399.0112
[17 empty] | 116 | 2025-01-05 | 210 | 0 | 0 | 696505.76 | 798399.0112
[17 empty] | 116 | 2025-01-06 | 211 | 3463.3784 | 3878.9838 | 699969.1384 | 802277.995
[17 empty] | 116 | 2025-01-07 | 212 | 3463.3784 | 3878.9838 | 703432.5168 | 806156.9788
[17 empty] | 116 | 2025-01-08 | 213 | 3463.3784 | 3878.9838 | 706895.8952 | 810035.9626
[17 empty] | 116 | 2025-01-09 | 214 | 3463.3784 | 3878.9838 | 710359.2736 | 813914.9464
[17 empty] | 116 | 2025-01-10 | 215 | 3463.3784 | 3878.9838 | 713822.652 | 817793.9302
[17 empty] | 116 | 2025-01-11 | 216 | 0 | 0 | 713822.652 | 817793.9302
[17 empty] | 116 | 2025-01-12 | 217 | 0 | 0 | 713822.652 | 817793.9302
[17 empty] | 116 | 2025-01-13 | 218 | 3463.3784 | 3878.9838 | 717286.0304 | 821672.914
[17 empty] | 116 | 2025-01-14 | 219 | 3463.3784 | 3878.9838 | 720749.4088 | 825551.8979
[17 empty] | 116 | 2025-01-15 | 220 | 3463.3784 | 3878.9838 | 724212.7872 | 829430.8817
[17 empty] | 116 | 2025-01-16 | 221 | 3463.3784 | 3878.9838 | 727676.1656 | 833309.8655
[17 empty] | 116 | 2025-01-17 | 222 | 3463.3784 | 3878.9838 | 731139.544 | 837188.8493
[17 empty] | 116 | 2025-01-18 | 223 | 0 | 0 | 731139.544 | 837188.8493
[17 empty] | 116 | 2025-01-19 | 224 | 0 | 0 | 731139.544 | 837188.8493
[17 empty] | 116 | 2025-01-20 | 225 | 3463.3784 | 3878.9838 | 734602.9224 | 841067.8331
[17 empty] | 116 | 2025-01-21 | 226 | 3463.3784 | 3878.9838 | 738066.3008 | 844946.8169
[17 empty] | 116 | 2025-01-22 | 227 | 3463.3784 | 3878.9838 | 741529.6792 | 848825.8007
[17 empty] | 116 | 2025-01-23 | 228 | 3463.3784 | 3878.9838 | 744993.0576 | 852704.7845
[17 empty] | 116 | 2025-01-24 | 229 | 3463.3784 | 3878.9838 | 748456.436 | 856583.7683
[17 empty] | 116 | 2025-01-25 | 230 | 0 | 0 | 748456.436 | 856583.7683
[17 empty] | 116 | 2025-01-26 | 231 | 0 | 0 | 748456.436 | 856583.7683
[17 empty] | 116 | 2025-01-27 | 232 | 3463.3784 | 3878.9838 | 751919.8144 | 860462.7521
[17 empty] | 116 | 2025-01-28 | 233 | 3463.3784 | 3878.9838 | 755383.1928 | 864341.7359
[17 empty] | 116 | 2025-01-29 | 234 | 3463.3784 | 3878.9838 | 758846.5712 | 868220.7197
[17 empty] | 116 | 2025-01-30 | 235 | 3463.3784 | 3878.9838 | 762309.9496 | 872099.7036
[17 empty] | 116 | 2025-01-31 | 236 | 3463.3784 | 3878.9838 | 765773.328 | 875978.6874
[17 empty] | 116 | 2025-02-01 | 237 | 0 | 0 | 765773.328 | 875978.6874
[17 empty] | 116 | 2025-02-02 | 238 | 0 | 0 | 765773.328 | 875978.6874
[17 empty] | 116 | 2025-02-03 | 239 | 3463.3784 | 3878.9838 | 769236.7064 | 879857.6712
[17 empty] | 116 | 2025-02-04 | 240 | 3463.3784 | 3878.9838 | 772700.0848 | 883736.655
[17 empty] | 116 | 2025-02-05 | 241 | 3463.3784 | 3878.9838 | 776163.4632 | 887615.6388
[17 empty] | 116 | 2025-02-06 | 242 | 3463.3784 | 3878.9838 | 779626.8416 | 891494.6226
[17 empty] | 116 | 2025-02-07 | 243 | 3463.3784 | 3878.9838 | 783090.22 | 895373.6064
[17 empty] | 116 | 2025-02-08 | 244 | 0 | 0 | 783090.22 | 895373.6064
[17 empty] | 116 | 2025-02-09 | 245 | 0 | 0 | 783090.22 | 895373.6064
[17 empty] | 116 | 2025-02-10 | 246 | 3463.3784 | 3878.9838 | 786553.5984 | 899252.5902
[17 empty] | 116 | 2025-02-11 | 247 | 3463.3784 | 3878.9838 | 790016.9768 | 903131.574
[17 empty] | 116 | 2025-02-12 | 248 | 3463.3784 | 3878.9838 | 793480.3552 | 907010.5578
[17 empty] | 116 | 2025-02-13 | 249 | 3463.3784 | 3878.9838 | 796943.7336 | 910889.5416
[17 empty] | 116 | 2025-02-14 | 250 | 3463.3784 | 3878.9838 | 800407.112 | 914768.5254
[17 empty] | 116 | 2025-02-15 | 251 | 0 | 0 | 800407.112 | 914768.5254
[17 empty] | 116 | 2025-02-16 | 252 | 0 | 0 | 800407.112 | 914768.5254
[17 empty] | 116 | 2025-02-17 | 253 | 3463.3784 | 3878.9838 | 803870.4904 | 918647.5092
[17 empty] | 116 | 2025-02-18 | 254 | 3463.3784 | 3878.9838 | 807333.8688 | 922526.4931
[17 empty] | 116 | 2025-02-19 | 255 | 3463.3784 | 3878.9838 | 810797.2472 | 926405.4769
[17 empty] | 116 | 2025-02-20 | 256 | 3463.3784 | 3878.9838 | 814260.6256 | 930284.4607
[17 empty] | 116 | 2025-02-21 | 257 | 3463.3784 | 3878.9838 | 817724.004 | 934163.4445
[17 empty] | 116 | 2025-02-22 | 258 | 0 | 0 | 817724.004 | 934163.4445
[17 empty] | 116 | 2025-02-23 | 259 | 0 | 0 | 817724.004 | 934163.4445
[17 empty] | 116 | 2025-02-24 | 260 | 3463.3784 | 3878.9838 | 821187.3824 | 938042.4283
[17 empty] | 116 | 2025-02-25 | 261 | 3463.3784 | 3878.9838 | 824650.7608 | 941921.4121
[17 empty] | 116 | 2025-02-26 | 262 | 3463.3784 | 3878.9838 | 828114.1392 | 945800.3959
[17 empty] | 116 | 2025-02-27 | 263 | 3463.3784 | 3878.9838 | 831577.5176 | 949679.3797
[17 empty] | 116 | 2025-02-28 | 264 | 3463.3784 | 3878.9838 | 835040.896 | 953558.3635
[17 empty] | 116 | 2025-03-01 | 265 | 0 | 0 | 835040.896 | 953558.3635
[17 empty] | 116 | 2025-03-02 | 266 | 0 | 0 | 835040.896 | 953558.3635
[17 empty] | 116 | 2025-03-03 | 267 | 3463.3784 | 3878.9838 | 838504.2744 | 957437.3473
[17 empty] | 116 | 2025-03-04 | 268 | 3463.3784 | 3878.9838 | 841967.6528 | 961316.3311
[17 empty] | 116 | 2025-03-05 | 269 | 3463.3784 | 3878.9838 | 845431.0312 | 965195.3149
[17 empty] | 116 | 2025-03-06 | 270 | 3463.3784 | 3878.9838 | 848894.4096 | 969074.2988
[17 empty] | 116 | 2025-03-07 | 271 | 3463.3784 | 3878.9838 | 852357.788 | 972953.2826
[17 empty] | 116 | 2025-03-08 | 272 | 0 | 0 | 852357.788 | 972953.2826
[17 empty] | 116 | 2025-03-09 | 273 | 0 | 0 | 852357.788 | 972953.2826
[17 empty] | 116 | 2025-03-10 | 274 | 3463.3784 | 3878.9838 | 855821.1664 | 976832.2664
[17 empty] | 116 | 2025-03-11 | 275 | 3463.3784 | 3878.9838 | 859284.5448 | 980711.2502
[17 empty] | 116 | 2025-03-12 | 276 | 3463.3784 | 3878.9838 | 862747.9232 | 984590.234
[17 empty] | 116 | 2025-03-13 | 277 | 3463.3784 | 3878.9838 | 866211.3016 | 988469.2178
[17 empty] | 116 | 2025-03-14 | 278 | 3463.3784 | 3878.9838 | 869674.68 | 992348.2016
[17 empty] | 116 | 2025-03-15 | 279 | 0 | 0 | 869674.68 | 992348.2016
[17 empty] | 116 | 2025-03-16 | 280 | 0 | 0 | 869674.68 | 992348.2016
[17 empty] | 116 | 2025-03-17 | 281 | 3463.3784 | 3878.9838 | 873138.0584 | 996227.1854
[17 empty] | 116 | 2025-03-18 | 282 | 3463.3784 | 3878.9838 | 876601.4368 | 1000106.1692
[17 empty] | 116 | 2025-03-19 | 283 | 3463.3784 | 3878.9838 | 880064.8152 | 1003985.153
[17 empty] | 116 | 2025-03-20 | 284 | 3463.3784 | 3878.9838 | 883528.1936 | 1007864.1368
[17 empty] | 116 | 2025-03-21 | 285 | 3463.3784 | 3878.9838 | 886991.572 | 1011743.1206
[17 empty] | 116 | 2025-03-22 | 286 | 0 | 0 | 886991.572 | 1011743.1206
[17 empty] | 116 | 2025-03-23 | 287 | 0 | 0 | 886991.572 | 1011743.1206
[17 empty] | 116 | 2025-03-24 | 288 | 3463.3784 | 3878.9838 | 890454.9504 | 1015622.1044
[17 empty] | 116 | 2025-03-25 | 289 | 3463.3784 | 3878.9838 | 893918.3288 | 1019501.0883
[17 empty] | 116 | 2025-03-26 | 290 | 3463.3784 | 3878.9838 | 897381.7072 | 1023380.0721
[17 empty] | 116 | 2025-03-27 | 291 | 3463.3784 | 3878.9838 | 900845.0856 | 1027259.0559
[17 empty] | 116 | 2025-03-28 | 292 | 3463.3784 | 3878.9838 | 904308.464 | 1031138.0397
[17 empty] | 116 | 2025-03-29 | 293 | 0 | 0 | 904308.464 | 1031138.0397
[17 empty] | 116 | 2025-03-30 | 294 | 0 | 0 | 904308.464 | 1031138.0397
[17 empty] | 116 | 2025-03-31 | 295 | 3463.3784 | 3878.9838 | 907771.8424 | 1035017.0235
[17 empty] | 116 | 2025-04-01 | 296 | 3463.3784 | 3878.9838 | 911235.2208 | 1038896.0073
[17 empty] | 116 | 2025-04-02 | 297 | 3463.3784 | 3878.9838 | 914698.5992 | 1042774.9911
[17 empty] | 116 | 2025-04-03 | 298 | 3463.3784 | 3878.9838 | 918161.9776 | 1046653.9749
[17 empty] | 116 | 2025-04-04 | 299 | 3463.3784 | 3878.9838 | 921625.356 | 1050532.9587
[17 empty] | 116 | 2025-04-05 | 300 | 0 | 0 | 921625.356 | 1050532.9587
[17 empty] | 116 | 2025-04-06 | 301 | 0 | 0 | 921625.356 | 1050532.9587
[17 empty] | 116 | 2025-04-07 | 302 | 3463.3784 | 3878.9838 | 925088.7344 | 1054411.9425
[17 empty] | 116 | 2025-04-08 | 303 | 3463.3784 | 3878.9838 | 928552.1128 | 1058290.9263
[17 empty] | 116 | 2025-04-09 | 304 | 3463.3784 | 3878.9838 | 932015.4912 | 1062169.9101
[17 empty] | 116 | 2025-04-10 | 305 | 3463.3784 | 3878.9838 | 935478.8696 | 1066048.894
[17 empty] | 116 | 2025-04-11 | 306 | 3463.3784 | 3878.9838 | 938942.248 | 1069927.8778
[17 empty] | 116 | 2025-04-12 | 307 | 0 | 0 | 938942.248 | 1069927.8778
[17 empty] | 116 | 2025-04-13 | 308 | 0 | 0 | 938942.248 | 1069927.8778
[17 empty] | 116 | 2025-04-14 | 309 | 3463.3784 | 3878.9838 | 942405.6264 | 1073806.8616
[17 empty] | 116 | 2025-04-15 | 310 | 3463.3784 | 3878.9838 | 945869.0048 | 1077685.8454
[17 empty] | 116 | 2025-04-16 | 311 | 3463.3784 | 3878.9838 | 949332.3832 | 1081564.8292
[17 empty] | 116 | 2025-04-17 | 312 | 3463.3784 | 3878.9838 | 952795.7616 | 1085443.813
[17 empty] | 116 | 2025-04-18 | 313 | 3463.3784 | 3878.9838 | 956259.14 | 1089322.7968
[17 empty] | 116 | 2025-04-19 | 314 | 0 | 0 | 956259.14 | 1089322.7968
[17 empty] | 116 | 2025-04-20 | 315 | 0 | 0 | 956259.14 | 1089322.7968
[17 empty] | 116 | 2025-04-21 | 316 | 3463.3784 | 3878.9838 | 959722.5184 | 1093201.7806
[17 empty] | 116 | 2025-04-22 | 317 | 3463.3784 | 3878.9838 | 963185.8968 | 1097080.7644
[17 empty] | 116 | 2025-04-23 | 318 | 3463.3784 | 3878.9838 | 966649.2752 | 1100959.7482
[17 empty] | 116 | 2025-04-24 | 319 | 3463.3784 | 3878.9838 | 970112.6536 | 1104838.732
[17 empty] | 116 | 2025-04-25 | 320 | 3463.3784 | 3878.9838 | 973576.032 | 1108717.7158
[17 empty] | 116 | 2025-04-26 | 321 | 0 | 0 | 973576.032 | 1108717.7158
[17 empty] | 116 | 2025-04-27 | 322 | 0 | 0 | 973576.032 | 1108717.7158
[17 empty] | 116 | 2025-04-28 | 323 | 3463.3784 | 3878.9838 | 977039.4104 | 1112596.6996
[17 empty] | 116 | 2025-04-29 | 324 | 3463.3784 | 3878.9838 | 980502.7888 | 1116475.6835
[17 empty] | 116 | 2025-04-30 | 325 | 3463.3784 | 3878.9838 | 983966.1672 | 1120354.6673
[17 empty] | 116 | 2025-05-01 | 326 | 3463.3784 | 3878.9838 | 987429.5456 | 1124233.6511
[17 empty] | 116 | 2025-05-02 | 327 | 3463.3784 | 3878.9838 | 990892.924 | 1128112.6349
[17 empty] | 116 | 2025-05-03 | 328 | 0 | 0 | 990892.924 | 1128112.6349
[17 empty] | 116 | 2025-05-04 | 329 | 0 | 0 | 990892.924 | 1128112.6349
[17 empty] | 116 | 2025-05-05 | 330 | 3463.3784 | 3878.9838 | 994356.3024 | 1131991.6187
[17 empty] | 116 | 2025-05-06 | 331 | 3463.3784 | 3878.9838 | 997819.6808 | 1135870.6025
[17 empty] | 116 | 2025-05-07 | 332 | 3463.3784 | 3878.9838 | 1001283.0592 | 1139749.5863
[17 empty] | 116 | 2025-05-08 | 333 | 3463.3784 | 3878.9838 | 1004746.4376 | 1143628.5701
[17 empty] | 116 | 2025-05-09 | 334 | 3463.3784 | 3878.9838 | 1008209.816 | 1147507.5539
[17 empty] | 116 | 2025-05-10 | 335 | 0 | 0 | 1008209.816 | 1147507.5539
[17 empty] | 116 | 2025-05-11 | 336 | 0 | 0 | 1008209.816 | 1147507.5539
[17 empty] | 116 | 2025-05-12 | 337 | 3463.3784 | 3878.9838 | 1011673.1944 | 1151386.5377
[17 empty] | 116 | 2025-05-13 | 338 | 3463.3784 | 3878.9838 | 1015136.5728 | 1155265.5215
[17 empty] | 116 | 2025-05-14 | 339 | 3463.3784 | 3878.9838 | 1018599.9512 | 1159144.5053
[17 empty] | 116 | 2025-05-15 | 340 | 3463.3784 | 3878.9838 | 1022063.3296 | 1163023.4892
[17 empty] | 116 | 2025-05-16 | 341 | 3463.3784 | 3878.9838 | 1025526.708 | 1166902.473
[17 empty] | 116 | 2025-05-17 | 342 | 0 | 0 | 1025526.708 | 1166902.473
[17 empty] | 116 | 2025-05-18 | 343 | 0 | 0 | 1025526.708 | 1166902.473
[17 empty] | 116 | 2025-05-19 | 344 | 3463.3784 | 3878.9838 | 1028990.0864 | 1170781.4568
[17 empty] | 116 | 2025-05-20 | 345 | 3463.3784 | 3878.9838 | 1032453.4648 | 1174660.4406
[17 empty] | 116 | 2025-05-21 | 346 | 3463.3784 | 3878.9838 | 1035916.8432 | 1178539.4244
[17 empty] | 116 | 2025-05-22 | 347 | 3463.3784 | 3878.9838 | 1039380.2216 | 1182418.4082
[17 empty] | 116 | 2025-05-23 | 348 | 3463.3784 | 3878.9838 | 1042843.6 | 1186297.392
[17 empty] | 116 | 2025-05-24 | 349 | 0 | 0 | 1042843.6 | 1186297.392
[17 empty] | 116 | 2025-05-25 | 350 | 0 | 0 | 1042843.6 | 1186297.392
[17 empty] | 116 | 2025-05-26 | 351 | 3463.3784 | 3878.9838 | 1046306.9784 | 1190176.3758
[17 empty] | 116 | 2025-05-27 | 352 | 3463.3784 | 3878.9838 | 1049770.3568 | 1194055.3596
[17 empty] | 116 | 2025-05-28 | 353 | 3463.3784 | 3878.9838 | 1053233.7352 | 1197934.3434
[17 empty] | 116 | 2025-05-29 | 354 | 3463.3784 | 3878.9838 | 1056697.1136 | 1201813.3272
[17 empty] | 116 | 2025-05-30 | 355 | 3463.3784 | 3878.9838 | 1060160.492 | 1205692.311
[17 empty] | 116 | 2025-05-31 | 356 | 0 | 0 | 1060160.492 | 1205692.311
[17 empty] | 116 | 2025-06-01 | 357 | 0 | 0 | 1060160.492 | 1205692.311
[17 empty] | 116 | 2025-06-02 | 358 | 3463.3784 | 3878.9838 | 1063623.8704 | 1209571.2948
[17 empty] | 116 | 2025-06-03 | 359 | 3463.3784 | 3878.9838 | 1067087.2488 | 1213450.2787
[17 empty] | 116 | 2025-06-04 | 360 | 3463.3784 | 3878.9838 | 1070550.6272 | 1217329.2625
[17 empty] | 116 | 2025-06-05 | 361 | 3463.3784 | 3878.9838 | 1074014.0056 | 1221208.2463
[17 empty] | 116 | 2025-06-06 | 362 | 3463.3784 | 3878.9838 | 1077477.384 | 1225087.2301
[17 empty] | 116 | 2025-06-07 | 363 | 0 | 0 | 1077477.384 | 1225087.2301
[17 empty] | 116 | 2025-06-08 | 364 | 0 | 0 | 1077477.384 | 1225087.2301
[17 empty] | 116 | 2025-06-09 | 365 | 3463.3784 | 3878.9838 | 1080940.7624 | 1228966.2139
[17 empty] | 116 | 2025-06-10 | 366 | 3463.3784 | 3878.9838 | 1084404.1408 | 1232845.1977
[17 empty] | 116 | 2025-06-11 | 367 | 3463.3784 | 3878.9838 | 1087867.5192 | 1236724.1815
[17 empty] | 116 | 2025-06-12 | 368 | 3463.3784 | 3878.9838 | 1091330.8976 | 1240603.1653
[17 empty] | 116 | 2025-06-13 | 369 | 3463.3784 | 3878.9838 | 1094794.276 | 1244482.1491
[17 empty] | 116 | 2025-06-14 | 370 | 0 | 0 | 1094794.276 | 1244482.1491
[17 empty] | 116 | 2025-06-15 | 371 | 0 | 0 | 1094794.276 | 1244482.1491
[17 empty] | 116 | 2025-06-16 | 372 | 3463.3784 | 3878.9838 | 1098257.6544 | 1248361.1329
[17 empty] | 116 | 2025-06-17 | 373 | 3463.3784 | 3878.9838 | 1101721.0328 | 1252240.1167
[17 empty] | 116 | 2025-06-18 | 374 | 3463.3784 | 3878.9838 | 1105184.4112 | 1256119.1005
[17 empty] | 116 | 2025-06-19 | 375 | 3463.3784 | 3878.9838 | 1108647.7896 | 1259998.0844
[17 empty] | 116 | 2025-06-20 | 376 | 400.3784 | 448.4238 | 1109048.168 | 1260446.5082
[17 empty] | 116 | 2025-06-21 | 377 | 0 | 0 | 1109048.168 | 1260446.5082
[17 empty] | 116 | 2025-06-22 | 378 | 0 | 0 | 1109048.168 | 1260446.5082
[17 empty] | 116 | 2025-06-23 | 379 | 400.3784 | 448.4238 | 1109448.5464 | 1260894.932
[17 empty] | 116 | 2025-06-24 | 380 | 400.3784 | 448.4238 | 1109848.9248 | 1261343.3558
[17 empty] | 116 | 2025-06-25 | 381 | 400.3784 | 448.4238 | 1110249.3032 | 1261791.7796
[17 empty] | 116 | 2025-06-26 | 382 | 400.3784 | 448.4238 | 1110649.6816 | 1262240.2034
[17 empty] | 116 | 2025-06-27 | 383 | 400.3784 | 448.4238 | 1111050.06 | 1262688.6272
[17 empty] | 116 | 2025-06-28 | 384 | 0 | 0 | 1111050.06 | 1262688.6272
[17 empty] | 116 | 2025-06-29 | 385 | 0 | 0 | 1111050.06 | 1262688.6272
[17 empty] | 117 | 2024-06-18 | 1 | 285.4583 | 339.6954 | 285.4583 | 339.6954
[17 empty] | 117 | 2024-06-19 | 2 | 285.4583 | 339.6954 | 570.9166 | 679.3908
[17 empty] | 117 | 2024-06-20 | 3 | 285.4583 | 339.6954 | 856.3749 | 1019.0861
[17 empty] | 117 | 2024-06-21 | 4 | 285.4583 | 339.6954 | 1141.8332 | 1358.7815
[17 empty] | 117 | 2024-06-22 | 5 | 0 | 0 | 1141.8332 | 1358.7815
[17 empty] | 117 | 2024-06-23 | 6 | 0 | 0 | 1141.8332 | 1358.7815
[17 empty] | 117 | 2024-06-24 | 7 | 2389.4583 | 2822.4154 | 3531.2915 | 4181.1969
[17 empty] | 117 | 2024-06-25 | 8 | 2389.4583 | 2822.4154 | 5920.7498 | 7003.6123
[17 empty] | 117 | 2024-06-26 | 9 | 2389.4583 | 2822.4154 | 8310.2081 | 9826.0277
[17 empty] | 117 | 2024-06-27 | 10 | 2389.4583 | 2822.4154 | 10699.6664 | 12648.443
[17 empty] | 117 | 2024-06-28 | 11 | 2389.4583 | 2822.4154 | 13089.1247 | 15470.8584
[17 empty] | 117 | 2024-06-29 | 12 | 0 | 0 | 13089.1247 | 15470.8584
[17 empty] | 117 | 2024-06-30 | 13 | 0 | 0 | 13089.1247 | 15470.8584
[17 empty] | 117 | 2024-07-01 | 14 | 2389.4583 | 2822.4154 | 15478.583 | 18293.2738
[17 empty] | 117 | 2024-07-02 | 15 | 2389.4583 | 2822.4154 | 17868.0413 | 21115.6892
[17 empty] | 117 | 2024-07-03 | 16 | 2389.4583 | 2822.4154 | 20257.4996 | 23938.1046
[17 empty] | 117 | 2024-07-04 | 17 | 2389.4583 | 2822.4154 | 22646.9579 | 26760.52
[17 empty] | 117 | 2024-07-05 | 18 | 2389.4583 | 2822.4154 | 25036.4162 | 29582.9353
[17 empty] | 117 | 2024-07-06 | 19 | 0 | 0 | 25036.4162 | 29582.9353
[17 empty] | 117 | 2024-07-07 | 20 | 0 | 0 | 25036.4162 | 29582.9353
[17 empty] | 117 | 2024-07-08 | 21 | 2389.4583 | 2822.4154 | 27425.8746 | 32405.3507
[17 empty] | 117 | 2024-07-09 | 22 | 2389.4583 | 2822.4154 | 29815.3329 | 35227.7661
[17 empty] | 117 | 2024-07-10 | 23 | 2389.4583 | 2822.4154 | 32204.7912 | 38050.1815
[17 empty] | 117 | 2024-07-11 | 24 | 2389.4583 | 2822.4154 | 34594.2495 | 40872.5969
[17 empty] | 117 | 2024-07-12 | 25 | 2389.4583 | 2822.4154 | 36983.7078 | 43695.0122
[17 empty] | 117 | 2024-07-13 | 26 | 0 | 0 | 36983.7078 | 43695.0122
[17 empty] | 117 | 2024-07-14 | 27 | 0 | 0 | 36983.7078 | 43695.0122
[17 empty] | 117 | 2024-07-15 | 28 | 2389.4583 | 2822.4154 | 39373.1661 | 46517.4276
[17 empty] | 117 | 2024-07-16 | 29 | 2389.4583 | 2822.4154 | 41762.6244 | 49339.843
[17 empty] | 117 | 2024-07-17 | 30 | 2389.4583 | 2822.4154 | 44152.0827 | 52162.2584
[17 empty] | 117 | 2024-07-18 | 31 | 2389.4583 | 2822.4154 | 46541.541 | 54984.6738
[17 empty] | 117 | 2024-07-19 | 32 | 2389.4583 | 2822.4154 | 48930.9993 | 57807.0892
[17 empty] | 117 | 2024-07-20 | 33 | 0 | 0 | 48930.9993 | 57807.0892
[17 empty] | 117 | 2024-07-21 | 34 | 0 | 0 | 48930.9993 | 57807.0892
[17 empty] | 117 | 2024-07-22 | 35 | 2389.4583 | 2822.4154 | 51320.4576 | 60629.5045
[17 empty] | 117 | 2024-07-23 | 36 | 2389.4583 | 2822.4154 | 53709.9159 | 63451.9199
[17 empty] | 117 | 2024-07-24 | 37 | 2389.4583 | 2822.4154 | 56099.3742 | 66274.3353
[17 empty] | 117 | 2024-07-25 | 38 | 2389.4583 | 2822.4154 | 58488.8325 | 69096.7507
[17 empty] | 117 | 2024-07-26 | 39 | 2389.4583 | 2822.4154 | 60878.2908 | 71919.1661
[17 empty] | 117 | 2024-07-27 | 40 | 0 | 0 | 60878.2908 | 71919.1661
[17 empty] | 117 | 2024-07-28 | 41 | 0 | 0 | 60878.2908 | 71919.1661
[17 empty] | 117 | 2024-07-29 | 42 | 2389.4583 | 2822.4154 | 63267.7491 | 74741.5814
[17 empty] | 117 | 2024-07-30 | 43 | 2389.4583 | 2822.4154 | 65657.2074 | 77563.9968
[17 empty] | 117 | 2024-07-31 | 44 | 2389.4583 | 2822.4154 | 68046.6657 | 80386.4122
[17 empty] | 117 | 2024-08-01 | 45 | 2389.4583 | 2822.4154 | 70436.124 | 83208.8276
[17 empty] | 117 | 2024-08-02 | 46 | 3994.0846 | 4635.6431 | 74430.2086 | 87844.4706
[17 empty] | 117 | 2024-08-03 | 47 | 0 | 0 | 74430.2086 | 87844.4706
[17 empty] | 117 | 2024-08-04 | 48 | 0 | 0 | 74430.2086 | 87844.4706
[17 empty] | 117 | 2024-08-05 | 49 | 1890.0846 | 2152.9231 | 76320.2932 | 89997.3937
[17 empty] | 117 | 2024-08-06 | 50 | 1890.0846 | 2152.9231 | 78210.3777 | 92150.3168
[17 empty] | 117 | 2024-08-07 | 51 | 1890.0846 | 2152.9231 | 80100.4623 | 94303.2398
[17 empty] | 117 | 2024-08-08 | 52 | 1890.0846 | 2152.9231 | 81990.5468 | 96456.1629
[17 empty] | 117 | 2024-08-09 | 53 | 1890.0846 | 2152.9231 | 83880.6314 | 98609.0859
[17 empty] | 117 | 2024-08-10 | 54 | 0 | 0 | 83880.6314 | 98609.0859
[17 empty] | 117 | 2024-08-11 | 55 | 0 | 0 | 83880.6314 | 98609.0859
[17 empty] | 117 | 2024-08-12 | 56 | 1890.0846 | 2152.9231 | 85770.716 | 100762.009
[17 empty] | 117 | 2024-08-13 | 57 | 1890.0846 | 2152.9231 | 87660.8005 | 102914.932
[17 empty] | 117 | 2024-08-14 | 58 | 1890.0846 | 2152.9231 | 89550.8851 | 105067.8551
[17 empty] | 117 | 2024-08-15 | 59 | 1890.0846 | 2152.9231 | 91440.9697 | 107220.7782
[17 empty] | 117 | 2024-08-16 | 60 | 1890.0846 | 2152.9231 | 93331.0542 | 109373.7012
[17 empty] | 117 | 2024-08-17 | 61 | 0 | 0 | 93331.0542 | 109373.7012
[17 empty] | 117 | 2024-08-18 | 62 | 0 | 0 | 93331.0542 | 109373.7012
[17 empty] | 117 | 2024-08-19 | 63 | 1890.0846 | 2152.9231 | 95221.1388 | 111526.6243
[17 empty] | 117 | 2024-08-20 | 64 | 1890.0846 | 2152.9231 | 97111.2234 | 113679.5473
[17 empty] | 117 | 2024-08-21 | 65 | 1890.0846 | 2152.9231 | 99001.3079 | 115832.4704
[17 empty] | 117 | 2024-08-22 | 66 | 1890.0846 | 2152.9231 | 100891.3925 | 117985.3935
[17 empty] | 117 | 2024-08-23 | 67 | 1890.0846 | 2152.9231 | 102781.4771 | 120138.3165
[17 empty] | 117 | 2024-08-24 | 68 | 0 | 0 | 102781.4771 | 120138.3165
[17 empty] | 117 | 2024-08-25 | 69 | 0 | 0 | 102781.4771 | 120138.3165
[17 empty] | 117 | 2024-08-26 | 70 | 1890.0846 | 2152.9231 | 104671.5616 | 122291.2396
[17 empty] | 117 | 2024-08-27 | 71 | 1890.0846 | 2152.9231 | 106561.6462 | 124444.1626
[17 empty] | 117 | 2024-08-28 | 72 | 1890.0846 | 2152.9231 | 108451.7308 | 126597.0857
[17 empty] | 117 | 2024-08-29 | 73 | 1890.0846 | 2152.9231 | 110341.8153 | 128750.0087
[17 empty] | 117 | 2024-08-30 | 74 | 1890.0846 | 2152.9231 | 112231.8999 | 130902.9318
[17 empty] | 117 | 2024-08-31 | 75 | 0 | 0 | 112231.8999 | 130902.9318
[17 empty] | 117 | 2024-09-01 | 76 | 0 | 0 | 112231.8999 | 130902.9318
[17 empty] | 117 | 2024-09-02 | 77 | 1890.0846 | 2152.9231 | 114121.9845 | 133055.8549
[17 empty] | 117 | 2024-09-03 | 78 | 1890.0846 | 2152.9231 | 116012.069 | 135208.7779
[17 empty] | 117 | 2024-09-04 | 79 | 1890.0846 | 2152.9231 | 117902.1536 | 137361.701
[17 empty] | 117 | 2024-09-05 | 80 | 1890.0846 | 2152.9231 | 119792.2382 | 139514.624
[17 empty] | 117 | 2024-09-06 | 81 | 1890.0846 | 2152.9231 | 121682.3227 | 141667.5471
[17 empty] | 117 | 2024-09-07 | 82 | 0 | 0 | 121682.3227 | 141667.5471
[17 empty] | 117 | 2024-09-08 | 83 | 0 | 0 | 121682.3227 | 141667.5471
[17 empty] | 117 | 2024-09-09 | 84 | 1890.0846 | 2152.9231 | 123572.4073 | 143820.4701
[17 empty] | 117 | 2024-09-10 | 85 | 1890.0846 | 2152.9231 | 125462.4919 | 145973.3932
[17 empty] | 117 | 2024-09-11 | 86 | 1890.0846 | 2152.9231 | 127352.5764 | 148126.3163
[17 empty] | 117 | 2024-09-12 | 87 | 1890.0846 | 2152.9231 | 129242.661 | 150279.2393
[17 empty] | 117 | 2024-09-13 | 88 | 1890.0846 | 2152.9231 | 131132.7456 | 152432.1624
[17 empty] | 117 | 2024-09-14 | 89 | 0 | 0 | 131132.7456 | 152432.1624
[17 empty] | 117 | 2024-09-15 | 90 | 0 | 0 | 131132.7456 | 152432.1624
[17 empty] | 117 | 2024-09-16 | 91 | 1890.0846 | 2152.9231 | 133022.8301 | 154585.0854
[17 empty] | 117 | 2024-09-17 | 92 | 1890.0846 | 2152.9231 | 134912.9147 | 156738.0085
[17 empty] | 117 | 2024-09-18 | 93 | 1890.0846 | 2152.9231 | 136802.9993 | 158890.9316
[17 empty] | 117 | 2024-09-19 | 94 | 1890.0846 | 2152.9231 | 138693.0838 | 161043.8546
[17 empty] | 117 | 2024-09-20 | 95 | 1890.0846 | 2152.9231 | 140583.1684 | 163196.7777
[17 empty] | 117 | 2024-09-21 | 96 | 0 | 0 | 140583.1684 | 163196.7777
[17 empty] | 117 | 2024-09-22 | 97 | 0 | 0 | 140583.1684 | 163196.7777
[17 empty] | 117 | 2024-09-23 | 98 | 1890.0846 | 2152.9231 | 142473.253 | 165349.7007
[17 empty] | 117 | 2024-09-24 | 99 | 1890.0846 | 2152.9231 | 144363.3375 | 167502.6238
[17 empty] | 117 | 2024-09-25 | 100 | 1890.0846 | 2152.9231 | 146253.4221 | 169655.5468
[17 empty] | 117 | 2024-09-26 | 101 | 1890.0846 | 2152.9231 | 148143.5067 | 171808.4699
[17 empty] | 117 | 2024-09-27 | 102 | 1890.0846 | 2152.9231 | 150033.5912 | 173961.393
[17 empty] | 117 | 2024-09-28 | 103 | 0 | 0 | 150033.5912 | 173961.393
[17 empty] | 117 | 2024-09-29 | 104 | 0 | 0 | 150033.5912 | 173961.393
[17 empty] | 117 | 2024-09-30 | 105 | 1890.0846 | 2152.9231 | 151923.6758 | 176114.316
[17 empty] | 117 | 2024-10-01 | 106 | 1890.0846 | 2152.9231 | 153813.7604 | 178267.2391
[17 empty] | 117 | 2024-10-02 | 107 | 1890.0846 | 2152.9231 | 155703.8449 | 180420.1621
[17 empty] | 117 | 2024-10-03 | 108 | 1890.0846 | 2152.9231 | 157593.9295 | 182573.0852
[17 empty] | 117 | 2024-10-04 | 109 | 1890.0846 | 2152.9231 | 159484.0141 | 184726.0083
[17 empty] | 117 | 2024-10-05 | 110 | 0 | 0 | 159484.0141 | 184726.0083
[17 empty] | 117 | 2024-10-06 | 111 | 0 | 0 | 159484.0141 | 184726.0083
[17 empty] | 117 | 2024-10-07 | 112 | 1890.0846 | 2152.9231 | 161374.0986 | 186878.9313
[17 empty] | 117 | 2024-10-08 | 113 | 1890.0846 | 2152.9231 | 163264.1832 | 189031.8544
[17 empty] | 117 | 2024-10-09 | 114 | 1890.0846 | 2152.9231 | 165154.2678 | 191184.7774
[17 empty] | 117 | 2024-10-10 | 115 | 1890.0846 | 2152.9231 | 167044.3523 | 193337.7005
[17 empty] | 117 | 2024-10-11 | 116 | 1890.0846 | 2152.9231 | 168934.4369 | 195490.6235
[17 empty] | 117 | 2024-10-12 | 117 | 0 | 0 | 168934.4369 | 195490.6235
[17 empty] | 117 | 2024-10-13 | 118 | 0 | 0 | 168934.4369 | 195490.6235
[17 empty] | 117 | 2024-10-14 | 119 | 1890.0846 | 2152.9231 | 170824.5215 | 197643.5466
[17 empty] | 117 | 2024-10-15 | 120 | 1890.0846 | 2152.9231 | 172714.606 | 199796.4697
[17 empty] | 117 | 2024-10-16 | 121 | 1890.0846 | 2152.9231 | 174604.6906 | 201949.3927
[17 empty] | 117 | 2024-10-17 | 122 | 1890.0846 | 2152.9231 | 176494.7752 | 204102.3158
[17 empty] | 117 | 2024-10-18 | 123 | 1890.0846 | 2152.9231 | 178384.8597 | 206255.2388
[17 empty] | 117 | 2024-10-19 | 124 | 0 | 0 | 178384.8597 | 206255.2388
[17 empty] | 117 | 2024-10-20 | 125 | 0 | 0 | 178384.8597 | 206255.2388
[17 empty] | 117 | 2024-10-21 | 126 | 1890.0846 | 2152.9231 | 180274.9443 | 208408.1619
[17 empty] | 117 | 2024-10-22 | 127 | 1890.0846 | 2152.9231 | 182165.0289 | 210561.0849
[17 empty] | 117 | 2024-10-23 | 128 | 1890.0846 | 2152.9231 | 184055.1134 | 212714.008
[17 empty] | 117 | 2024-10-24 | 129 | 1890.0846 | 2152.9231 | 185945.198 | 214866.9311
[17 empty] | 117 | 2024-10-25 | 130 | 1890.0846 | 2152.9231 | 187835.2826 | 217019.8541
[17 empty] | 117 | 2024-10-26 | 131 | 0 | 0 | 187835.2826 | 217019.8541
[17 empty] | 117 | 2024-10-27 | 132 | 0 | 0 | 187835.2826 | 217019.8541
[17 empty] | 117 | 2024-10-28 | 133 | 1890.0846 | 2152.9231 | 189725.3671 | 219172.7772
[17 empty] | 117 | 2024-10-29 | 134 | 1890.0846 | 2152.9231 | 191615.4517 | 221325.7002
[17 empty] | 117 | 2024-10-30 | 135 | 1890.0846 | 2152.9231 | 193505.5363 | 223478.6233
[17 empty] | 117 | 2024-10-31 | 136 | 1890.0846 | 2152.9231 | 195395.6208 | 225631.5464
[17 empty] | 117 | 2024-11-01 | 137 | 1890.0846 | 2152.9231 | 197285.7054 | 227784.4694
[17 empty] | 117 | 2024-11-02 | 138 | 0 | 0 | 197285.7054 | 227784.4694
[17 empty] | 117 | 2024-11-03 | 139 | 0 | 0 | 197285.7054 | 227784.4694
[17 empty] | 117 | 2024-11-04 | 140 | 1890.0846 | 2152.9231 | 199175.79 | 229937.3925
[17 empty] | 117 | 2024-11-05 | 141 | 1890.0846 | 2152.9231 | 201065.8745 | 232090.3155
[17 empty] | 117 | 2024-11-06 | 142 | 1890.0846 | 2152.9231 | 202955.9591 | 234243.2386
[17 empty] | 117 | 2024-11-07 | 143 | 1890.0846 | 2152.9231 | 204846.0437 | 236396.1616
[17 empty] | 117 | 2024-11-08 | 144 | 1890.0846 | 2152.9231 | 206736.1282 | 238549.0847
[17 empty] | 117 | 2024-11-09 | 145 | 0 | 0 | 206736.1282 | 238549.0847
[17 empty] | 117 | 2024-11-10 | 146 | 0 | 0 | 206736.1282 | 238549.0847
[17 empty] | 117 | 2024-11-11 | 147 | 1890.0846 | 2152.9231 | 208626.2128 | 240702.0078
[17 empty] | 117 | 2024-11-12 | 148 | 1890.0846 | 2152.9231 | 210516.2974 | 242854.9308
[17 empty] | 117 | 2024-11-13 | 149 | 1890.0846 | 2152.9231 | 212406.3819 | 245007.8539
[17 empty] | 117 | 2024-11-14 | 150 | 1890.0846 | 2152.9231 | 214296.4665 | 247160.7769
[17 empty] | 117 | 2024-11-15 | 151 | 1890.0846 | 2152.9231 | 216186.551 | 249313.7
[17 empty] | 117 | 2024-11-16 | 152 | 0 | 0 | 216186.551 | 249313.7
[17 empty] | 117 | 2024-11-17 | 153 | 0 | 0 | 216186.551 | 249313.7
[17 empty] | 117 | 2024-11-18 | 154 | 1890.0846 | 2152.9231 | 218076.6356 | 251466.623
[17 empty] | 117 | 2024-11-19 | 155 | 1890.0846 | 2152.9231 | 219966.7202 | 253619.5461
[17 empty] | 117 | 2024-11-20 | 156 | 1890.0846 | 2152.9231 | 221856.8047 | 255772.4692
[17 empty] | 117 | 2024-11-21 | 157 | 1890.0846 | 2152.9231 | 223746.8893 | 257925.3922
[17 empty] | 117 | 2024-11-22 | 158 | 1890.0846 | 2152.9231 | 225636.9739 | 260078.3153
[17 empty] | 117 | 2024-11-23 | 159 | 0 | 0 | 225636.9739 | 260078.3153
[17 empty] | 117 | 2024-11-24 | 160 | 0 | 0 | 225636.9739 | 260078.3153
[17 empty] | 117 | 2024-11-25 | 161 | 1890.0846 | 2152.9231 | 227527.0584 | 262231.2383
[17 empty] | 117 | 2024-11-26 | 162 | 1890.0846 | 2152.9231 | 229417.143 | 264384.1614
[17 empty] | 117 | 2024-11-27 | 163 | 1890.0846 | 2152.9231 | 231307.2276 | 266537.0845
[17 empty] | 117 | 2024-11-28 | 164 | 5975.7989 | 6728.9231 | 237283.0264 | 273266.0075
[17 empty] | 117 | 2024-11-29 | 165 | 5975.7989 | 6728.9231 | 243258.8253 | 279994.9306
[17 empty] | 117 | 2024-11-30 | 166 | 0 | 0 | 243258.8253 | 279994.9306
[17 empty] | 117 | 2024-12-01 | 167 | 0 | 0 | 243258.8253 | 279994.9306
[17 empty] | 117 | 2024-12-02 | 168 | 5975.7989 | 6728.9231 | 249234.6241 | 286723.8536
[17 empty] | 117 | 2024-12-03 | 169 | 5975.7989 | 6728.9231 | 255210.423 | 293452.7767
[17 empty] | 117 | 2024-12-04 | 170 | 5975.7989 | 6728.9231 | 261186.2218 | 300181.6997
[17 empty] | 117 | 2024-12-05 | 171 | 5975.7989 | 6728.9231 | 267162.0207 | 306910.6228
[17 empty] | 117 | 2024-12-06 | 172 | 5975.7989 | 6728.9231 | 273137.8195 | 313639.5459
[17 empty] | 117 | 2024-12-07 | 173 | 0 | 0 | 273137.8195 | 313639.5459
[17 empty] | 117 | 2024-12-08 | 174 | 0 | 0 | 273137.8195 | 313639.5459
[17 empty] | 117 | 2024-12-09 | 175 | 10259.7989 | 12169.6031 | 283397.6184 | 325809.1489
[17 empty] | 117 | 2024-12-10 | 176 | 10259.7989 | 12169.6031 | 293657.4172 | 337978.752
[17 empty] | 117 | 2024-12-11 | 177 | 10259.7989 | 12169.6031 | 303917.2161 | 350148.355
[17 empty] | 117 | 2024-12-12 | 178 | 10259.7989 | 12169.6031 | 314177.0149 | 362317.9581
[17 empty] | 117 | 2024-12-13 | 179 | 10259.7989 | 12169.6031 | 324436.8138 | 374487.5612
[17 empty] | 117 | 2024-12-14 | 180 | 0 | 0 | 324436.8138 | 374487.5612
[17 empty] | 117 | 2024-12-15 | 181 | 0 | 0 | 324436.8138 | 374487.5612
[17 empty] | 117 | 2024-12-16 | 182 | 10259.7989 | 12169.6031 | 334696.6127 | 386657.1642
[17 empty] | 117 | 2024-12-17 | 183 | 10259.7989 | 12169.6031 | 344956.4115 | 398826.7673
[17 empty] | 117 | 2024-12-18 | 184 | 10259.7989 | 12169.6031 | 355216.2104 | 410996.3703
[17 empty] | 117 | 2024-12-19 | 185 | 8655.1726 | 10356.3754 | 363871.3829 | 421352.7457
[17 empty] | 117 | 2024-12-20 | 186 | 8655.1726 | 10356.3754 | 372526.5555 | 431709.1211
[17 empty] | 117 | 2024-12-21 | 187 | 0 | 0 | 372526.5555 | 431709.1211
[17 empty] | 117 | 2024-12-22 | 188 | 0 | 0 | 372526.5555 | 431709.1211
[17 empty] | 117 | 2024-12-23 | 189 | 8655.1726 | 10356.3754 | 381181.7281 | 442065.4965
[17 empty] | 117 | 2024-12-24 | 190 | 8655.1726 | 10356.3754 | 389836.9007 | 452421.8719
[17 empty] | 117 | 2024-12-25 | 191 | 8655.1726 | 10356.3754 | 398492.0733 | 462778.2472
[17 empty] | 117 | 2024-12-26 | 192 | 8655.1726 | 10356.3754 | 407147.2459 | 473134.6226
[17 empty] | 117 | 2024-12-27 | 193 | 4569.4583 | 5780.3754 | 411716.7042 | 478914.998
[17 empty] | 117 | 2024-12-28 | 194 | 0 | 0 | 411716.7042 | 478914.998
[17 empty] | 117 | 2024-12-29 | 195 | 0 | 0 | 411716.7042 | 478914.998
[17 empty] | 117 | 2024-12-30 | 196 | 4569.4583 | 5780.3754 | 416286.1625 | 484695.3734
[17 empty] | 117 | 2024-12-31 | 197 | 4569.4583 | 5780.3754 | 420855.6208 | 490475.7488
[17 empty] | 117 | 2025-01-01 | 198 | 4569.4583 | 5780.3754 | 425425.0791 | 496256.1241
[17 empty] | 117 | 2025-01-02 | 199 | 4569.4583 | 5780.3754 | 429994.5374 | 502036.4995
[17 empty] | 117 | 2025-01-03 | 200 | 4569.4583 | 5780.3754 | 434563.9957 | 507816.8749
[17 empty] | 117 | 2025-01-04 | 201 | 0 | 0 | 434563.9957 | 507816.8749
[17 empty] | 117 | 2025-01-05 | 202 | 0 | 0 | 434563.9957 | 507816.8749
[17 empty] | 117 | 2025-01-06 | 203 | 4569.4583 | 5780.3754 | 439133.454 | 513597.2503
[17 empty] | 117 | 2025-01-07 | 204 | 4569.4583 | 5780.3754 | 443702.9123 | 519377.6257
[17 empty] | 117 | 2025-01-08 | 205 | 4569.4583 | 5780.3754 | 448272.3706 | 525158.001
[17 empty] | 117 | 2025-01-09 | 206 | 4569.4583 | 5780.3754 | 452841.8289 | 530938.3764
[17 empty] | 117 | 2025-01-10 | 207 | 4569.4583 | 5780.3754 | 457411.2872 | 536718.7518
[17 empty] | 117 | 2025-01-11 | 208 | 0 | 0 | 457411.2872 | 536718.7518
[17 empty] | 117 | 2025-01-12 | 209 | 0 | 0 | 457411.2872 | 536718.7518
[17 empty] | 117 | 2025-01-13 | 210 | 4569.4583 | 5780.3754 | 461980.7455 | 542499.1272
[17 empty] | 117 | 2025-01-14 | 211 | 4569.4583 | 5780.3754 | 466550.2038 | 548279.5026
[17 empty] | 117 | 2025-01-15 | 212 | 4569.4583 | 5780.3754 | 471119.6621 | 554059.878
[17 empty] | 117 | 2025-01-16 | 213 | 4569.4583 | 5780.3754 | 475689.1204 | 559840.2533
[17 empty] | 117 | 2025-01-17 | 214 | 4569.4583 | 5780.3754 | 480258.5787 | 565620.6287
[17 empty] | 117 | 2025-01-18 | 215 | 0 | 0 | 480258.5787 | 565620.6287
[17 empty] | 117 | 2025-01-19 | 216 | 0 | 0 | 480258.5787 | 565620.6287
[17 empty] | 117 | 2025-01-20 | 217 | 4569.4583 | 5780.3754 | 484828.0371 | 571401.0041
[17 empty] | 117 | 2025-01-21 | 218 | 4569.4583 | 5780.3754 | 489397.4954 | 577181.3795
[17 empty] | 117 | 2025-01-22 | 219 | 4569.4583 | 5780.3754 | 493966.9537 | 582961.7549
[17 empty] | 117 | 2025-01-23 | 220 | 4569.4583 | 5780.3754 | 498536.412 | 588742.1302
[17 empty] | 117 | 2025-01-24 | 221 | 4569.4583 | 5780.3754 | 503105.8703 | 594522.5056
[17 empty] | 117 | 2025-01-25 | 222 | 0 | 0 | 503105.8703 | 594522.5056
[17 empty] | 117 | 2025-01-26 | 223 | 0 | 0 | 503105.8703 | 594522.5056
[17 empty] | 117 | 2025-01-27 | 224 | 4569.4583 | 5780.3754 | 507675.3286 | 600302.881
[17 empty] | 117 | 2025-01-28 | 225 | 4569.4583 | 5780.3754 | 512244.7869 | 606083.2564
[17 empty] | 117 | 2025-01-29 | 226 | 4569.4583 | 5780.3754 | 516814.2452 | 611863.6318
[17 empty] | 117 | 2025-01-30 | 227 | 4569.4583 | 5780.3754 | 521383.7035 | 617644.0071
[17 empty] | 117 | 2025-01-31 | 228 | 4569.4583 | 5780.3754 | 525953.1618 | 623424.3825
[17 empty] | 117 | 2025-02-01 | 229 | 0 | 0 | 525953.1618 | 623424.3825
[17 empty] | 117 | 2025-02-02 | 230 | 0 | 0 | 525953.1618 | 623424.3825
[17 empty] | 117 | 2025-02-03 | 231 | 4569.4583 | 5780.3754 | 530522.6201 | 629204.7579
[17 empty] | 117 | 2025-02-04 | 232 | 4569.4583 | 5780.3754 | 535092.0784 | 634985.1333
[17 empty] | 117 | 2025-02-05 | 233 | 4569.4583 | 5780.3754 | 539661.5367 | 640765.5087
[17 empty] | 117 | 2025-02-06 | 234 | 4569.4583 | 5780.3754 | 544230.995 | 646545.8841
[17 empty] | 117 | 2025-02-07 | 235 | 4569.4583 | 5780.3754 | 548800.4533 | 652326.2594
[17 empty] | 117 | 2025-02-08 | 236 | 0 | 0 | 548800.4533 | 652326.2594
[17 empty] | 117 | 2025-02-09 | 237 | 0 | 0 | 548800.4533 | 652326.2594
[17 empty] | 117 | 2025-02-10 | 238 | 4569.4583 | 5780.3754 | 553369.9116 | 658106.6348
[17 empty] | 117 | 2025-02-11 | 239 | 4569.4583 | 5780.3754 | 557939.3699 | 663887.0102
[17 empty] | 117 | 2025-02-12 | 240 | 4569.4583 | 5780.3754 | 562508.8282 | 669667.3856
[17 empty] | 117 | 2025-02-13 | 241 | 4569.4583 | 5780.3754 | 567078.2865 | 675447.761
[17 empty] | 117 | 2025-02-14 | 242 | 4569.4583 | 5780.3754 | 571647.7448 | 681228.1363
[17 empty] | 117 | 2025-02-15 | 243 | 0 | 0 | 571647.7448 | 681228.1363
[17 empty] | 117 | 2025-02-16 | 244 | 0 | 0 | 571647.7448 | 681228.1363
[17 empty] | 117 | 2025-02-17 | 245 | 4569.4583 | 5780.3754 | 576217.2031 | 687008.5117
[17 empty] | 117 | 2025-02-18 | 246 | 4569.4583 | 5780.3754 | 580786.6614 | 692788.8871
[17 empty] | 117 | 2025-02-19 | 247 | 4569.4583 | 5780.3754 | 585356.1197 | 698569.2625
[17 empty] | 117 | 2025-02-20 | 248 | 4569.4583 | 5780.3754 | 589925.578 | 704349.6379
[17 empty] | 117 | 2025-02-21 | 249 | 4569.4583 | 5780.3754 | 594495.0363 | 710130.0132
[17 empty] | 117 | 2025-02-22 | 250 | 0 | 0 | 594495.0363 | 710130.0132
[17 empty] | 117 | 2025-02-23 | 251 | 0 | 0 | 594495.0363 | 710130.0132
[17 empty] | 117 | 2025-02-24 | 252 | 4569.4583 | 5780.3754 | 599064.4946 | 715910.3886
[17 empty] | 117 | 2025-02-25 | 253 | 4569.4583 | 5780.3754 | 603633.9529 | 721690.764
[17 empty] | 117 | 2025-02-26 | 254 | 4569.4583 | 5780.3754 | 608203.4113 | 727471.1394
[17 empty] | 117 | 2025-02-27 | 255 | 4569.4583 | 5780.3754 | 612772.8696 | 733251.5148
[17 empty] | 117 | 2025-02-28 | 256 | 4569.4583 | 5780.3754 | 617342.3279 | 739031.8902
[17 empty] | 117 | 2025-03-01 | 257 | 0 | 0 | 617342.3279 | 739031.8902
[17 empty] | 117 | 2025-03-02 | 258 | 0 | 0 | 617342.3279 | 739031.8902
[17 empty] | 117 | 2025-03-03 | 259 | 4569.4583 | 5780.3754 | 621911.7862 | 744812.2655
[17 empty] | 117 | 2025-03-04 | 260 | 4569.4583 | 5780.3754 | 626481.2445 | 750592.6409
[17 empty] | 117 | 2025-03-05 | 261 | 4569.4583 | 5780.3754 | 631050.7028 | 756373.0163
[17 empty] | 117 | 2025-03-06 | 262 | 4569.4583 | 5780.3754 | 635620.1611 | 762153.3917
[17 empty] | 117 | 2025-03-07 | 263 | 4569.4583 | 5780.3754 | 640189.6194 | 767933.7671
[17 empty] | 117 | 2025-03-08 | 264 | 0 | 0 | 640189.6194 | 767933.7671
[17 empty] | 117 | 2025-03-09 | 265 | 0 | 0 | 640189.6194 | 767933.7671
[17 empty] | 117 | 2025-03-10 | 266 | 4569.4583 | 5780.3754 | 644759.0777 | 773714.1424
[17 empty] | 117 | 2025-03-11 | 267 | 4569.4583 | 5780.3754 | 649328.536 | 779494.5178
[17 empty] | 117 | 2025-03-12 | 268 | 4569.4583 | 5780.3754 | 653897.9943 | 785274.8932
[17 empty] | 117 | 2025-03-13 | 269 | 4569.4583 | 5780.3754 | 658467.4526 | 791055.2686
[17 empty] | 117 | 2025-03-14 | 270 | 4569.4583 | 5780.3754 | 663036.9109 | 796835.644
[17 empty] | 117 | 2025-03-15 | 271 | 0 | 0 | 663036.9109 | 796835.644
[17 empty] | 117 | 2025-03-16 | 272 | 0 | 0 | 663036.9109 | 796835.644
[17 empty] | 117 | 2025-03-17 | 273 | 4569.4583 | 5780.3754 | 667606.3692 | 802616.0193
[17 empty] | 117 | 2025-03-18 | 274 | 4569.4583 | 5780.3754 | 672175.8275 | 808396.3947
[17 empty] | 117 | 2025-03-19 | 275 | 4569.4583 | 5780.3754 | 676745.2858 | 814176.7701
[17 empty] | 117 | 2025-03-20 | 276 | 4569.4583 | 5780.3754 | 681314.7441 | 819957.1455
[17 empty] | 117 | 2025-03-21 | 277 | 4569.4583 | 5780.3754 | 685884.2024 | 825737.5209
[17 empty] | 117 | 2025-03-22 | 278 | 0 | 0 | 685884.2024 | 825737.5209
[17 empty] | 117 | 2025-03-23 | 279 | 0 | 0 | 685884.2024 | 825737.5209
[17 empty] | 117 | 2025-03-24 | 280 | 4569.4583 | 5780.3754 | 690453.6607 | 831517.8963
[17 empty] | 117 | 2025-03-25 | 281 | 4569.4583 | 5780.3754 | 695023.119 | 837298.2716
[17 empty] | 117 | 2025-03-26 | 282 | 4569.4583 | 5780.3754 | 699592.5773 | 843078.647
[17 empty] | 117 | 2025-03-27 | 283 | 4569.4583 | 5780.3754 | 704162.0356 | 848859.0224
[17 empty] | 117 | 2025-03-28 | 284 | 4569.4583 | 5780.3754 | 708731.4939 | 854639.3978
[17 empty] | 117 | 2025-03-29 | 285 | 0 | 0 | 708731.4939 | 854639.3978
[17 empty] | 117 | 2025-03-30 | 286 | 0 | 0 | 708731.4939 | 854639.3978
[17 empty] | 117 | 2025-03-31 | 287 | 4569.4583 | 5780.3754 | 713300.9522 | 860419.7732
[17 empty] | 117 | 2025-04-01 | 288 | 4569.4583 | 5780.3754 | 717870.4105 | 866200.1485
[17 empty] | 117 | 2025-04-02 | 289 | 4569.4583 | 5780.3754 | 722439.8688 | 871980.5239
[17 empty] | 117 | 2025-04-03 | 290 | 4569.4583 | 5780.3754 | 727009.3271 | 877760.8993
[17 empty] | 117 | 2025-04-04 | 291 | 4569.4583 | 5780.3754 | 731578.7854 | 883541.2747
[17 empty] | 117 | 2025-04-05 | 292 | 0 | 0 | 731578.7854 | 883541.2747
[17 empty] | 117 | 2025-04-06 | 293 | 0 | 0 | 731578.7854 | 883541.2747
[17 empty] | 117 | 2025-04-07 | 294 | 4569.4583 | 5780.3754 | 736148.2438 | 889321.6501
[17 empty] | 117 | 2025-04-08 | 295 | 4569.4583 | 5780.3754 | 740717.7021 | 895102.0254
[17 empty] | 117 | 2025-04-09 | 296 | 4569.4583 | 5780.3754 | 745287.1604 | 900882.4008
[17 empty] | 117 | 2025-04-10 | 297 | 4569.4583 | 5780.3754 | 749856.6187 | 906662.7762
[17 empty] | 117 | 2025-04-11 | 298 | 4569.4583 | 5780.3754 | 754426.077 | 912443.1516
[17 empty] | 117 | 2025-04-12 | 299 | 0 | 0 | 754426.077 | 912443.1516
[17 empty] | 117 | 2025-04-13 | 300 | 0 | 0 | 754426.077 | 912443.1516
[17 empty] | 117 | 2025-04-14 | 301 | 4569.4583 | 5780.3754 | 758995.5353 | 918223.527
[17 empty] | 117 | 2025-04-15 | 302 | 4569.4583 | 5780.3754 | 763564.9936 | 924003.9024
[17 empty] | 117 | 2025-04-16 | 303 | 4569.4583 | 5780.3754 | 768134.4519 | 929784.2777
[17 empty] | 117 | 2025-04-17 | 304 | 4569.4583 | 5780.3754 | 772703.9102 | 935564.6531
[17 empty] | 117 | 2025-04-18 | 305 | 285.4583 | 339.6954 | 772989.3685 | 935904.3485
[17 empty] | 117 | 2025-04-19 | 306 | 0 | 0 | 772989.3685 | 935904.3485
[17 empty] | 117 | 2025-04-20 | 307 | 0 | 0 | 772989.3685 | 935904.3485
[17 empty] | 117 | 2025-04-21 | 308 | 285.4583 | 339.6954 | 773274.8268 | 936244.0439
[17 empty] | 117 | 2025-04-22 | 309 | 285.4583 | 339.6954 | 773560.2851 | 936583.7393
[17 empty] | 117 | 2025-04-23 | 310 | 285.4583 | 339.6954 | 773845.7434 | 936923.4346
[17 empty] | 117 | 2025-04-24 | 311 | 285.4583 | 339.6954 | 774131.2017 | 937263.13
[17 empty] | 117 | 2025-04-25 | 312 | 285.4583 | 339.6954 | 774416.66 | 937602.8254
[17 empty] | 117 | 2025-04-26 | 313 | 0 | 0 | 774416.66 | 937602.8254
[17 empty] | 117 | 2025-04-27 | 314 | 0 | 0 | 774416.66 | 937602.8254
[17 empty] | 118 | 2024-07-30 | 1 | 247.1071 | 298.9996 | 247.1071 | 298.9996
[17 empty] | 118 | 2024-07-31 | 2 | 247.1071 | 298.9996 | 494.2141 | 597.9991
[17 empty] | 118 | 2024-08-01 | 3 | 247.1071 | 298.9996 | 741.3212 | 896.9987
[17 empty] | 118 | 2024-08-02 | 4 | 247.1071 | 298.9996 | 988.4283 | 1195.9982
[17 empty] | 118 | 2024-08-03 | 5 | 0 | 0 | 988.4283 | 1195.9982
[17 empty] | 118 | 2024-08-04 | 6 | 0 | 0 | 988.4283 | 1195.9982
[17 empty] | 118 | 2024-08-05 | 7 | 1236.1071 | 1555.0296 | 2224.5354 | 2751.0278
[17 empty] | 118 | 2024-08-06 | 8 | 1236.1071 | 1555.0296 | 3460.6424 | 4306.0574
[17 empty] | 118 | 2024-08-07 | 9 | 1236.1071 | 1555.0296 | 4696.7495 | 5861.0869
[17 empty] | 118 | 2024-08-08 | 10 | 1236.1071 | 1555.0296 | 5932.8566 | 7416.1165
[17 empty] | 118 | 2024-08-09 | 11 | 1236.1071 | 1555.0296 | 7168.9637 | 8971.146
[17 empty] | 118 | 2024-08-10 | 12 | 0 | 0 | 7168.9637 | 8971.146
[17 empty] | 118 | 2024-08-11 | 13 | 0 | 0 | 7168.9637 | 8971.146
[17 empty] | 118 | 2024-08-12 | 14 | 1236.1071 | 1555.0296 | 8405.0707 | 10526.1756
[17 empty] | 118 | 2024-08-13 | 15 | 1236.1071 | 1555.0296 | 9641.1778 | 12081.2052
[17 empty] | 118 | 2024-08-14 | 16 | 1236.1071 | 1555.0296 | 10877.2849 | 13636.2347
[17 empty] | 118 | 2024-08-15 | 17 | 1236.1071 | 1555.0296 | 12113.392 | 15191.2643
[17 empty] | 118 | 2024-08-16 | 18 | 1236.1071 | 1555.0296 | 13349.499 | 16746.2938
[17 empty] | 118 | 2024-08-17 | 19 | 0 | 0 | 13349.499 | 16746.2938
[17 empty] | 118 | 2024-08-18 | 20 | 0 | 0 | 13349.499 | 16746.2938
[17 empty] | 118 | 2024-08-19 | 21 | 1236.1071 | 1555.0296 | 14585.6061 | 18301.3234
[17 empty] | 118 | 2024-08-20 | 22 | 1236.1071 | 1555.0296 | 15821.7132 | 19856.353
[17 empty] | 118 | 2024-08-21 | 23 | 1236.1071 | 1555.0296 | 17057.8203 | 21411.3825
[17 empty] | 118 | 2024-08-22 | 24 | 1236.1071 | 1555.0296 | 18293.9273 | 22966.4121
[17 empty] | 118 | 2024-08-23 | 25 | 1236.1071 | 1555.0296 | 19530.0344 | 24521.4416
[17 empty] | 118 | 2024-08-24 | 26 | 0 | 0 | 19530.0344 | 24521.4416
[17 empty] | 118 | 2024-08-25 | 27 | 0 | 0 | 19530.0344 | 24521.4416
[17 empty] | 118 | 2024-08-26 | 28 | 1236.1071 | 1555.0296 | 20766.1415 | 26076.4712
[17 empty] | 118 | 2024-08-27 | 29 | 1236.1071 | 1555.0296 | 22002.2486 | 27631.5008
[17 empty] | 118 | 2024-08-28 | 30 | 1236.1071 | 1555.0296 | 23238.3556 | 29186.5303
[17 empty] | 118 | 2024-08-29 | 31 | 1236.1071 | 1555.0296 | 24474.4627 | 30741.5599
[17 empty] | 118 | 2024-08-30 | 32 | 1236.1071 | 1555.0296 | 25710.5698 | 32296.5894
[17 empty] | 118 | 2024-08-31 | 33 | 0 | 0 | 25710.5698 | 32296.5894
[17 empty] | 118 | 2024-09-01 | 34 | 0 | 0 | 25710.5698 | 32296.5894
[17 empty] | 118 | 2024-09-02 | 35 | 1236.1071 | 1555.0296 | 26946.6769 | 33851.619
[17 empty] | 118 | 2024-09-03 | 36 | 1236.1071 | 1555.0296 | 28182.7839 | 35406.6486
[17 empty] | 118 | 2024-09-04 | 37 | 1236.1071 | 1555.0296 | 29418.891 | 36961.6781
[17 empty] | 118 | 2024-09-05 | 38 | 1236.1071 | 1555.0296 | 30654.9981 | 38516.7077
[17 empty] | 118 | 2024-09-06 | 39 | 1236.1071 | 1555.0296 | 31891.1052 | 40071.7372
[17 empty] | 118 | 2024-09-07 | 40 | 0 | 0 | 31891.1052 | 40071.7372
[17 empty] | 118 | 2024-09-08 | 41 | 0 | 0 | 31891.1052 | 40071.7372
[17 empty] | 118 | 2024-09-09 | 42 | 1236.1071 | 1555.0296 | 33127.2122 | 41626.7668
[17 empty] | 118 | 2024-09-10 | 43 | 1236.1071 | 1555.0296 | 34363.3193 | 43181.7964
[17 empty] | 118 | 2024-09-11 | 44 | 1236.1071 | 1555.0296 | 35599.4264 | 44736.8259
[17 empty] | 118 | 2024-09-12 | 45 | 1236.1071 | 1555.0296 | 36835.5334 | 46291.8555
[17 empty] | 118 | 2024-09-13 | 46 | 1236.1071 | 1555.0296 | 38071.6405 | 47846.885
[17 empty] | 118 | 2024-09-14 | 47 | 0 | 0 | 38071.6405 | 47846.885
[17 empty] | 118 | 2024-09-15 | 48 | 0 | 0 | 38071.6405 | 47846.885
[17 empty] | 118 | 2024-09-16 | 49 | 1236.1071 | 1555.0296 | 39307.7476 | 49401.9146
[17 empty] | 118 | 2024-09-17 | 50 | 1236.1071 | 1555.0296 | 40543.8547 | 50956.9442
[17 empty] | 118 | 2024-09-18 | 51 | 1236.1071 | 1555.0296 | 41779.9617 | 52511.9737
[17 empty] | 118 | 2024-09-19 | 52 | 1236.1071 | 1555.0296 | 43016.0688 | 54067.0033
[17 empty] | 118 | 2024-09-20 | 53 | 1236.1071 | 1555.0296 | 44252.1759 | 55622.0328
[17 empty] | 118 | 2024-09-21 | 54 | 0 | 0 | 44252.1759 | 55622.0328
[17 empty] | 118 | 2024-09-22 | 55 | 0 | 0 | 44252.1759 | 55622.0328
[17 empty] | 118 | 2024-09-23 | 56 | 1236.1071 | 1555.0296 | 45488.283 | 57177.0624
[17 empty] | 118 | 2024-09-24 | 57 | 1236.1071 | 1555.0296 | 46724.39 | 58732.092
[17 empty] | 118 | 2024-09-25 | 58 | 1236.1071 | 1555.0296 | 47960.4971 | 60287.1215
[17 empty] | 118 | 2024-09-26 | 59 | 3294.2237 | 4189.4189 | 51254.7209 | 64476.5404
[17 empty] | 118 | 2024-09-27 | 60 | 2305.2237 | 2933.3889 | 53559.9446 | 67409.9293
[17 empty] | 118 | 2024-09-28 | 61 | 0 | 0 | 53559.9446 | 67409.9293
[17 empty] | 118 | 2024-09-29 | 62 | 0 | 0 | 53559.9446 | 67409.9293
[17 empty] | 118 | 2024-09-30 | 63 | 2305.2237 | 2933.3889 | 55865.1683 | 70343.3182
[17 empty] | 118 | 2024-10-01 | 64 | 2305.2237 | 2933.3889 | 58170.3921 | 73276.7071
[17 empty] | 118 | 2024-10-02 | 65 | 2305.2237 | 2933.3889 | 60475.6158 | 76210.096
[17 empty] | 118 | 2024-10-03 | 66 | 2305.2237 | 2933.3889 | 62780.8396 | 79143.4849
[17 empty] | 118 | 2024-10-04 | 67 | 2305.2237 | 2933.3889 | 65086.0633 | 82076.8738
[17 empty] | 118 | 2024-10-05 | 68 | 0 | 0 | 65086.0633 | 82076.8738
[17 empty] | 118 | 2024-10-06 | 69 | 0 | 0 | 65086.0633 | 82076.8738
[17 empty] | 118 | 2024-10-07 | 70 | 2305.2237 | 2933.3889 | 67391.287 | 85010.2627
[17 empty] | 118 | 2024-10-08 | 71 | 2305.2237 | 2933.3889 | 69696.5108 | 87943.6516
[17 empty] | 118 | 2024-10-09 | 72 | 2305.2237 | 2933.3889 | 72001.7345 | 90877.0404
[17 empty] | 118 | 2024-10-10 | 73 | 2305.2237 | 2933.3889 | 74306.9583 | 93810.4293
[17 empty] | 118 | 2024-10-11 | 74 | 2305.2237 | 2933.3889 | 76612.182 | 96743.8182
[17 empty] | 118 | 2024-10-12 | 75 | 0 | 0 | 76612.182 | 96743.8182
[17 empty] | 118 | 2024-10-13 | 76 | 0 | 0 | 76612.182 | 96743.8182
[17 empty] | 118 | 2024-10-14 | 77 | 2305.2237 | 2933.3889 | 78917.4057 | 99677.2071
[17 empty] | 118 | 2024-10-15 | 78 | 2305.2237 | 2933.3889 | 81222.6295 | 102610.596
[17 empty] | 118 | 2024-10-16 | 79 | 2305.2237 | 2933.3889 | 83527.8532 | 105543.9849
[17 empty] | 118 | 2024-10-17 | 80 | 2305.2237 | 2933.3889 | 85833.077 | 108477.3738
[17 empty] | 118 | 2024-10-18 | 81 | 2305.2237 | 2933.3889 | 88138.3007 | 111410.7627
[17 empty] | 118 | 2024-10-19 | 82 | 0 | 0 | 88138.3007 | 111410.7627
[17 empty] | 118 | 2024-10-20 | 83 | 0 | 0 | 88138.3007 | 111410.7627
[17 empty] | 118 | 2024-10-21 | 84 | 2305.2237 | 2933.3889 | 90443.5245 | 114344.1516
[17 empty] | 118 | 2024-10-22 | 85 | 2305.2237 | 2933.3889 | 92748.7482 | 117277.5405
[17 empty] | 118 | 2024-10-23 | 86 | 2305.2237 | 2933.3889 | 95053.9719 | 120210.9294
[17 empty] | 118 | 2024-10-24 | 87 | 2305.2237 | 2933.3889 | 97359.1957 | 123144.3183
[17 empty] | 118 | 2024-10-25 | 88 | 2305.2237 | 2933.3889 | 99664.4194 | 126077.7072
[17 empty] | 118 | 2024-10-26 | 89 | 0 | 0 | 99664.4194 | 126077.7072
[17 empty] | 118 | 2024-10-27 | 90 | 0 | 0 | 99664.4194 | 126077.7072
[17 empty] | 118 | 2024-10-28 | 91 | 2305.2237 | 2933.3889 | 101969.6432 | 129011.0961
[17 empty] | 118 | 2024-10-29 | 92 | 2305.2237 | 2933.3889 | 104274.8669 | 131944.4849
[17 empty] | 118 | 2024-10-30 | 93 | 2305.2237 | 2933.3889 | 106580.0906 | 134877.8738
[17 empty] | 118 | 2024-10-31 | 94 | 2305.2237 | 2933.3889 | 108885.3144 | 137811.2627
[17 empty] | 118 | 2024-11-01 | 95 | 2305.2237 | 2933.3889 | 111190.5381 | 140744.6516
[17 empty] | 118 | 2024-11-02 | 96 | 0 | 0 | 111190.5381 | 140744.6516
[17 empty] | 118 | 2024-11-03 | 97 | 0 | 0 | 111190.5381 | 140744.6516
[17 empty] | 118 | 2024-11-04 | 98 | 2305.2237 | 2933.3889 | 113495.7619 | 143678.0405
[17 empty] | 118 | 2024-11-05 | 99 | 2305.2237 | 2933.3889 | 115800.9856 | 146611.4294
[17 empty] | 118 | 2024-11-06 | 100 | 2305.2237 | 2933.3889 | 118106.2093 | 149544.8183
[17 empty] | 118 | 2024-11-07 | 101 | 2305.2237 | 2933.3889 | 120411.4331 | 152478.2072
[17 empty] | 118 | 2024-11-08 | 102 | 2305.2237 | 2933.3889 | 122716.6568 | 155411.5961
[17 empty] | 118 | 2024-11-09 | 103 | 0 | 0 | 122716.6568 | 155411.5961
[17 empty] | 118 | 2024-11-10 | 104 | 0 | 0 | 122716.6568 | 155411.5961
[17 empty] | 118 | 2024-11-11 | 105 | 2305.2237 | 2933.3889 | 125021.8806 | 158344.985
[17 empty] | 118 | 2024-11-12 | 106 | 2305.2237 | 2933.3889 | 127327.1043 | 161278.3739
[17 empty] | 118 | 2024-11-13 | 107 | 2305.2237 | 2933.3889 | 129632.328 | 164211.7628
[17 empty] | 118 | 2024-11-14 | 108 | 2305.2237 | 2933.3889 | 131937.5518 | 167145.1517
[17 empty] | 118 | 2024-11-15 | 109 | 2305.2237 | 2933.3889 | 134242.7755 | 170078.5406
[17 empty] | 118 | 2024-11-16 | 110 | 0 | 0 | 134242.7755 | 170078.5406
[17 empty] | 118 | 2024-11-17 | 111 | 0 | 0 | 134242.7755 | 170078.5406
[17 empty] | 118 | 2024-11-18 | 112 | 2305.2237 | 2933.3889 | 136547.9993 | 173011.9295
[17 empty] | 118 | 2024-11-19 | 113 | 2305.2237 | 2933.3889 | 138853.223 | 175945.3183
[17 empty] | 118 | 2024-11-20 | 114 | 2305.2237 | 2933.3889 | 141158.4468 | 178878.7072
[17 empty] | 118 | 2024-11-21 | 115 | 2305.2237 | 2933.3889 | 143463.6705 | 181812.0961
[17 empty] | 118 | 2024-11-22 | 116 | 2305.2237 | 2933.3889 | 145768.8942 | 184745.485
[17 empty] | 118 | 2024-11-23 | 117 | 0 | 0 | 145768.8942 | 184745.485
[17 empty] | 118 | 2024-11-24 | 118 | 0 | 0 | 145768.8942 | 184745.485
[17 empty] | 118 | 2024-11-25 | 119 | 2305.2237 | 2933.3889 | 148074.118 | 187678.8739
[17 empty] | 118 | 2024-11-26 | 120 | 2305.2237 | 2933.3889 | 150379.3417 | 190612.2628
[17 empty] | 118 | 2024-11-27 | 121 | 2305.2237 | 2933.3889 | 152684.5655 | 193545.6517
[17 empty] | 118 | 2024-11-28 | 122 | 4418.6084 | 5532.852 | 157103.1738 | 199078.5037
[17 empty] | 118 | 2024-11-29 | 123 | 4418.6084 | 5532.852 | 161521.7822 | 204611.3556
[17 empty] | 118 | 2024-11-30 | 124 | 0 | 0 | 161521.7822 | 204611.3556
[17 empty] | 118 | 2024-12-01 | 125 | 0 | 0 | 161521.7822 | 204611.3556
[17 empty] | 118 | 2024-12-02 | 126 | 4418.6084 | 5532.852 | 165940.3905 | 210144.2076
[17 empty] | 118 | 2024-12-03 | 127 | 4418.6084 | 5532.852 | 170358.9989 | 215677.0596
[17 empty] | 118 | 2024-12-04 | 128 | 4418.6084 | 5532.852 | 174777.6072 | 221209.9116
[17 empty] | 118 | 2024-12-05 | 129 | 4418.6084 | 5532.852 | 179196.2156 | 226742.7635
[17 empty] | 118 | 2024-12-06 | 130 | 4418.6084 | 5532.852 | 183614.824 | 232275.6155
[17 empty] | 118 | 2024-12-07 | 131 | 0 | 0 | 183614.824 | 232275.6155
[17 empty] | 118 | 2024-12-08 | 132 | 0 | 0 | 183614.824 | 232275.6155
[17 empty] | 118 | 2024-12-09 | 133 | 6527.6084 | 7958.202 | 190142.4323 | 240233.8175
[17 empty] | 118 | 2024-12-10 | 134 | 6527.6084 | 7958.202 | 196670.0407 | 248192.0194
[17 empty] | 118 | 2024-12-11 | 135 | 6527.6084 | 7958.202 | 203197.649 | 256150.2214
[17 empty] | 118 | 2024-12-12 | 136 | 6527.6084 | 7958.202 | 209725.2574 | 264108.4234
[17 empty] | 118 | 2024-12-13 | 137 | 6527.6084 | 7958.202 | 216252.8657 | 272066.6253
[17 empty] | 118 | 2024-12-14 | 138 | 0 | 0 | 216252.8657 | 272066.6253
[17 empty] | 118 | 2024-12-15 | 139 | 0 | 0 | 216252.8657 | 272066.6253
[17 empty] | 118 | 2024-12-16 | 140 | 6527.6084 | 7958.202 | 222780.4741 | 280024.8273
[17 empty] | 118 | 2024-12-17 | 141 | 6527.6084 | 7958.202 | 229308.0824 | 287983.0293
[17 empty] | 118 | 2024-12-18 | 142 | 6527.6084 | 7958.202 | 235835.6908 | 295941.2313
[17 empty] | 118 | 2024-12-19 | 143 | 4469.4917 | 5323.8126 | 240305.1825 | 301265.0439
[17 empty] | 118 | 2024-12-20 | 144 | 4469.4917 | 5323.8126 | 244774.6742 | 306588.8565
[17 empty] | 118 | 2024-12-21 | 145 | 0 | 0 | 244774.6742 | 306588.8565
[17 empty] | 118 | 2024-12-22 | 146 | 0 | 0 | 244774.6742 | 306588.8565
[17 empty] | 118 | 2024-12-23 | 147 | 4469.4917 | 5323.8126 | 249244.1659 | 311912.6692
[17 empty] | 118 | 2024-12-24 | 148 | 4469.4917 | 5323.8126 | 253713.6576 | 317236.4818
[17 empty] | 118 | 2024-12-25 | 149 | 4469.4917 | 5323.8126 | 258183.1493 | 322560.2944
[17 empty] | 118 | 2024-12-26 | 150 | 4469.4917 | 5323.8126 | 262652.6409 | 327884.1071
[17 empty] | 118 | 2024-12-27 | 151 | 4469.4917 | 5323.8126 | 267122.1326 | 333207.9197
[17 empty] | 118 | 2024-12-28 | 152 | 0 | 0 | 267122.1326 | 333207.9197
[17 empty] | 118 | 2024-12-29 | 153 | 0 | 0 | 267122.1326 | 333207.9197
[17 empty] | 118 | 2024-12-30 | 154 | 4469.4917 | 5323.8126 | 271591.6243 | 338531.7324
[17 empty] | 118 | 2024-12-31 | 155 | 4469.4917 | 5323.8126 | 276061.116 | 343855.545
[17 empty] | 118 | 2025-01-01 | 156 | 4469.4917 | 5323.8126 | 280530.6077 | 349179.3576
[17 empty] | 118 | 2025-01-02 | 157 | 4469.4917 | 5323.8126 | 285000.0994 | 354503.1703
[17 empty] | 118 | 2025-01-03 | 158 | 4469.4917 | 5323.8126 | 289469.5911 | 359826.9829
[17 empty] | 118 | 2025-01-04 | 159 | 0 | 0 | 289469.5911 | 359826.9829
[17 empty] | 118 | 2025-01-05 | 160 | 0 | 0 | 289469.5911 | 359826.9829
[17 empty] | 118 | 2025-01-06 | 161 | 4469.4917 | 5323.8126 | 293939.0828 | 365150.7955
[17 empty] | 118 | 2025-01-07 | 162 | 4469.4917 | 5323.8126 | 298408.5745 | 370474.6082
[17 empty] | 118 | 2025-01-08 | 163 | 4469.4917 | 5323.8126 | 302878.0661 | 375798.4208
[17 empty] | 118 | 2025-01-09 | 164 | 4469.4917 | 5323.8126 | 307347.5578 | 381122.2334
[17 empty] | 118 | 2025-01-10 | 165 | 4469.4917 | 5323.8126 | 311817.0495 | 386446.0461
[17 empty] | 118 | 2025-01-11 | 166 | 0 | 0 | 311817.0495 | 386446.0461
[17 empty] | 118 | 2025-01-12 | 167 | 0 | 0 | 311817.0495 | 386446.0461
[17 empty] | 118 | 2025-01-13 | 168 | 4469.4917 | 5323.8126 | 316286.5412 | 391769.8587
[17 empty] | 118 | 2025-01-14 | 169 | 4469.4917 | 5323.8126 | 320756.0329 | 397093.6714
[17 empty] | 118 | 2025-01-15 | 170 | 4469.4917 | 5323.8126 | 325225.5246 | 402417.484
[17 empty] | 118 | 2025-01-16 | 171 | 4469.4917 | 5323.8126 | 329695.0163 | 407741.2966
[17 empty] | 118 | 2025-01-17 | 172 | 4469.4917 | 5323.8126 | 334164.508 | 413065.1093
[17 empty] | 118 | 2025-01-18 | 173 | 0 | 0 | 334164.508 | 413065.1093
[17 empty] | 118 | 2025-01-19 | 174 | 0 | 0 | 334164.508 | 413065.1093
[17 empty] | 118 | 2025-01-20 | 175 | 4469.4917 | 5323.8126 | 338633.9997 | 418388.9219
[17 empty] | 118 | 2025-01-21 | 176 | 4469.4917 | 5323.8126 | 343103.4914 | 423712.7345
[17 empty] | 118 | 2025-01-22 | 177 | 2356.1071 | 2724.3496 | 345459.5984 | 426437.0841
[17 empty] | 118 | 2025-01-23 | 178 | 2356.1071 | 2724.3496 | 347815.7055 | 429161.4337
[17 empty] | 118 | 2025-01-24 | 179 | 2356.1071 | 2724.3496 | 350171.8126 | 431885.7832
[17 empty] | 118 | 2025-01-25 | 180 | 0 | 0 | 350171.8126 | 431885.7832
[17 empty] | 118 | 2025-01-26 | 181 | 0 | 0 | 350171.8126 | 431885.7832
[17 empty] | 118 | 2025-01-27 | 182 | 2356.1071 | 2724.3496 | 352527.9197 | 434610.1328
[17 empty] | 118 | 2025-01-28 | 183 | 2356.1071 | 2724.3496 | 354884.0267 | 437334.4823
[17 empty] | 118 | 2025-01-29 | 184 | 2356.1071 | 2724.3496 | 357240.1338 | 440058.8319
[17 empty] | 118 | 2025-01-30 | 185 | 2356.1071 | 2724.3496 | 359596.2409 | 442783.1815
[17 empty] | 118 | 2025-01-31 | 186 | 2356.1071 | 2724.3496 | 361952.3479 | 445507.531
[17 empty] | 118 | 2025-02-01 | 187 | 0 | 0 | 361952.3479 | 445507.531
[17 empty] | 118 | 2025-02-02 | 188 | 0 | 0 | 361952.3479 | 445507.531
[17 empty] | 118 | 2025-02-03 | 189 | 2356.1071 | 2724.3496 | 364308.455 | 448231.8806
[17 empty] | 118 | 2025-02-04 | 190 | 2356.1071 | 2724.3496 | 366664.5621 | 450956.2301
[17 empty] | 118 | 2025-02-05 | 191 | 2356.1071 | 2724.3496 | 369020.6692 | 453680.5797
[17 empty] | 118 | 2025-02-06 | 192 | 2356.1071 | 2724.3496 | 371376.7762 | 456404.9293
[17 empty] | 118 | 2025-02-07 | 193 | 2356.1071 | 2724.3496 | 373732.8833 | 459129.2788
[17 empty] | 118 | 2025-02-08 | 194 | 0 | 0 | 373732.8833 | 459129.2788
[17 empty] | 118 | 2025-02-09 | 195 | 0 | 0 | 373732.8833 | 459129.2788
[17 empty] | 118 | 2025-02-10 | 196 | 2356.1071 | 2724.3496 | 376088.9904 | 461853.6284
[17 empty] | 118 | 2025-02-11 | 197 | 2356.1071 | 2724.3496 | 378445.0975 | 464577.9779
[17 empty] | 118 | 2025-02-12 | 198 | 2356.1071 | 2724.3496 | 380801.2045 | 467302.3275
[17 empty] | 118 | 2025-02-13 | 199 | 2356.1071 | 2724.3496 | 383157.3116 | 470026.6771
[17 empty] | 118 | 2025-02-14 | 200 | 2356.1071 | 2724.3496 | 385513.4187 | 472751.0266
[17 empty] | 118 | 2025-02-15 | 201 | 0 | 0 | 385513.4187 | 472751.0266
[17 empty] | 118 | 2025-02-16 | 202 | 0 | 0 | 385513.4187 | 472751.0266
[17 empty] | 118 | 2025-02-17 | 203 | 2356.1071 | 2724.3496 | 387869.5258 | 475475.3762
[17 empty] | 118 | 2025-02-18 | 204 | 2356.1071 | 2724.3496 | 390225.6328 | 478199.7257
[17 empty] | 118 | 2025-02-19 | 205 | 2356.1071 | 2724.3496 | 392581.7399 | 480924.0753
[17 empty] | 118 | 2025-02-20 | 206 | 2356.1071 | 2724.3496 | 394937.847 | 483648.4249
[17 empty] | 118 | 2025-02-21 | 207 | 2356.1071 | 2724.3496 | 397293.9541 | 486372.7744
[17 empty] | 118 | 2025-02-22 | 208 | 0 | 0 | 397293.9541 | 486372.7744
[17 empty] | 118 | 2025-02-23 | 209 | 0 | 0 | 397293.9541 | 486372.7744
[17 empty] | 118 | 2025-02-24 | 210 | 2356.1071 | 2724.3496 | 399650.0611 | 489097.124
[17 empty] | 118 | 2025-02-25 | 211 | 2356.1071 | 2724.3496 | 402006.1682 | 491821.4735
[17 empty] | 118 | 2025-02-26 | 212 | 2356.1071 | 2724.3496 | 404362.2753 | 494545.8231
[17 empty] | 118 | 2025-02-27 | 213 | 2356.1071 | 2724.3496 | 406718.3824 | 497270.1727
[17 empty] | 118 | 2025-02-28 | 214 | 2356.1071 | 2724.3496 | 409074.4894 | 499994.5222
[17 empty] | 118 | 2025-03-01 | 215 | 0 | 0 | 409074.4894 | 499994.5222
[17 empty] | 118 | 2025-03-02 | 216 | 0 | 0 | 409074.4894 | 499994.5222
[17 empty] | 118 | 2025-03-03 | 217 | 2356.1071 | 2724.3496 | 411430.5965 | 502718.8718
[17 empty] | 118 | 2025-03-04 | 218 | 2356.1071 | 2724.3496 | 413786.7036 | 505443.2213
[17 empty] | 118 | 2025-03-05 | 219 | 2356.1071 | 2724.3496 | 416142.8107 | 508167.5709
[17 empty] | 118 | 2025-03-06 | 220 | 2356.1071 | 2724.3496 | 418498.9177 | 510891.9205
[17 empty] | 118 | 2025-03-07 | 221 | 2356.1071 | 2724.3496 | 420855.0248 | 513616.27
[17 empty] | 118 | 2025-03-08 | 222 | 0 | 0 | 420855.0248 | 513616.27
[17 empty] | 118 | 2025-03-09 | 223 | 0 | 0 | 420855.0248 | 513616.27
[17 empty] | 118 | 2025-03-10 | 224 | 2356.1071 | 2724.3496 | 423211.1319 | 516340.6196
[17 empty] | 118 | 2025-03-11 | 225 | 2356.1071 | 2724.3496 | 425567.239 | 519064.9691
[17 empty] | 118 | 2025-03-12 | 226 | 2356.1071 | 2724.3496 | 427923.346 | 521789.3187
[17 empty] | 118 | 2025-03-13 | 227 | 2356.1071 | 2724.3496 | 430279.4531 | 524513.6683
[17 empty] | 118 | 2025-03-14 | 228 | 2356.1071 | 2724.3496 | 432635.5602 | 527238.0178
[17 empty] | 118 | 2025-03-15 | 229 | 0 | 0 | 432635.5602 | 527238.0178
[17 empty] | 118 | 2025-03-16 | 230 | 0 | 0 | 432635.5602 | 527238.0178
[17 empty] | 118 | 2025-03-17 | 231 | 2356.1071 | 2724.3496 | 434991.6672 | 529962.3674
[17 empty] | 118 | 2025-03-18 | 232 | 2356.1071 | 2724.3496 | 437347.7743 | 532686.7169
[17 empty] | 118 | 2025-03-19 | 233 | 2356.1071 | 2724.3496 | 439703.8814 | 535411.0665
[17 empty] | 118 | 2025-03-20 | 234 | 2356.1071 | 2724.3496 | 442059.9885 | 538135.4161
[17 empty] | 118 | 2025-03-21 | 235 | 2356.1071 | 2724.3496 | 444416.0955 | 540859.7656
[17 empty] | 118 | 2025-03-22 | 236 | 0 | 0 | 444416.0955 | 540859.7656
[17 empty] | 118 | 2025-03-23 | 237 | 0 | 0 | 444416.0955 | 540859.7656
[17 empty] | 118 | 2025-03-24 | 238 | 2356.1071 | 2724.3496 | 446772.2026 | 543584.1152
[17 empty] | 118 | 2025-03-25 | 239 | 2356.1071 | 2724.3496 | 449128.3097 | 546308.4647
[17 empty] | 118 | 2025-03-26 | 240 | 2356.1071 | 2724.3496 | 451484.4168 | 549032.8143
[17 empty] | 118 | 2025-03-27 | 241 | 2356.1071 | 2724.3496 | 453840.5238 | 551757.1638
[17 empty] | 118 | 2025-03-28 | 242 | 2356.1071 | 2724.3496 | 456196.6309 | 554481.5134
[17 empty] | 118 | 2025-03-29 | 243 | 0 | 0 | 456196.6309 | 554481.5134
[17 empty] | 118 | 2025-03-30 | 244 | 0 | 0 | 456196.6309 | 554481.5134
[17 empty] | 118 | 2025-03-31 | 245 | 2356.1071 | 2724.3496 | 458552.738 | 557205.863
[17 empty] | 118 | 2025-04-01 | 246 | 2356.1071 | 2724.3496 | 460908.8451 | 559930.2125
[17 empty] | 118 | 2025-04-02 | 247 | 2356.1071 | 2724.3496 | 463264.9521 | 562654.5621
[17 empty] | 118 | 2025-04-03 | 248 | 2356.1071 | 2724.3496 | 465621.0592 | 565378.9116
[17 empty] | 118 | 2025-04-04 | 249 | 2356.1071 | 2724.3496 | 467977.1663 | 568103.2612
[17 empty] | 118 | 2025-04-05 | 250 | 0 | 0 | 467977.1663 | 568103.2612
[17 empty] | 118 | 2025-04-06 | 251 | 0 | 0 | 467977.1663 | 568103.2612
[17 empty] | 118 | 2025-04-07 | 252 | 2356.1071 | 2724.3496 | 470333.2734 | 570827.6108
[17 empty] | 118 | 2025-04-08 | 253 | 2356.1071 | 2724.3496 | 472689.3804 | 573551.9603
[17 empty] | 118 | 2025-04-09 | 254 | 2356.1071 | 2724.3496 | 475045.4875 | 576276.3099
[17 empty] | 118 | 2025-04-10 | 255 | 2356.1071 | 2724.3496 | 477401.5946 | 579000.6594
[17 empty] | 118 | 2025-04-11 | 256 | 2356.1071 | 2724.3496 | 479757.7017 | 581725.009
[17 empty] | 118 | 2025-04-12 | 257 | 0 | 0 | 479757.7017 | 581725.009
[17 empty] | 118 | 2025-04-13 | 258 | 0 | 0 | 479757.7017 | 581725.009
[17 empty] | 118 | 2025-04-14 | 259 | 2356.1071 | 2724.3496 | 482113.8087 | 584449.3586
[17 empty] | 118 | 2025-04-15 | 260 | 2356.1071 | 2724.3496 | 484469.9158 | 587173.7081
[17 empty] | 118 | 2025-04-16 | 261 | 2356.1071 | 2724.3496 | 486826.0229 | 589898.0577
[17 empty] | 118 | 2025-04-17 | 262 | 2356.1071 | 2724.3496 | 489182.13 | 592622.4072
[17 empty] | 118 | 2025-04-18 | 263 | 2356.1071 | 2724.3496 | 491538.237 | 595346.7568
[17 empty] | 118 | 2025-04-19 | 264 | 0 | 0 | 491538.237 | 595346.7568
[17 empty] | 118 | 2025-04-20 | 265 | 0 | 0 | 491538.237 | 595346.7568
[17 empty] | 118 | 2025-04-21 | 266 | 2356.1071 | 2724.3496 | 493894.3441 | 598071.1064
[17 empty] | 118 | 2025-04-22 | 267 | 2356.1071 | 2724.3496 | 496250.4512 | 600795.4559
[17 empty] | 118 | 2025-04-23 | 268 | 2356.1071 | 2724.3496 | 498606.5583 | 603519.8055
[17 empty] | 118 | 2025-04-24 | 269 | 2356.1071 | 2724.3496 | 500962.6653 | 606244.155
[17 empty] | 118 | 2025-04-25 | 270 | 2356.1071 | 2724.3496 | 503318.7724 | 608968.5046
[17 empty] | 118 | 2025-04-26 | 271 | 0 | 0 | 503318.7724 | 608968.5046
[17 empty] | 118 | 2025-04-27 | 272 | 0 | 0 | 503318.7724 | 608968.5046
[17 empty] | 118 | 2025-04-28 | 273 | 2356.1071 | 2724.3496 | 505674.8795 | 611692.8542
[17 empty] | 118 | 2025-04-29 | 274 | 2356.1071 | 2724.3496 | 508030.9866 | 614417.2037
[17 empty] | 118 | 2025-04-30 | 275 | 2356.1071 | 2724.3496 | 510387.0936 | 617141.5533
[17 empty] | 118 | 2025-05-01 | 276 | 2356.1071 | 2724.3496 | 512743.2007 | 619865.9028
[17 empty] | 118 | 2025-05-02 | 277 | 2356.1071 | 2724.3496 | 515099.3078 | 622590.2524
[17 empty] | 118 | 2025-05-03 | 278 | 0 | 0 | 515099.3078 | 622590.2524
[17 empty] | 118 | 2025-05-04 | 279 | 0 | 0 | 515099.3078 | 622590.2524
[17 empty] | 118 | 2025-05-05 | 280 | 2356.1071 | 2724.3496 | 517455.4148 | 625314.602
[17 empty] | 118 | 2025-05-06 | 281 | 2356.1071 | 2724.3496 | 519811.5219 | 628038.9515
[17 empty] | 118 | 2025-05-07 | 282 | 2356.1071 | 2724.3496 | 522167.629 | 630763.3011
[17 empty] | 118 | 2025-05-08 | 283 | 2356.1071 | 2724.3496 | 524523.7361 | 633487.6506
[17 empty] | 118 | 2025-05-09 | 284 | 2356.1071 | 2724.3496 | 526879.8431 | 636212.0002
[17 empty] | 118 | 2025-05-10 | 285 | 0 | 0 | 526879.8431 | 636212.0002
[17 empty] | 118 | 2025-05-11 | 286 | 0 | 0 | 526879.8431 | 636212.0002
[17 empty] | 118 | 2025-05-12 | 287 | 2356.1071 | 2724.3496 | 529235.9502 | 638936.3498
[17 empty] | 118 | 2025-05-13 | 288 | 2356.1071 | 2724.3496 | 531592.0573 | 641660.6993
[17 empty] | 118 | 2025-05-14 | 289 | 2356.1071 | 2724.3496 | 533948.1644 | 644385.0489
[17 empty] | 118 | 2025-05-15 | 290 | 2356.1071 | 2724.3496 | 536304.2714 | 647109.3984
[17 empty] | 118 | 2025-05-16 | 291 | 2356.1071 | 2724.3496 | 538660.3785 | 649833.748
[17 empty] | 118 | 2025-05-17 | 292 | 0 | 0 | 538660.3785 | 649833.748
[17 empty] | 118 | 2025-05-18 | 293 | 0 | 0 | 538660.3785 | 649833.748
[17 empty] | 118 | 2025-05-19 | 294 | 2356.1071 | 2724.3496 | 541016.4856 | 652558.0976
[17 empty] | 118 | 2025-05-20 | 295 | 2356.1071 | 2724.3496 | 543372.5927 | 655282.4471
[17 empty] | 118 | 2025-05-21 | 296 | 2356.1071 | 2724.3496 | 545728.6997 | 658006.7967
[17 empty] | 118 | 2025-05-22 | 297 | 2356.1071 | 2724.3496 | 548084.8068 | 660731.1462
[17 empty] | 118 | 2025-05-23 | 298 | 2356.1071 | 2724.3496 | 550440.9139 | 663455.4958
[17 empty] | 118 | 2025-05-24 | 299 | 0 | 0 | 550440.9139 | 663455.4958
[17 empty] | 118 | 2025-05-25 | 300 | 0 | 0 | 550440.9139 | 663455.4958
[17 empty] | 118 | 2025-05-26 | 301 | 2356.1071 | 2724.3496 | 552797.021 | 666179.8454
[17 empty] | 118 | 2025-05-27 | 302 | 2356.1071 | 2724.3496 | 555153.128 | 668904.1949
[17 empty] | 118 | 2025-05-28 | 303 | 2356.1071 | 2724.3496 | 557509.2351 | 671628.5445
[17 empty] | 118 | 2025-05-29 | 304 | 2356.1071 | 2724.3496 | 559865.3422 | 674352.894
[17 empty] | 118 | 2025-05-30 | 305 | 2356.1071 | 2724.3496 | 562221.4493 | 677077.2436
[17 empty] | 118 | 2025-05-31 | 306 | 0 | 0 | 562221.4493 | 677077.2436
[17 empty] | 118 | 2025-06-01 | 307 | 0 | 0 | 562221.4493 | 677077.2436
[17 empty] | 118 | 2025-06-02 | 308 | 2356.1071 | 2724.3496 | 564577.5563 | 679801.5932
[17 empty] | 118 | 2025-06-03 | 309 | 2356.1071 | 2724.3496 | 566933.6634 | 682525.9427
[17 empty] | 118 | 2025-06-04 | 310 | 2356.1071 | 2724.3496 | 569289.7705 | 685250.2923
[17 empty] | 118 | 2025-06-05 | 311 | 247.1071 | 298.9996 | 569536.8776 | 685549.2918
[17 empty] | 118 | 2025-06-06 | 312 | 247.1071 | 298.9996 | 569783.9846 | 685848.2914
[17 empty] | 118 | 2025-06-07 | 313 | 0 | 0 | 569783.9846 | 685848.2914
[17 empty] | 118 | 2025-06-08 | 314 | 0 | 0 | 569783.9846 | 685848.2914
[17 empty] | 118 | 2025-06-09 | 315 | 247.1071 | 298.9996 | 570031.0917 | 686147.291
[17 empty] | 118 | 2025-06-10 | 316 | 247.1071 | 298.9996 | 570278.1988 | 686446.2905
[17 empty] | 118 | 2025-06-11 | 317 | 247.1071 | 298.9996 | 570525.3059 | 686745.2901
[17 empty] | 118 | 2025-06-12 | 318 | 247.1071 | 298.9996 | 570772.4129 | 687044.2896
[17 empty] | 118 | 2025-06-13 | 319 | 247.1071 | 298.9996 | 571019.52 | 687343.2892
[17 empty] | 118 | 2025-06-14 | 320 | 0 | 0 | 571019.52 | 687343.2892
[17 empty] | 119 | 2024-08-05 | 1 | 644.9773 | 819.1212 | 644.9773 | 819.1212
[17 empty] | 119 | 2024-08-06 | 2 | 644.9773 | 819.1212 | 1289.9547 | 1638.2424
[17 empty] | 119 | 2024-08-07 | 3 | 644.9773 | 819.1212 | 1934.932 | 2457.3636
[17 empty] | 119 | 2024-08-08 | 4 | 644.9773 | 819.1212 | 2579.9093 | 3276.4849
[17 empty] | 119 | 2024-08-09 | 5 | 644.9773 | 819.1212 | 3224.8867 | 4095.6061
[17 empty] | 119 | 2024-08-10 | 6 | 0 | 0 | 3224.8867 | 4095.6061
[17 empty] | 119 | 2024-08-11 | 7 | 0 | 0 | 3224.8867 | 4095.6061
[17 empty] | 119 | 2024-08-12 | 8 | 5691.9773 | 6976.4612 | 8916.864 | 11072.0673
[17 empty] | 119 | 2024-08-13 | 9 | 5691.9773 | 6976.4612 | 14608.8413 | 18048.5285
[17 empty] | 119 | 2024-08-14 | 10 | 5691.9773 | 6976.4612 | 20300.8187 | 25024.9897
[17 empty] | 119 | 2024-08-15 | 11 | 5691.9773 | 6976.4612 | 25992.796 | 32001.4509
[17 empty] | 119 | 2024-08-16 | 12 | 5691.9773 | 6976.4612 | 31684.7733 | 38977.9121
[17 empty] | 119 | 2024-08-17 | 13 | 0 | 0 | 31684.7733 | 38977.9121
[17 empty] | 119 | 2024-08-18 | 14 | 0 | 0 | 31684.7733 | 38977.9121
[17 empty] | 119 | 2024-08-19 | 15 | 5691.9773 | 6976.4612 | 37376.7507 | 45954.3733
[17 empty] | 119 | 2024-08-20 | 16 | 5691.9773 | 6976.4612 | 43068.728 | 52930.8346
[17 empty] | 119 | 2024-08-21 | 17 | 5691.9773 | 6976.4612 | 48760.7053 | 59907.2958
[17 empty] | 119 | 2024-08-22 | 18 | 5691.9773 | 6976.4612 | 54452.6827 | 66883.757
[17 empty] | 119 | 2024-08-23 | 19 | 5691.9773 | 6976.4612 | 60144.66 | 73860.2182
[17 empty] | 119 | 2024-08-24 | 20 | 0 | 0 | 60144.66 | 73860.2182
[17 empty] | 119 | 2024-08-25 | 21 | 0 | 0 | 60144.66 | 73860.2182
[17 empty] | 119 | 2024-08-26 | 22 | 5691.9773 | 6976.4612 | 65836.6373 | 80836.6794
[17 empty] | 119 | 2024-08-27 | 23 | 5691.9773 | 6976.4612 | 71528.6147 | 87813.1406
[17 empty] | 119 | 2024-08-28 | 24 | 5691.9773 | 6976.4612 | 77220.592 | 94789.6018
[17 empty] | 119 | 2024-08-29 | 25 | 5691.9773 | 6976.4612 | 82912.5693 | 101766.0631
[17 empty] | 119 | 2024-08-30 | 26 | 5691.9773 | 6976.4612 | 88604.5467 | 108742.5243
[17 empty] | 119 | 2024-08-31 | 27 | 0 | 0 | 88604.5467 | 108742.5243
[17 empty] | 119 | 2024-09-01 | 28 | 0 | 0 | 88604.5467 | 108742.5243
[17 empty] | 119 | 2024-09-02 | 29 | 5691.9773 | 6976.4612 | 94296.524 | 115718.9855
[17 empty] | 119 | 2024-09-03 | 30 | 5691.9773 | 6976.4612 | 99988.5013 | 122695.4467
[17 empty] | 119 | 2024-09-04 | 31 | 5691.9773 | 6976.4612 | 105680.4787 | 129671.9079
[17 empty] | 119 | 2024-09-05 | 32 | 5691.9773 | 6976.4612 | 111372.456 | 136648.3691
[17 empty] | 119 | 2024-09-06 | 33 | 5691.9773 | 6976.4612 | 117064.4333 | 143624.8303
[17 empty] | 119 | 2024-09-07 | 34 | 0 | 0 | 117064.4333 | 143624.8303
[17 empty] | 119 | 2024-09-08 | 35 | 0 | 0 | 117064.4333 | 143624.8303
[17 empty] | 119 | 2024-09-09 | 36 | 5691.9773 | 6976.4612 | 122756.4107 | 150601.2915
[17 empty] | 119 | 2024-09-10 | 37 | 5691.9773 | 6976.4612 | 128448.388 | 157577.7528
[17 empty] | 119 | 2024-09-11 | 38 | 5691.9773 | 6976.4612 | 134140.3653 | 164554.214
[17 empty] | 119 | 2024-09-12 | 39 | 8638.8145 | 10335.8556 | 142779.1799 | 174890.0696
[17 empty] | 119 | 2024-09-13 | 40 | 3591.8145 | 4178.5156 | 146370.9944 | 179068.5852
[17 empty] | 119 | 2024-09-14 | 41 | 0 | 0 | 146370.9944 | 179068.5852
[17 empty] | 119 | 2024-09-15 | 42 | 0 | 0 | 146370.9944 | 179068.5852
[17 empty] | 119 | 2024-09-16 | 43 | 3591.8145 | 4178.5156 | 149962.809 | 183247.1009
[17 empty] | 119 | 2024-09-17 | 44 | 3591.8145 | 4178.5156 | 153554.6235 | 187425.6165
[17 empty] | 119 | 2024-09-18 | 45 | 3591.8145 | 4178.5156 | 157146.438 | 191604.1321
[17 empty] | 119 | 2024-09-19 | 46 | 3591.8145 | 4178.5156 | 160738.2526 | 195782.6478
[17 empty] | 119 | 2024-09-20 | 47 | 3591.8145 | 4178.5156 | 164330.0671 | 199961.1634
[17 empty] | 119 | 2024-09-21 | 48 | 0 | 0 | 164330.0671 | 199961.1634
[17 empty] | 119 | 2024-09-22 | 49 | 0 | 0 | 164330.0671 | 199961.1634
[17 empty] | 119 | 2024-09-23 | 50 | 3591.8145 | 4178.5156 | 167921.8817 | 204139.679
[17 empty] | 119 | 2024-09-24 | 51 | 3591.8145 | 4178.5156 | 171513.6962 | 208318.1947
[17 empty] | 119 | 2024-09-25 | 52 | 3591.8145 | 4178.5156 | 175105.5108 | 212496.7103
[17 empty] | 119 | 2024-09-26 | 53 | 3591.8145 | 4178.5156 | 178697.3253 | 216675.2259
[17 empty] | 119 | 2024-09-27 | 54 | 3591.8145 | 4178.5156 | 182289.1398 | 220853.7416
[17 empty] | 119 | 2024-09-28 | 55 | 0 | 0 | 182289.1398 | 220853.7416
[17 empty] | 119 | 2024-09-29 | 56 | 0 | 0 | 182289.1398 | 220853.7416
[17 empty] | 119 | 2024-09-30 | 57 | 3591.8145 | 4178.5156 | 185880.9544 | 225032.2572
[17 empty] | 119 | 2024-10-01 | 58 | 3591.8145 | 4178.5156 | 189472.7689 | 229210.7728
[17 empty] | 119 | 2024-10-02 | 59 | 3591.8145 | 4178.5156 | 193064.5835 | 233389.2885
[17 empty] | 119 | 2024-10-03 | 60 | 3591.8145 | 4178.5156 | 196656.398 | 237567.8041
[17 empty] | 119 | 2024-10-04 | 61 | 3591.8145 | 4178.5156 | 200248.2126 | 241746.3197
[17 empty] | 119 | 2024-10-05 | 62 | 0 | 0 | 200248.2126 | 241746.3197
[17 empty] | 119 | 2024-10-06 | 63 | 0 | 0 | 200248.2126 | 241746.3197
[17 empty] | 119 | 2024-10-07 | 64 | 3591.8145 | 4178.5156 | 203840.0271 | 245924.8353
[17 empty] | 119 | 2024-10-08 | 65 | 3591.8145 | 4178.5156 | 207431.8416 | 250103.351
[17 empty] | 119 | 2024-10-09 | 66 | 3591.8145 | 4178.5156 | 211023.6562 | 254281.8666
[17 empty] | 119 | 2024-10-10 | 67 | 3591.8145 | 4178.5156 | 214615.4707 | 258460.3822
[17 empty] | 119 | 2024-10-11 | 68 | 3591.8145 | 4178.5156 | 218207.2853 | 262638.8979
[17 empty] | 119 | 2024-10-12 | 69 | 0 | 0 | 218207.2853 | 262638.8979
[17 empty] | 119 | 2024-10-13 | 70 | 0 | 0 | 218207.2853 | 262638.8979
[17 empty] | 119 | 2024-10-14 | 71 | 3591.8145 | 4178.5156 | 221799.0998 | 266817.4135
[17 empty] | 119 | 2024-10-15 | 72 | 3591.8145 | 4178.5156 | 225390.9144 | 270995.9291
[17 empty] | 119 | 2024-10-16 | 73 | 3591.8145 | 4178.5156 | 228982.7289 | 275174.4448
[17 empty] | 119 | 2024-10-17 | 74 | 3591.8145 | 4178.5156 | 232574.5434 | 279352.9604
[17 empty] | 119 | 2024-10-18 | 75 | 3591.8145 | 4178.5156 | 236166.358 | 283531.476
[17 empty] | 119 | 2024-10-19 | 76 | 0 | 0 | 236166.358 | 283531.476
[17 empty] | 119 | 2024-10-20 | 77 | 0 | 0 | 236166.358 | 283531.476
[17 empty] | 119 | 2024-10-21 | 78 | 3591.8145 | 4178.5156 | 239758.1725 | 287709.9917
[17 empty] | 119 | 2024-10-22 | 79 | 8246.3145 | 9391.5556 | 248004.4871 | 297101.5473
[17 empty] | 119 | 2024-10-23 | 80 | 8246.3145 | 9391.5556 | 256250.8016 | 306493.1029
[17 empty] | 119 | 2024-10-24 | 81 | 8246.3145 | 9391.5556 | 264497.1162 | 315884.6586
[17 empty] | 119 | 2024-10-25 | 82 | 8246.3145 | 9391.5556 | 272743.4307 | 325276.2142
[17 empty] | 119 | 2024-10-26 | 83 | 0 | 0 | 272743.4307 | 325276.2142
[17 empty] | 119 | 2024-10-27 | 84 | 0 | 0 | 272743.4307 | 325276.2142
[17 empty] | 119 | 2024-10-28 | 85 | 8246.3145 | 9391.5556 | 280989.7452 | 334667.7698
[17 empty] | 119 | 2024-10-29 | 86 | 8246.3145 | 9391.5556 | 289236.0598 | 344059.3255
[17 empty] | 119 | 2024-10-30 | 87 | 8246.3145 | 9391.5556 | 297482.3743 | 353450.8811
[17 empty] | 119 | 2024-10-31 | 88 | 8246.3145 | 9391.5556 | 305728.6889 | 362842.4367
[17 empty] | 119 | 2024-11-01 | 89 | 13518.9418 | 16140.5185 | 319247.6307 | 378982.9553
[17 empty] | 119 | 2024-11-02 | 90 | 0 | 0 | 319247.6307 | 378982.9553
[17 empty] | 119 | 2024-11-03 | 91 | 0 | 0 | 319247.6307 | 378982.9553
[17 empty] | 119 | 2024-11-04 | 92 | 13518.9418 | 16140.5185 | 332766.5725 | 395123.4738
[17 empty] | 119 | 2024-11-05 | 93 | 13518.9418 | 16140.5185 | 346285.5143 | 411263.9923
[17 empty] | 119 | 2024-11-06 | 94 | 13518.9418 | 16140.5185 | 359804.4561 | 427404.5109
[17 empty] | 119 | 2024-11-07 | 95 | 13518.9418 | 16140.5185 | 373323.3979 | 443545.0294
[17 empty] | 119 | 2024-11-08 | 96 | 13518.9418 | 16140.5185 | 386842.3398 | 459685.548
[17 empty] | 119 | 2024-11-09 | 97 | 0 | 0 | 386842.3398 | 459685.548
[17 empty] | 119 | 2024-11-10 | 98 | 0 | 0 | 386842.3398 | 459685.548
[17 empty] | 119 | 2024-11-11 | 99 | 13518.9418 | 16140.5185 | 400361.2816 | 475826.0665
[17 empty] | 119 | 2024-11-12 | 100 | 10572.1046 | 12781.1241 | 410933.3862 | 488607.1906
[17 empty] | 119 | 2024-11-13 | 101 | 10572.1046 | 12781.1241 | 421505.4908 | 501388.3148
[17 empty] | 119 | 2024-11-14 | 102 | 10572.1046 | 12781.1241 | 432077.5954 | 514169.4389
[17 empty] | 119 | 2024-11-15 | 103 | 10572.1046 | 12781.1241 | 442649.7 | 526950.563
[17 empty] | 119 | 2024-11-16 | 104 | 0 | 0 | 442649.7 | 526950.563
[17 empty] | 119 | 2024-11-17 | 105 | 0 | 0 | 442649.7 | 526950.563
[17 empty] | 119 | 2024-11-18 | 106 | 10572.1046 | 12781.1241 | 453221.8046 | 539731.6871
[17 empty] | 119 | 2024-11-19 | 107 | 10572.1046 | 12781.1241 | 463793.9092 | 552512.8112
[17 empty] | 119 | 2024-11-20 | 108 | 10572.1046 | 12781.1241 | 474366.0138 | 565293.9354
[17 empty] | 119 | 2024-11-21 | 109 | 10572.1046 | 12781.1241 | 484938.1184 | 578075.0595
[17 empty] | 119 | 2024-11-22 | 110 | 10572.1046 | 12781.1241 | 495510.223 | 590856.1836
[17 empty] | 119 | 2024-11-23 | 111 | 0 | 0 | 495510.223 | 590856.1836
[17 empty] | 119 | 2024-11-24 | 112 | 0 | 0 | 495510.223 | 590856.1836
[17 empty] | 119 | 2024-11-25 | 113 | 10572.1046 | 12781.1241 | 506082.3276 | 603637.3077
[17 empty] | 119 | 2024-11-26 | 114 | 10572.1046 | 12781.1241 | 516654.4322 | 616418.4319
[17 empty] | 119 | 2024-11-27 | 115 | 10572.1046 | 12781.1241 | 527226.5368 | 629199.556
[17 empty] | 119 | 2024-11-28 | 116 | 10572.1046 | 12781.1241 | 537798.6415 | 641980.6801
[17 empty] | 119 | 2024-11-29 | 117 | 10572.1046 | 12781.1241 | 548370.7461 | 654761.8042
[17 empty] | 119 | 2024-11-30 | 118 | 0 | 0 | 548370.7461 | 654761.8042
[17 empty] | 119 | 2024-12-01 | 119 | 0 | 0 | 548370.7461 | 654761.8042
[17 empty] | 119 | 2024-12-02 | 120 | 10572.1046 | 12781.1241 | 558942.8507 | 667542.9283
[17 empty] | 119 | 2024-12-03 | 121 | 5917.6046 | 7568.0841 | 564860.4553 | 675111.0125
[17 empty] | 119 | 2024-12-04 | 122 | 5917.6046 | 7568.0841 | 570778.0599 | 682679.0966
[17 empty] | 119 | 2024-12-05 | 123 | 5917.6046 | 7568.0841 | 576695.6645 | 690247.1807
[17 empty] | 119 | 2024-12-06 | 124 | 5917.6046 | 7568.0841 | 582613.2691 | 697815.2648
[17 empty] | 119 | 2024-12-07 | 125 | 0 | 0 | 582613.2691 | 697815.2648
[17 empty] | 119 | 2024-12-08 | 126 | 0 | 0 | 582613.2691 | 697815.2648
[17 empty] | 119 | 2024-12-09 | 127 | 5917.6046 | 7568.0841 | 588530.8737 | 705383.349
[17 empty] | 119 | 2024-12-10 | 128 | 5917.6046 | 7568.0841 | 594448.4783 | 712951.4331
[17 empty] | 119 | 2024-12-11 | 129 | 5917.6046 | 7568.0841 | 600366.0829 | 720519.5172
[17 empty] | 119 | 2024-12-12 | 130 | 5917.6046 | 7568.0841 | 606283.6875 | 728087.6013
[17 empty] | 119 | 2024-12-13 | 131 | 5917.6046 | 7568.0841 | 612201.2921 | 735655.6854
[17 empty] | 119 | 2024-12-14 | 132 | 0 | 0 | 612201.2921 | 735655.6854
[17 empty] | 119 | 2024-12-15 | 133 | 0 | 0 | 612201.2921 | 735655.6854
[17 empty] | 119 | 2024-12-16 | 134 | 5917.6046 | 7568.0841 | 618118.8967 | 743223.7696
[17 empty] | 119 | 2024-12-17 | 135 | 5917.6046 | 7568.0841 | 624036.5013 | 750791.8537
[17 empty] | 119 | 2024-12-18 | 136 | 5917.6046 | 7568.0841 | 629954.1059 | 758359.9378
[17 empty] | 119 | 2024-12-19 | 137 | 5917.6046 | 7568.0841 | 635871.7105 | 765928.0219
[17 empty] | 119 | 2024-12-20 | 138 | 5917.6046 | 7568.0841 | 641789.3152 | 773496.1061
[17 empty] | 119 | 2024-12-21 | 139 | 0 | 0 | 641789.3152 | 773496.1061
[17 empty] | 119 | 2024-12-22 | 140 | 0 | 0 | 641789.3152 | 773496.1061
[17 empty] | 119 | 2024-12-23 | 141 | 5917.6046 | 7568.0841 | 647706.9198 | 781064.1902
[17 empty] | 119 | 2024-12-24 | 142 | 5917.6046 | 7568.0841 | 653624.5244 | 788632.2743
[17 empty] | 119 | 2024-12-25 | 143 | 5917.6046 | 7568.0841 | 659542.129 | 796200.3584
[17 empty] | 119 | 2024-12-26 | 144 | 5917.6046 | 7568.0841 | 665459.7336 | 803768.4426
[17 empty] | 119 | 2024-12-27 | 145 | 5917.6046 | 7568.0841 | 671377.3382 | 811336.5267
[17 empty] | 119 | 2024-12-28 | 146 | 0 | 0 | 671377.3382 | 811336.5267
[17 empty] | 119 | 2024-12-29 | 147 | 0 | 0 | 671377.3382 | 811336.5267
[17 empty] | 119 | 2024-12-30 | 148 | 5917.6046 | 7568.0841 | 677294.9428 | 818904.6108
[17 empty] | 119 | 2024-12-31 | 149 | 5917.6046 | 7568.0841 | 683212.5474 | 826472.6949
[17 empty] | 119 | 2025-01-01 | 150 | 5917.6046 | 7568.0841 | 689130.152 | 834040.779
[17 empty] | 119 | 2025-01-02 | 151 | 5917.6046 | 7568.0841 | 695047.7566 | 841608.8632
[17 empty] | 119 | 2025-01-03 | 152 | 5917.6046 | 7568.0841 | 700965.3612 | 849176.9473
[17 empty] | 119 | 2025-01-04 | 153 | 0 | 0 | 700965.3612 | 849176.9473
[17 empty] | 119 | 2025-01-05 | 154 | 0 | 0 | 700965.3612 | 849176.9473
[17 empty] | 119 | 2025-01-06 | 155 | 5917.6046 | 7568.0841 | 706882.9658 | 856745.0314
[17 empty] | 119 | 2025-01-07 | 156 | 5917.6046 | 7568.0841 | 712800.5704 | 864313.1155
[17 empty] | 119 | 2025-01-08 | 157 | 5917.6046 | 7568.0841 | 718718.175 | 871881.1997
[17 empty] | 119 | 2025-01-09 | 158 | 5917.6046 | 7568.0841 | 724635.7796 | 879449.2838
[17 empty] | 119 | 2025-01-10 | 159 | 5917.6046 | 7568.0841 | 730553.3842 | 887017.3679
[17 empty] | 119 | 2025-01-11 | 160 | 0 | 0 | 730553.3842 | 887017.3679
[17 empty] | 119 | 2025-01-12 | 161 | 0 | 0 | 730553.3842 | 887017.3679
[17 empty] | 119 | 2025-01-13 | 162 | 5917.6046 | 7568.0841 | 736470.9888 | 894585.452
[17 empty] | 119 | 2025-01-14 | 163 | 5917.6046 | 7568.0841 | 742388.5935 | 902153.5361
[17 empty] | 119 | 2025-01-15 | 164 | 5917.6046 | 7568.0841 | 748306.1981 | 909721.6203
[17 empty] | 119 | 2025-01-16 | 165 | 5917.6046 | 7568.0841 | 754223.8027 | 917289.7044
[17 empty] | 119 | 2025-01-17 | 166 | 5917.6046 | 7568.0841 | 760141.4073 | 924857.7885
[17 empty] | 119 | 2025-01-18 | 167 | 0 | 0 | 760141.4073 | 924857.7885
[17 empty] | 119 | 2025-01-19 | 168 | 0 | 0 | 760141.4073 | 924857.7885
[17 empty] | 119 | 2025-01-20 | 169 | 5917.6046 | 7568.0841 | 766059.0119 | 932425.8726
[17 empty] | 119 | 2025-01-21 | 170 | 5917.6046 | 7568.0841 | 771976.6165 | 939993.9568
[17 empty] | 119 | 2025-01-22 | 171 | 5917.6046 | 7568.0841 | 777894.2211 | 947562.0409
[17 empty] | 119 | 2025-01-23 | 172 | 5917.6046 | 7568.0841 | 783811.8257 | 955130.125
[17 empty] | 119 | 2025-01-24 | 173 | 5917.6046 | 7568.0841 | 789729.4303 | 962698.2091
[17 empty] | 119 | 2025-01-25 | 174 | 0 | 0 | 789729.4303 | 962698.2091
[17 empty] | 119 | 2025-01-26 | 175 | 0 | 0 | 789729.4303 | 962698.2091
[17 empty] | 119 | 2025-01-27 | 176 | 5917.6046 | 7568.0841 | 795647.0349 | 970266.2932
[17 empty] | 119 | 2025-01-28 | 177 | 5917.6046 | 7568.0841 | 801564.6395 | 977834.3774
[17 empty] | 119 | 2025-01-29 | 178 | 5917.6046 | 7568.0841 | 807482.2441 | 985402.4615
[17 empty] | 119 | 2025-01-30 | 179 | 5917.6046 | 7568.0841 | 813399.8487 | 992970.5456
[17 empty] | 119 | 2025-01-31 | 180 | 5917.6046 | 7568.0841 | 819317.4533 | 1000538.6297
[17 empty] | 119 | 2025-02-01 | 181 | 0 | 0 | 819317.4533 | 1000538.6297
[17 empty] | 119 | 2025-02-02 | 182 | 0 | 0 | 819317.4533 | 1000538.6297
[17 empty] | 119 | 2025-02-03 | 183 | 5917.6046 | 7568.0841 | 825235.0579 | 1008106.7139
[17 empty] | 119 | 2025-02-04 | 184 | 5917.6046 | 7568.0841 | 831152.6625 | 1015674.798
[17 empty] | 119 | 2025-02-05 | 185 | 5917.6046 | 7568.0841 | 837070.2672 | 1023242.8821
[17 empty] | 119 | 2025-02-06 | 186 | 5917.6046 | 7568.0841 | 842987.8718 | 1030810.9662
[17 empty] | 119 | 2025-02-07 | 187 | 5917.6046 | 7568.0841 | 848905.4764 | 1038379.0503
[17 empty] | 119 | 2025-02-08 | 188 | 0 | 0 | 848905.4764 | 1038379.0503
[17 empty] | 119 | 2025-02-09 | 189 | 0 | 0 | 848905.4764 | 1038379.0503
[17 empty] | 119 | 2025-02-10 | 190 | 5917.6046 | 7568.0841 | 854823.081 | 1045947.1345
[17 empty] | 119 | 2025-02-11 | 191 | 5917.6046 | 7568.0841 | 860740.6856 | 1053515.2186
[17 empty] | 119 | 2025-02-12 | 192 | 5917.6046 | 7568.0841 | 866658.2902 | 1061083.3027
[17 empty] | 119 | 2025-02-13 | 193 | 5917.6046 | 7568.0841 | 872575.8948 | 1068651.3868
[17 empty] | 119 | 2025-02-14 | 194 | 5917.6046 | 7568.0841 | 878493.4994 | 1076219.471
[17 empty] | 119 | 2025-02-15 | 195 | 0 | 0 | 878493.4994 | 1076219.471
[17 empty] | 119 | 2025-02-16 | 196 | 0 | 0 | 878493.4994 | 1076219.471
[17 empty] | 119 | 2025-02-17 | 197 | 5917.6046 | 7568.0841 | 884411.104 | 1083787.5551
[17 empty] | 119 | 2025-02-18 | 198 | 5917.6046 | 7568.0841 | 890328.7086 | 1091355.6392
[17 empty] | 119 | 2025-02-19 | 199 | 5917.6046 | 7568.0841 | 896246.3132 | 1098923.7233
[17 empty] | 119 | 2025-02-20 | 200 | 5917.6046 | 7568.0841 | 902163.9178 | 1106491.8074
[17 empty] | 119 | 2025-02-21 | 201 | 5917.6046 | 7568.0841 | 908081.5224 | 1114059.8916
[17 empty] | 119 | 2025-02-22 | 202 | 0 | 0 | 908081.5224 | 1114059.8916
[17 empty] | 119 | 2025-02-23 | 203 | 0 | 0 | 908081.5224 | 1114059.8916
[17 empty] | 119 | 2025-02-24 | 204 | 5917.6046 | 7568.0841 | 913999.127 | 1121627.9757
[17 empty] | 119 | 2025-02-25 | 205 | 5917.6046 | 7568.0841 | 919916.7316 | 1129196.0598
[17 empty] | 119 | 2025-02-26 | 206 | 5917.6046 | 7568.0841 | 925834.3362 | 1136764.1439
[17 empty] | 119 | 2025-02-27 | 207 | 5917.6046 | 7568.0841 | 931751.9408 | 1144332.2281
[17 empty] | 119 | 2025-02-28 | 208 | 5917.6046 | 7568.0841 | 937669.5455 | 1151900.3122
[17 empty] | 119 | 2025-03-01 | 209 | 0 | 0 | 937669.5455 | 1151900.3122
[17 empty] | 119 | 2025-03-02 | 210 | 0 | 0 | 937669.5455 | 1151900.3122
[17 empty] | 119 | 2025-03-03 | 211 | 5917.6046 | 7568.0841 | 943587.1501 | 1159468.3963
[17 empty] | 119 | 2025-03-04 | 212 | 5917.6046 | 7568.0841 | 949504.7547 | 1167036.4804
[17 empty] | 119 | 2025-03-05 | 213 | 5917.6046 | 7568.0841 | 955422.3593 | 1174604.5645
[17 empty] | 119 | 2025-03-06 | 214 | 5917.6046 | 7568.0841 | 961339.9639 | 1182172.6487
[17 empty] | 119 | 2025-03-07 | 215 | 5917.6046 | 7568.0841 | 967257.5685 | 1189740.7328
[17 empty] | 119 | 2025-03-08 | 216 | 0 | 0 | 967257.5685 | 1189740.7328
[17 empty] | 119 | 2025-03-09 | 217 | 0 | 0 | 967257.5685 | 1189740.7328
[17 empty] | 119 | 2025-03-10 | 218 | 5917.6046 | 7568.0841 | 973175.1731 | 1197308.8169
[17 empty] | 119 | 2025-03-11 | 219 | 5917.6046 | 7568.0841 | 979092.7777 | 1204876.901
[17 empty] | 119 | 2025-03-12 | 220 | 5917.6046 | 7568.0841 | 985010.3823 | 1212444.9852
[17 empty] | 119 | 2025-03-13 | 221 | 5917.6046 | 7568.0841 | 990927.9869 | 1220013.0693
[17 empty] | 119 | 2025-03-14 | 222 | 5917.6046 | 7568.0841 | 996845.5915 | 1227581.1534
[17 empty] | 119 | 2025-03-15 | 223 | 0 | 0 | 996845.5915 | 1227581.1534
[17 empty] | 119 | 2025-03-16 | 224 | 0 | 0 | 996845.5915 | 1227581.1534
[17 empty] | 119 | 2025-03-17 | 225 | 5917.6046 | 7568.0841 | 1002763.1961 | 1235149.2375
[17 empty] | 119 | 2025-03-18 | 226 | 5917.6046 | 7568.0841 | 1008680.8007 | 1242717.3217
[17 empty] | 119 | 2025-03-19 | 227 | 5917.6046 | 7568.0841 | 1014598.4053 | 1250285.4058
[17 empty] | 119 | 2025-03-20 | 228 | 5917.6046 | 7568.0841 | 1020516.0099 | 1257853.4899
[17 empty] | 119 | 2025-03-21 | 229 | 5917.6046 | 7568.0841 | 1026433.6145 | 1265421.574
[17 empty] | 119 | 2025-03-22 | 230 | 0 | 0 | 1026433.6145 | 1265421.574
[17 empty] | 119 | 2025-03-23 | 231 | 0 | 0 | 1026433.6145 | 1265421.574
[17 empty] | 119 | 2025-03-24 | 232 | 5917.6046 | 7568.0841 | 1032351.2192 | 1272989.6581
[17 empty] | 119 | 2025-03-25 | 233 | 5917.6046 | 7568.0841 | 1038268.8238 | 1280557.7423
[17 empty] | 119 | 2025-03-26 | 234 | 5917.6046 | 7568.0841 | 1044186.4284 | 1288125.8264
[17 empty] | 119 | 2025-03-27 | 235 | 5917.6046 | 7568.0841 | 1050104.033 | 1295693.9105
[17 empty] | 119 | 2025-03-28 | 236 | 5917.6046 | 7568.0841 | 1056021.6376 | 1303261.9946
[17 empty] | 119 | 2025-03-29 | 237 | 0 | 0 | 1056021.6376 | 1303261.9946
[17 empty] | 119 | 2025-03-30 | 238 | 0 | 0 | 1056021.6376 | 1303261.9946
[17 empty] | 119 | 2025-03-31 | 239 | 5917.6046 | 7568.0841 | 1061939.2422 | 1310830.0788
[17 empty] | 119 | 2025-04-01 | 240 | 5917.6046 | 7568.0841 | 1067856.8468 | 1318398.1629
[17 empty] | 119 | 2025-04-02 | 241 | 5917.6046 | 7568.0841 | 1073774.4514 | 1325966.247
[17 empty] | 119 | 2025-04-03 | 242 | 5917.6046 | 7568.0841 | 1079692.056 | 1333534.3311
[17 empty] | 119 | 2025-04-04 | 243 | 644.9773 | 819.1212 | 1080337.0333 | 1334353.4523
[17 empty] | 119 | 2025-04-05 | 244 | 0 | 0 | 1080337.0333 | 1334353.4523
[17 empty] | 119 | 2025-04-06 | 245 | 0 | 0 | 1080337.0333 | 1334353.4523
[17 empty] | 119 | 2025-04-07 | 246 | 644.9773 | 819.1212 | 1080982.0107 | 1335172.5735
[17 empty] | 119 | 2025-04-08 | 247 | 644.9773 | 819.1212 | 1081626.988 | 1335991.6948
[17 empty] | 119 | 2025-04-09 | 248 | 644.9773 | 819.1212 | 1082271.9653 | 1336810.816
[17 empty] | 119 | 2025-04-10 | 249 | 644.9773 | 819.1212 | 1082916.9427 | 1337629.9372
[17 empty] | 119 | 2025-04-11 | 250 | 644.9773 | 819.1212 | 1083561.92 | 1338449.0584
[17 empty] | 119 | 2025-04-12 | 251 | 0 | 0 | 1083561.92 | 1338449.0584
[17 empty] | 119 | 2025-04-13 | 252 | 0 | 0 | 1083561.92 | 1338449.0584
[17 empty] | 120 | 2024-08-20 | 1 | 215.5336 | 256.485 | 215.5336 | 256.485
[17 empty] | 120 | 2024-08-21 | 2 | 215.5336 | 256.485 | 431.0672 | 512.9699
[17 empty] | 120 | 2024-08-22 | 3 | 215.5336 | 256.485 | 646.6008 | 769.4549
[17 empty] | 120 | 2024-08-23 | 4 | 215.5336 | 256.485 | 862.1344 | 1025.9399
[17 empty] | 120 | 2024-08-24 | 5 | 0 | 0 | 862.1344 | 1025.9399
[17 empty] | 120 | 2024-08-25 | 6 | 0 | 0 | 862.1344 | 1025.9399
[17 empty] | 120 | 2024-08-26 | 7 | 1914.5336 | 2159.365 | 2776.668 | 3185.3049
[17 empty] | 120 | 2024-08-27 | 8 | 1914.5336 | 2159.365 | 4691.2015 | 5344.6698
[17 empty] | 120 | 2024-08-28 | 9 | 1914.5336 | 2159.365 | 6605.7351 | 7504.0348
[17 empty] | 120 | 2024-08-29 | 10 | 1914.5336 | 2159.365 | 8520.2687 | 9663.3998
[17 empty] | 120 | 2024-08-30 | 11 | 1914.5336 | 2159.365 | 10434.8023 | 11822.7648
[17 empty] | 120 | 2024-08-31 | 12 | 0 | 0 | 10434.8023 | 11822.7648
[17 empty] | 120 | 2024-09-01 | 13 | 0 | 0 | 10434.8023 | 11822.7648
[17 empty] | 120 | 2024-09-02 | 14 | 1914.5336 | 2159.365 | 12349.3359 | 13982.1297
[17 empty] | 120 | 2024-09-03 | 15 | 1914.5336 | 2159.365 | 14263.8695 | 16141.4947
[17 empty] | 120 | 2024-09-04 | 16 | 1914.5336 | 2159.365 | 16178.4031 | 18300.8597
[17 empty] | 120 | 2024-09-05 | 17 | 1914.5336 | 2159.365 | 18092.9367 | 20460.2246
[17 empty] | 120 | 2024-09-06 | 18 | 1914.5336 | 2159.365 | 20007.4703 | 22619.5896
[17 empty] | 120 | 2024-09-07 | 19 | 0 | 0 | 20007.4703 | 22619.5896
[17 empty] | 120 | 2024-09-08 | 20 | 0 | 0 | 20007.4703 | 22619.5896
[17 empty] | 120 | 2024-09-09 | 21 | 1914.5336 | 2159.365 | 21922.0039 | 24778.9546
[17 empty] | 120 | 2024-09-10 | 22 | 1914.5336 | 2159.365 | 23836.5375 | 26938.3196
[17 empty] | 120 | 2024-09-11 | 23 | 1914.5336 | 2159.365 | 25751.071 | 29097.6845
[17 empty] | 120 | 2024-09-12 | 24 | 1914.5336 | 2159.365 | 27665.6046 | 31257.0495
[17 empty] | 120 | 2024-09-13 | 25 | 4366.2146 | 4954.2814 | 32031.8193 | 36211.3309
[17 empty] | 120 | 2024-09-14 | 26 | 0 | 0 | 32031.8193 | 36211.3309
[17 empty] | 120 | 2024-09-15 | 27 | 0 | 0 | 32031.8193 | 36211.3309
[17 empty] | 120 | 2024-09-16 | 28 | 2667.2146 | 3051.4014 | 34699.0339 | 39262.7322
[17 empty] | 120 | 2024-09-17 | 29 | 2667.2146 | 3051.4014 | 37366.2485 | 42314.1336
[17 empty] | 120 | 2024-09-18 | 30 | 2667.2146 | 3051.4014 | 40033.4631 | 45365.5349
[17 empty] | 120 | 2024-09-19 | 31 | 2667.2146 | 3051.4014 | 42700.6778 | 48416.9363
[17 empty] | 120 | 2024-09-20 | 32 | 2667.2146 | 3051.4014 | 45367.8924 | 51468.3376
[17 empty] | 120 | 2024-09-21 | 33 | 0 | 0 | 45367.8924 | 51468.3376
[17 empty] | 120 | 2024-09-22 | 34 | 0 | 0 | 45367.8924 | 51468.3376
[17 empty] | 120 | 2024-09-23 | 35 | 2667.2146 | 3051.4014 | 48035.107 | 54519.739
[17 empty] | 120 | 2024-09-24 | 36 | 2667.2146 | 3051.4014 | 50702.3216 | 57571.1403
[17 empty] | 120 | 2024-09-25 | 37 | 2667.2146 | 3051.4014 | 53369.5363 | 60622.5417
[17 empty] | 120 | 2024-09-26 | 38 | 2667.2146 | 3051.4014 | 56036.7509 | 63673.943
[17 empty] | 120 | 2024-09-27 | 39 | 2667.2146 | 3051.4014 | 58703.9655 | 66725.3444
[17 empty] | 120 | 2024-09-28 | 40 | 0 | 0 | 58703.9655 | 66725.3444
[17 empty] | 120 | 2024-09-29 | 41 | 0 | 0 | 58703.9655 | 66725.3444
[17 empty] | 120 | 2024-09-30 | 42 | 2667.2146 | 3051.4014 | 61371.1801 | 69776.7457
[17 empty] | 120 | 2024-10-01 | 43 | 2667.2146 | 3051.4014 | 64038.3948 | 72828.1471
[17 empty] | 120 | 2024-10-02 | 44 | 2667.2146 | 3051.4014 | 66705.6094 | 75879.5484
[17 empty] | 120 | 2024-10-03 | 45 | 2667.2146 | 3051.4014 | 69372.824 | 78930.9498
[17 empty] | 120 | 2024-10-04 | 46 | 2667.2146 | 3051.4014 | 72040.0386 | 81982.3512
[17 empty] | 120 | 2024-10-05 | 47 | 0 | 0 | 72040.0386 | 81982.3512
[17 empty] | 120 | 2024-10-06 | 48 | 0 | 0 | 72040.0386 | 81982.3512
[17 empty] | 120 | 2024-10-07 | 49 | 2667.2146 | 3051.4014 | 74707.2533 | 85033.7525
[17 empty] | 120 | 2024-10-08 | 50 | 2667.2146 | 3051.4014 | 77374.4679 | 88085.1539
[17 empty] | 120 | 2024-10-09 | 51 | 2667.2146 | 3051.4014 | 80041.6825 | 91136.5552
[17 empty] | 120 | 2024-10-10 | 52 | 2667.2146 | 3051.4014 | 82708.8971 | 94187.9566
[17 empty] | 120 | 2024-10-11 | 53 | 2667.2146 | 3051.4014 | 85376.1118 | 97239.3579
[17 empty] | 120 | 2024-10-12 | 54 | 0 | 0 | 85376.1118 | 97239.3579
[17 empty] | 120 | 2024-10-13 | 55 | 0 | 0 | 85376.1118 | 97239.3579
[17 empty] | 120 | 2024-10-14 | 56 | 2667.2146 | 3051.4014 | 88043.3264 | 100290.7593
[17 empty] | 120 | 2024-10-15 | 57 | 2667.2146 | 3051.4014 | 90710.541 | 103342.1606
[17 empty] | 120 | 2024-10-16 | 58 | 2667.2146 | 3051.4014 | 93377.7556 | 106393.562
[17 empty] | 120 | 2024-10-17 | 59 | 2667.2146 | 3051.4014 | 96044.9703 | 109444.9633
[17 empty] | 120 | 2024-10-18 | 60 | 2667.2146 | 3051.4014 | 98712.1849 | 112496.3647
[17 empty] | 120 | 2024-10-19 | 61 | 0 | 0 | 98712.1849 | 112496.3647
[17 empty] | 120 | 2024-10-20 | 62 | 0 | 0 | 98712.1849 | 112496.3647
[17 empty] | 120 | 2024-10-21 | 63 | 2667.2146 | 3051.4014 | 101379.3995 | 115547.766
[17 empty] | 120 | 2024-10-22 | 64 | 2667.2146 | 3051.4014 | 104046.6141 | 118599.1674
[17 empty] | 120 | 2024-10-23 | 65 | 2667.2146 | 3051.4014 | 106713.8288 | 121650.5687
[17 empty] | 120 | 2024-10-24 | 66 | 2667.2146 | 3051.4014 | 109381.0434 | 124701.9701
[17 empty] | 120 | 2024-10-25 | 67 | 2667.2146 | 3051.4014 | 112048.258 | 127753.3714
[17 empty] | 120 | 2024-10-26 | 68 | 0 | 0 | 112048.258 | 127753.3714
[17 empty] | 120 | 2024-10-27 | 69 | 0 | 0 | 112048.258 | 127753.3714
[17 empty] | 120 | 2024-10-28 | 70 | 2667.2146 | 3051.4014 | 114715.4726 | 130804.7728
[17 empty] | 120 | 2024-10-29 | 71 | 2667.2146 | 3051.4014 | 117382.6873 | 133856.1741
[17 empty] | 120 | 2024-10-30 | 72 | 2667.2146 | 3051.4014 | 120049.9019 | 136907.5755
[17 empty] | 120 | 2024-10-31 | 73 | 2667.2146 | 3051.4014 | 122717.1165 | 139958.9768
[17 empty] | 120 | 2024-11-01 | 74 | 2667.2146 | 3051.4014 | 125384.3311 | 143010.3782
[17 empty] | 120 | 2024-11-02 | 75 | 0 | 0 | 125384.3311 | 143010.3782
[17 empty] | 120 | 2024-11-03 | 76 | 0 | 0 | 125384.3311 | 143010.3782
[17 empty] | 120 | 2024-11-04 | 77 | 2667.2146 | 3051.4014 | 128051.5458 | 146061.7795
[17 empty] | 120 | 2024-11-05 | 78 | 2667.2146 | 3051.4014 | 130718.7604 | 149113.1809
[17 empty] | 120 | 2024-11-06 | 79 | 2667.2146 | 3051.4014 | 133385.975 | 152164.5823
[17 empty] | 120 | 2024-11-07 | 80 | 2667.2146 | 3051.4014 | 136053.1896 | 155215.9836
[17 empty] | 120 | 2024-11-08 | 81 | 2667.2146 | 3051.4014 | 138720.4043 | 158267.385
[17 empty] | 120 | 2024-11-09 | 82 | 0 | 0 | 138720.4043 | 158267.385
[17 empty] | 120 | 2024-11-10 | 83 | 0 | 0 | 138720.4043 | 158267.385
[17 empty] | 120 | 2024-11-11 | 84 | 2667.2146 | 3051.4014 | 141387.6189 | 161318.7863
[17 empty] | 120 | 2024-11-12 | 85 | 2667.2146 | 3051.4014 | 144054.8335 | 164370.1877
[17 empty] | 120 | 2024-11-13 | 86 | 2667.2146 | 3051.4014 | 146722.0481 | 167421.589
[17 empty] | 120 | 2024-11-14 | 87 | 2667.2146 | 3051.4014 | 149389.2628 | 170472.9904
[17 empty] | 120 | 2024-11-15 | 88 | 2667.2146 | 3051.4014 | 152056.4774 | 173524.3917
[17 empty] | 120 | 2024-11-16 | 89 | 0 | 0 | 152056.4774 | 173524.3917
[17 empty] | 120 | 2024-11-17 | 90 | 0 | 0 | 152056.4774 | 173524.3917
[17 empty] | 120 | 2024-11-18 | 91 | 2667.2146 | 3051.4014 | 154723.692 | 176575.7931
[17 empty] | 120 | 2024-11-19 | 92 | 2667.2146 | 3051.4014 | 157390.9066 | 179627.1944
[17 empty] | 120 | 2024-11-20 | 93 | 2667.2146 | 3051.4014 | 160058.1213 | 182678.5958
[17 empty] | 120 | 2024-11-21 | 94 | 2667.2146 | 3051.4014 | 162725.3359 | 185729.9971
[17 empty] | 120 | 2024-11-22 | 95 | 2667.2146 | 3051.4014 | 165392.5505 | 188781.3985
[17 empty] | 120 | 2024-11-23 | 96 | 0 | 0 | 165392.5505 | 188781.3985
[17 empty] | 120 | 2024-11-24 | 97 | 0 | 0 | 165392.5505 | 188781.3985
[17 empty] | 120 | 2024-11-25 | 98 | 2667.2146 | 3051.4014 | 168059.7651 | 191832.7998
[17 empty] | 120 | 2024-11-26 | 99 | 2667.2146 | 3051.4014 | 170726.9798 | 194884.2012
[17 empty] | 120 | 2024-11-27 | 100 | 2667.2146 | 3051.4014 | 173394.1944 | 197935.6025
[17 empty] | 120 | 2024-11-28 | 101 | 2667.2146 | 3051.4014 | 176061.409 | 200987.0039
[17 empty] | 120 | 2024-11-29 | 102 | 2667.2146 | 3051.4014 | 178728.6236 | 204038.4052
[17 empty] | 120 | 2024-11-30 | 103 | 0 | 0 | 178728.6236 | 204038.4052
[17 empty] | 120 | 2024-12-01 | 104 | 0 | 0 | 178728.6236 | 204038.4052
[17 empty] | 120 | 2024-12-02 | 105 | 2667.2146 | 3051.4014 | 181395.8383 | 207089.8066
[17 empty] | 120 | 2024-12-03 | 106 | 2667.2146 | 3051.4014 | 184063.0529 | 210141.2079
[17 empty] | 120 | 2024-12-04 | 107 | 2667.2146 | 3051.4014 | 186730.2675 | 213192.6093
[17 empty] | 120 | 2024-12-05 | 108 | 2667.2146 | 3051.4014 | 189397.4821 | 216244.0107
[17 empty] | 120 | 2024-12-06 | 109 | 2667.2146 | 3051.4014 | 192064.6968 | 219295.412
[17 empty] | 120 | 2024-12-07 | 110 | 0 | 0 | 192064.6968 | 219295.412
[17 empty] | 120 | 2024-12-08 | 111 | 0 | 0 | 192064.6968 | 219295.412
[17 empty] | 120 | 2024-12-09 | 112 | 2667.2146 | 3051.4014 | 194731.9114 | 222346.8134
[17 empty] | 120 | 2024-12-10 | 113 | 2667.2146 | 3051.4014 | 197399.126 | 225398.2147
[17 empty] | 120 | 2024-12-11 | 114 | 2667.2146 | 3051.4014 | 200066.3406 | 228449.6161
[17 empty] | 120 | 2024-12-12 | 115 | 2667.2146 | 3051.4014 | 202733.5553 | 231501.0174
[17 empty] | 120 | 2024-12-13 | 116 | 2667.2146 | 3051.4014 | 205400.7699 | 234552.4188
[17 empty] | 120 | 2024-12-14 | 117 | 0 | 0 | 205400.7699 | 234552.4188
[17 empty] | 120 | 2024-12-15 | 118 | 0 | 0 | 205400.7699 | 234552.4188
[17 empty] | 120 | 2024-12-16 | 119 | 2667.2146 | 3051.4014 | 208067.9845 | 237603.8201
[17 empty] | 120 | 2024-12-17 | 120 | 2667.2146 | 3051.4014 | 210735.1991 | 240655.2215
[17 empty] | 120 | 2024-12-18 | 121 | 2667.2146 | 3051.4014 | 213402.4138 | 243706.6228
[17 empty] | 120 | 2024-12-19 | 122 | 2667.2146 | 3051.4014 | 216069.6284 | 246758.0242
[17 empty] | 120 | 2024-12-20 | 123 | 2667.2146 | 3051.4014 | 218736.843 | 249809.4255
[17 empty] | 120 | 2024-12-21 | 124 | 0 | 0 | 218736.843 | 249809.4255
[17 empty] | 120 | 2024-12-22 | 125 | 0 | 0 | 218736.843 | 249809.4255
[17 empty] | 120 | 2024-12-23 | 126 | 2667.2146 | 3051.4014 | 221404.0576 | 252860.8269
[17 empty] | 120 | 2024-12-24 | 127 | 2667.2146 | 3051.4014 | 224071.2723 | 255912.2282
[17 empty] | 120 | 2024-12-25 | 128 | 2667.2146 | 3051.4014 | 226738.4869 | 258963.6296
[17 empty] | 120 | 2024-12-26 | 129 | 2667.2146 | 3051.4014 | 229405.7015 | 262015.0309
[17 empty] | 120 | 2024-12-27 | 130 | 2667.2146 | 3051.4014 | 232072.9161 | 265066.4323
[17 empty] | 120 | 2024-12-28 | 131 | 0 | 0 | 232072.9161 | 265066.4323
[17 empty] | 120 | 2024-12-29 | 132 | 0 | 0 | 232072.9161 | 265066.4323
[17 empty] | 120 | 2024-12-30 | 133 | 2667.2146 | 3051.4014 | 234740.1308 | 268117.8336
[17 empty] | 120 | 2024-12-31 | 134 | 2667.2146 | 3051.4014 | 237407.3454 | 271169.235
[17 empty] | 120 | 2025-01-01 | 135 | 2667.2146 | 3051.4014 | 240074.56 | 274220.6363
[17 empty] | 120 | 2025-01-02 | 136 | 2667.2146 | 3051.4014 | 242741.7747 | 277272.0377
[17 empty] | 120 | 2025-01-03 | 137 | 2667.2146 | 3051.4014 | 245408.9893 | 280323.439
[17 empty] | 120 | 2025-01-04 | 138 | 0 | 0 | 245408.9893 | 280323.439
[17 empty] | 120 | 2025-01-05 | 139 | 0 | 0 | 245408.9893 | 280323.439
[17 empty] | 120 | 2025-01-06 | 140 | 2667.2146 | 3051.4014 | 248076.2039 | 283374.8404
[17 empty] | 120 | 2025-01-07 | 141 | 2667.2146 | 3051.4014 | 250743.4185 | 286426.2418
[17 empty] | 120 | 2025-01-08 | 142 | 2667.2146 | 3051.4014 | 253410.6332 | 289477.6431
[17 empty] | 120 | 2025-01-09 | 143 | 2667.2146 | 3051.4014 | 256077.8478 | 292529.0445
[17 empty] | 120 | 2025-01-10 | 144 | 2667.2146 | 3051.4014 | 258745.0624 | 295580.4458
[17 empty] | 120 | 2025-01-11 | 145 | 0 | 0 | 258745.0624 | 295580.4458
[17 empty] | 120 | 2025-01-12 | 146 | 0 | 0 | 258745.0624 | 295580.4458
[17 empty] | 120 | 2025-01-13 | 147 | 2667.2146 | 3051.4014 | 261412.277 | 298631.8472
[17 empty] | 120 | 2025-01-14 | 148 | 2667.2146 | 3051.4014 | 264079.4917 | 301683.2485
[17 empty] | 120 | 2025-01-15 | 149 | 2667.2146 | 3051.4014 | 266746.7063 | 304734.6499
[17 empty] | 120 | 2025-01-16 | 150 | 2667.2146 | 3051.4014 | 269413.9209 | 307786.0512
[17 empty] | 120 | 2025-01-17 | 151 | 2667.2146 | 3051.4014 | 272081.1355 | 310837.4526
[17 empty] | 120 | 2025-01-18 | 152 | 0 | 0 | 272081.1355 | 310837.4526
[17 empty] | 120 | 2025-01-19 | 153 | 0 | 0 | 272081.1355 | 310837.4526
[17 empty] | 120 | 2025-01-20 | 154 | 2667.2146 | 3051.4014 | 274748.3502 | 313888.8539
[17 empty] | 120 | 2025-01-21 | 155 | 2667.2146 | 3051.4014 | 277415.5648 | 316940.2553
[17 empty] | 120 | 2025-01-22 | 156 | 2667.2146 | 3051.4014 | 280082.7794 | 319991.6566
[17 empty] | 120 | 2025-01-23 | 157 | 2667.2146 | 3051.4014 | 282749.994 | 323043.058
[17 empty] | 120 | 2025-01-24 | 158 | 2667.2146 | 3051.4014 | 285417.2087 | 326094.4593
[17 empty] | 120 | 2025-01-25 | 159 | 0 | 0 | 285417.2087 | 326094.4593
[17 empty] | 120 | 2025-01-26 | 160 | 0 | 0 | 285417.2087 | 326094.4593
[17 empty] | 120 | 2025-01-27 | 161 | 2667.2146 | 3051.4014 | 288084.4233 | 329145.8607
[17 empty] | 120 | 2025-01-28 | 162 | 2667.2146 | 3051.4014 | 290751.6379 | 332197.262
[17 empty] | 120 | 2025-01-29 | 163 | 2667.2146 | 3051.4014 | 293418.8525 | 335248.6634
[17 empty] | 120 | 2025-01-30 | 164 | 2667.2146 | 3051.4014 | 296086.0672 | 338300.0647
[17 empty] | 120 | 2025-01-31 | 165 | 2667.2146 | 3051.4014 | 298753.2818 | 341351.4661
[17 empty] | 120 | 2025-02-01 | 166 | 0 | 0 | 298753.2818 | 341351.4661
[17 empty] | 120 | 2025-02-02 | 167 | 0 | 0 | 298753.2818 | 341351.4661
[17 empty] | 120 | 2025-02-03 | 168 | 5671.2146 | 6896.5214 | 304424.4964 | 348247.9874
[17 empty] | 120 | 2025-02-04 | 169 | 5671.2146 | 6896.5214 | 310095.711 | 355144.5088
[17 empty] | 120 | 2025-02-05 | 170 | 5671.2146 | 6896.5214 | 315766.9257 | 362041.0302
[17 empty] | 120 | 2025-02-06 | 171 | 5671.2146 | 6896.5214 | 321438.1403 | 368937.5515
[17 empty] | 120 | 2025-02-07 | 172 | 5671.2146 | 6896.5214 | 327109.3549 | 375834.0729
[17 empty] | 120 | 2025-02-08 | 173 | 0 | 0 | 327109.3549 | 375834.0729
[17 empty] | 120 | 2025-02-09 | 174 | 0 | 0 | 327109.3549 | 375834.0729
[17 empty] | 120 | 2025-02-10 | 175 | 5671.2146 | 6896.5214 | 332780.5695 | 382730.5942
[17 empty] | 120 | 2025-02-11 | 176 | 7779.4823 | 9574.0214 | 340560.0519 | 392304.6156
[17 empty] | 120 | 2025-02-12 | 177 | 7779.4823 | 9574.0214 | 348339.5342 | 401878.6369
[17 empty] | 120 | 2025-02-13 | 178 | 7779.4823 | 9574.0214 | 356119.0166 | 411452.6583
[17 empty] | 120 | 2025-02-14 | 179 | 7779.4823 | 9574.0214 | 363898.4989 | 421026.6796
[17 empty] | 120 | 2025-02-15 | 180 | 0 | 0 | 363898.4989 | 421026.6796
[17 empty] | 120 | 2025-02-16 | 181 | 0 | 0 | 363898.4989 | 421026.6796
[17 empty] | 120 | 2025-02-17 | 182 | 7779.4823 | 9574.0214 | 371677.9812 | 430600.701
[17 empty] | 120 | 2025-02-18 | 183 | 7779.4823 | 9574.0214 | 379457.4636 | 440174.7223
[17 empty] | 120 | 2025-02-19 | 184 | 7779.4823 | 9574.0214 | 387236.9459 | 449748.7437
[17 empty] | 120 | 2025-02-20 | 185 | 7779.4823 | 9574.0214 | 395016.4283 | 459322.765
[17 empty] | 120 | 2025-02-21 | 186 | 7779.4823 | 9574.0214 | 402795.9106 | 468896.7864
[17 empty] | 120 | 2025-02-22 | 187 | 0 | 0 | 402795.9106 | 468896.7864
[17 empty] | 120 | 2025-02-23 | 188 | 0 | 0 | 402795.9106 | 468896.7864
[17 empty] | 120 | 2025-02-24 | 189 | 5327.8013 | 6779.105 | 408123.7119 | 475675.8914
[17 empty] | 120 | 2025-02-25 | 190 | 5327.8013 | 6779.105 | 413451.5132 | 482454.9963
[17 empty] | 120 | 2025-02-26 | 191 | 5327.8013 | 6779.105 | 418779.3145 | 489234.1013
[17 empty] | 120 | 2025-02-27 | 192 | 5327.8013 | 6779.105 | 424107.1158 | 496013.2063
[17 empty] | 120 | 2025-02-28 | 193 | 5327.8013 | 6779.105 | 429434.9171 | 502792.3112
[17 empty] | 120 | 2025-03-01 | 194 | 0 | 0 | 429434.9171 | 502792.3112
[17 empty] | 120 | 2025-03-02 | 195 | 0 | 0 | 429434.9171 | 502792.3112
[17 empty] | 120 | 2025-03-03 | 196 | 5327.8013 | 6779.105 | 434762.7185 | 509571.4162
[17 empty] | 120 | 2025-03-04 | 197 | 5327.8013 | 6779.105 | 440090.5198 | 516350.5212
[17 empty] | 120 | 2025-03-05 | 198 | 5327.8013 | 6779.105 | 445418.3211 | 523129.6262
[17 empty] | 120 | 2025-03-06 | 199 | 5327.8013 | 6779.105 | 450746.1224 | 529908.7311
[17 empty] | 120 | 2025-03-07 | 200 | 5327.8013 | 6779.105 | 456073.9237 | 536687.8361
[17 empty] | 120 | 2025-03-08 | 201 | 0 | 0 | 456073.9237 | 536687.8361
[17 empty] | 120 | 2025-03-09 | 202 | 0 | 0 | 456073.9237 | 536687.8361
[17 empty] | 120 | 2025-03-10 | 203 | 5327.8013 | 6779.105 | 461401.725 | 543466.9411
[17 empty] | 120 | 2025-03-11 | 204 | 5327.8013 | 6779.105 | 466729.5263 | 550246.0461
[17 empty] | 120 | 2025-03-12 | 205 | 5327.8013 | 6779.105 | 472057.3276 | 557025.151
[17 empty] | 120 | 2025-03-13 | 206 | 5327.8013 | 6779.105 | 477385.1289 | 563804.256
[17 empty] | 120 | 2025-03-14 | 207 | 5327.8013 | 6779.105 | 482712.9302 | 570583.361
[17 empty] | 120 | 2025-03-15 | 208 | 0 | 0 | 482712.9302 | 570583.361
[17 empty] | 120 | 2025-03-16 | 209 | 0 | 0 | 482712.9302 | 570583.361
[17 empty] | 120 | 2025-03-17 | 210 | 5327.8013 | 6779.105 | 488040.7315 | 577362.4659
[17 empty] | 120 | 2025-03-18 | 211 | 5327.8013 | 6779.105 | 493368.5328 | 584141.5709
[17 empty] | 120 | 2025-03-19 | 212 | 5327.8013 | 6779.105 | 498696.3341 | 590920.6759
[17 empty] | 120 | 2025-03-20 | 213 | 5327.8013 | 6779.105 | 504024.1354 | 597699.7809
[17 empty] | 120 | 2025-03-21 | 214 | 5327.8013 | 6779.105 | 509351.9368 | 604478.8858
[17 empty] | 120 | 2025-03-22 | 215 | 0 | 0 | 509351.9368 | 604478.8858
[17 empty] | 120 | 2025-03-23 | 216 | 0 | 0 | 509351.9368 | 604478.8858
[17 empty] | 120 | 2025-03-24 | 217 | 5327.8013 | 6779.105 | 514679.7381 | 611257.9908
[17 empty] | 120 | 2025-03-25 | 218 | 5327.8013 | 6779.105 | 520007.5394 | 618037.0958
[17 empty] | 120 | 2025-03-26 | 219 | 5327.8013 | 6779.105 | 525335.3407 | 624816.2008
[17 empty] | 120 | 2025-03-27 | 220 | 5327.8013 | 6779.105 | 530663.142 | 631595.3057
[17 empty] | 120 | 2025-03-28 | 221 | 5327.8013 | 6779.105 | 535990.9433 | 638374.4107
[17 empty] | 120 | 2025-03-29 | 222 | 0 | 0 | 535990.9433 | 638374.4107
[17 empty] | 120 | 2025-03-30 | 223 | 0 | 0 | 535990.9433 | 638374.4107
[17 empty] | 120 | 2025-03-31 | 224 | 2323.8013 | 2933.985 | 538314.7446 | 641308.3957
[17 empty] | 120 | 2025-04-01 | 225 | 2323.8013 | 2933.985 | 540638.5459 | 644242.3806
[17 empty] | 120 | 2025-04-02 | 226 | 2323.8013 | 2933.985 | 542962.3472 | 647176.3656
[17 empty] | 120 | 2025-04-03 | 227 | 2323.8013 | 2933.985 | 545286.1485 | 650110.3506
[17 empty] | 120 | 2025-04-04 | 228 | 2323.8013 | 2933.985 | 547609.9498 | 653044.3356
[17 empty] | 120 | 2025-04-05 | 229 | 0 | 0 | 547609.9498 | 653044.3356
[17 empty] | 120 | 2025-04-06 | 230 | 0 | 0 | 547609.9498 | 653044.3356
[17 empty] | 120 | 2025-04-07 | 231 | 2323.8013 | 2933.985 | 549933.7511 | 655978.3205
[17 empty] | 120 | 2025-04-08 | 232 | 2323.8013 | 2933.985 | 552257.5524 | 658912.3055
[17 empty] | 120 | 2025-04-09 | 233 | 2323.8013 | 2933.985 | 554581.3537 | 661846.2905
[17 empty] | 120 | 2025-04-10 | 234 | 2323.8013 | 2933.985 | 556905.1551 | 664780.2755
[17 empty] | 120 | 2025-04-11 | 235 | 2323.8013 | 2933.985 | 559228.9564 | 667714.2604
[17 empty] | 120 | 2025-04-12 | 236 | 0 | 0 | 559228.9564 | 667714.2604
[17 empty] | 120 | 2025-04-13 | 237 | 0 | 0 | 559228.9564 | 667714.2604
[17 empty] | 120 | 2025-04-14 | 238 | 2323.8013 | 2933.985 | 561552.7577 | 670648.2454
[17 empty] | 120 | 2025-04-15 | 239 | 2323.8013 | 2933.985 | 563876.559 | 673582.2304
[17 empty] | 120 | 2025-04-16 | 240 | 2323.8013 | 2933.985 | 566200.3603 | 676516.2154
[17 empty] | 120 | 2025-04-17 | 241 | 2323.8013 | 2933.985 | 568524.1616 | 679450.2003
[17 empty] | 120 | 2025-04-18 | 242 | 2323.8013 | 2933.985 | 570847.9629 | 682384.1853
[17 empty] | 120 | 2025-04-19 | 243 | 0 | 0 | 570847.9629 | 682384.1853
[17 empty] | 120 | 2025-04-20 | 244 | 0 | 0 | 570847.9629 | 682384.1853
[17 empty] | 120 | 2025-04-21 | 245 | 2323.8013 | 2933.985 | 573171.7642 | 685318.1703
[17 empty] | 120 | 2025-04-22 | 246 | 2323.8013 | 2933.985 | 575495.5655 | 688252.1552
[17 empty] | 120 | 2025-04-23 | 247 | 2323.8013 | 2933.985 | 577819.3668 | 691186.1402
[17 empty] | 120 | 2025-04-24 | 248 | 2323.8013 | 2933.985 | 580143.1681 | 694120.1252
[17 empty] | 120 | 2025-04-25 | 249 | 2323.8013 | 2933.985 | 582466.9694 | 697054.1102
[17 empty] | 120 | 2025-04-26 | 250 | 0 | 0 | 582466.9694 | 697054.1102
[17 empty] | 120 | 2025-04-27 | 251 | 0 | 0 | 582466.9694 | 697054.1102
[17 empty] | 120 | 2025-04-28 | 252 | 2323.8013 | 2933.985 | 584790.7707 | 699988.0951
[17 empty] | 120 | 2025-04-29 | 253 | 2323.8013 | 2933.985 | 587114.572 | 702922.0801
[17 empty] | 120 | 2025-04-30 | 254 | 2323.8013 | 2933.985 | 589438.3734 | 705856.0651
[17 empty] | 120 | 2025-05-01 | 255 | 2323.8013 | 2933.985 | 591762.1747 | 708790.0501
[17 empty] | 120 | 2025-05-02 | 256 | 2323.8013 | 2933.985 | 594085.976 | 711724.035
[17 empty] | 120 | 2025-05-03 | 257 | 0 | 0 | 594085.976 | 711724.035
[17 empty] | 120 | 2025-05-04 | 258 | 0 | 0 | 594085.976 | 711724.035
[17 empty] | 120 | 2025-05-05 | 259 | 2323.8013 | 2933.985 | 596409.7773 | 714658.02
[17 empty] | 120 | 2025-05-06 | 260 | 2323.8013 | 2933.985 | 598733.5786 | 717592.005
[17 empty] | 120 | 2025-05-07 | 261 | 2323.8013 | 2933.985 | 601057.3799 | 720525.9899
[17 empty] | 120 | 2025-05-08 | 262 | 2323.8013 | 2933.985 | 603381.1812 | 723459.9749
[17 empty] | 120 | 2025-05-09 | 263 | 2323.8013 | 2933.985 | 605704.9825 | 726393.9599
[17 empty] | 120 | 2025-05-10 | 264 | 0 | 0 | 605704.9825 | 726393.9599
[17 empty] | 120 | 2025-05-11 | 265 | 0 | 0 | 605704.9825 | 726393.9599
[17 empty] | 120 | 2025-05-12 | 266 | 2323.8013 | 2933.985 | 608028.7838 | 729327.9449
[17 empty] | 120 | 2025-05-13 | 267 | 2323.8013 | 2933.985 | 610352.5851 | 732261.9298
[17 empty] | 120 | 2025-05-14 | 268 | 2323.8013 | 2933.985 | 612676.3864 | 735195.9148
[17 empty] | 120 | 2025-05-15 | 269 | 2323.8013 | 2933.985 | 615000.1877 | 738129.8998
[17 empty] | 120 | 2025-05-16 | 270 | 2323.8013 | 2933.985 | 617323.989 | 741063.8848
[17 empty] | 120 | 2025-05-17 | 271 | 0 | 0 | 617323.989 | 741063.8848
[17 empty] | 120 | 2025-05-18 | 272 | 0 | 0 | 617323.989 | 741063.8848
[17 empty] | 120 | 2025-05-19 | 273 | 2323.8013 | 2933.985 | 619647.7904 | 743997.8697
[17 empty] | 120 | 2025-05-20 | 274 | 2323.8013 | 2933.985 | 621971.5917 | 746931.8547
[17 empty] | 120 | 2025-05-21 | 275 | 2323.8013 | 2933.985 | 624295.393 | 749865.8397
[17 empty] | 120 | 2025-05-22 | 276 | 2323.8013 | 2933.985 | 626619.1943 | 752799.8246
[17 empty] | 120 | 2025-05-23 | 277 | 2323.8013 | 2933.985 | 628942.9956 | 755733.8096
[17 empty] | 120 | 2025-05-24 | 278 | 0 | 0 | 628942.9956 | 755733.8096
[17 empty] | 120 | 2025-05-25 | 279 | 0 | 0 | 628942.9956 | 755733.8096
[17 empty] | 120 | 2025-05-26 | 280 | 2323.8013 | 2933.985 | 631266.7969 | 758667.7946
[17 empty] | 120 | 2025-05-27 | 281 | 2323.8013 | 2933.985 | 633590.5982 | 761601.7796
[17 empty] | 120 | 2025-05-28 | 282 | 2323.8013 | 2933.985 | 635914.3995 | 764535.7645
[17 empty] | 120 | 2025-05-29 | 283 | 2323.8013 | 2933.985 | 638238.2008 | 767469.7495
[17 empty] | 120 | 2025-05-30 | 284 | 2323.8013 | 2933.985 | 640562.0021 | 770403.7345
[17 empty] | 120 | 2025-05-31 | 285 | 0 | 0 | 640562.0021 | 770403.7345
[17 empty] | 120 | 2025-06-01 | 286 | 0 | 0 | 640562.0021 | 770403.7345
[17 empty] | 120 | 2025-06-02 | 287 | 2323.8013 | 2933.985 | 642885.8034 | 773337.7195
[17 empty] | 120 | 2025-06-03 | 288 | 2323.8013 | 2933.985 | 645209.6047 | 776271.7044
[17 empty] | 120 | 2025-06-04 | 289 | 2323.8013 | 2933.985 | 647533.406 | 779205.6894
[17 empty] | 120 | 2025-06-05 | 290 | 2323.8013 | 2933.985 | 649857.2073 | 782139.6744
[17 empty] | 120 | 2025-06-06 | 291 | 2323.8013 | 2933.985 | 652181.0087 | 785073.6594
[17 empty] | 120 | 2025-06-07 | 292 | 0 | 0 | 652181.0087 | 785073.6594
[17 empty] | 120 | 2025-06-08 | 293 | 0 | 0 | 652181.0087 | 785073.6594
[17 empty] | 120 | 2025-06-09 | 294 | 2323.8013 | 2933.985 | 654504.81 | 788007.6443
[17 empty] | 120 | 2025-06-10 | 295 | 2323.8013 | 2933.985 | 656828.6113 | 790941.6293
[17 empty] | 120 | 2025-06-11 | 296 | 2323.8013 | 2933.985 | 659152.4126 | 793875.6143
[17 empty] | 120 | 2025-06-12 | 297 | 2323.8013 | 2933.985 | 661476.2139 | 796809.5992
[17 empty] | 120 | 2025-06-13 | 298 | 2323.8013 | 2933.985 | 663800.0152 | 799743.5842
[17 empty] | 120 | 2025-06-14 | 299 | 0 | 0 | 663800.0152 | 799743.5842
[17 empty] | 120 | 2025-06-15 | 300 | 0 | 0 | 663800.0152 | 799743.5842
[17 empty] | 120 | 2025-06-16 | 301 | 2323.8013 | 2933.985 | 666123.8165 | 802677.5692
[17 empty] | 120 | 2025-06-17 | 302 | 2323.8013 | 2933.985 | 668447.6178 | 805611.5542
[17 empty] | 120 | 2025-06-18 | 303 | 2323.8013 | 2933.985 | 670771.4191 | 808545.5391
[17 empty] | 120 | 2025-06-19 | 304 | 2323.8013 | 2933.985 | 673095.2204 | 811479.5241
[17 empty] | 120 | 2025-06-20 | 305 | 2323.8013 | 2933.985 | 675419.0217 | 814413.5091
[17 empty] | 120 | 2025-06-21 | 306 | 0 | 0 | 675419.0217 | 814413.5091
[17 empty] | 120 | 2025-06-22 | 307 | 0 | 0 | 675419.0217 | 814413.5091
[17 empty] | 120 | 2025-06-23 | 308 | 2323.8013 | 2933.985 | 677742.823 | 817347.4941
[17 empty] | 120 | 2025-06-24 | 309 | 2323.8013 | 2933.985 | 680066.6243 | 820281.479
[17 empty] | 120 | 2025-06-25 | 310 | 2323.8013 | 2933.985 | 682390.4256 | 823215.464
[17 empty] | 120 | 2025-06-26 | 311 | 2323.8013 | 2933.985 | 684714.227 | 826149.449
[17 empty] | 120 | 2025-06-27 | 312 | 2323.8013 | 2933.985 | 687038.0283 | 829083.4339
[17 empty] | 120 | 2025-06-28 | 313 | 0 | 0 | 687038.0283 | 829083.4339
[17 empty] | 120 | 2025-06-29 | 314 | 0 | 0 | 687038.0283 | 829083.4339
[17 empty] | 120 | 2025-06-30 | 315 | 2323.8013 | 2933.985 | 689361.8296 | 832017.4189
[17 empty] | 120 | 2025-07-01 | 316 | 2323.8013 | 2933.985 | 691685.6309 | 834951.4039
[17 empty] | 120 | 2025-07-02 | 317 | 2323.8013 | 2933.985 | 694009.4322 | 837885.3889
[17 empty] | 120 | 2025-07-03 | 318 | 2323.8013 | 2933.985 | 696333.2335 | 840819.3738
[17 empty] | 120 | 2025-07-04 | 319 | 2323.8013 | 2933.985 | 698657.0348 | 843753.3588
[17 empty] | 120 | 2025-07-05 | 320 | 0 | 0 | 698657.0348 | 843753.3588
[17 empty] | 120 | 2025-07-06 | 321 | 0 | 0 | 698657.0348 | 843753.3588
[17 empty] | 120 | 2025-07-07 | 322 | 2323.8013 | 2933.985 | 700980.8361 | 846687.3438
[17 empty] | 120 | 2025-07-08 | 323 | 2323.8013 | 2933.985 | 703304.6374 | 849621.3288
[17 empty] | 120 | 2025-07-09 | 324 | 2323.8013 | 2933.985 | 705628.4387 | 852555.3137
[17 empty] | 120 | 2025-07-10 | 325 | 2323.8013 | 2933.985 | 707952.24 | 855489.2987
[17 empty] | 120 | 2025-07-11 | 326 | 2323.8013 | 2933.985 | 710276.0413 | 858423.2837
[17 empty] | 120 | 2025-07-12 | 327 | 0 | 0 | 710276.0413 | 858423.2837
[17 empty] | 120 | 2025-07-13 | 328 | 0 | 0 | 710276.0413 | 858423.2837
[17 empty] | 120 | 2025-07-14 | 329 | 2323.8013 | 2933.985 | 712599.8426 | 861357.2686
[17 empty] | 120 | 2025-07-15 | 330 | 2323.8013 | 2933.985 | 714923.6439 | 864291.2536
[17 empty] | 120 | 2025-07-16 | 331 | 2323.8013 | 2933.985 | 717247.4453 | 867225.2386
[17 empty] | 120 | 2025-07-17 | 332 | 2323.8013 | 2933.985 | 719571.2466 | 870159.2236
[17 empty] | 120 | 2025-07-18 | 333 | 2323.8013 | 2933.985 | 721895.0479 | 873093.2085
[17 empty] | 120 | 2025-07-19 | 334 | 0 | 0 | 721895.0479 | 873093.2085
[17 empty] | 120 | 2025-07-20 | 335 | 0 | 0 | 721895.0479 | 873093.2085
[17 empty] | 120 | 2025-07-21 | 336 | 2323.8013 | 2933.985 | 724218.8492 | 876027.1935
[17 empty] | 120 | 2025-07-22 | 337 | 2323.8013 | 2933.985 | 726542.6505 | 878961.1785
[17 empty] | 120 | 2025-07-23 | 338 | 2323.8013 | 2933.985 | 728866.4518 | 881895.1635
[17 empty] | 120 | 2025-07-24 | 339 | 2323.8013 | 2933.985 | 731190.2531 | 884829.1484
[17 empty] | 120 | 2025-07-25 | 340 | 2323.8013 | 2933.985 | 733514.0544 | 887763.1334
[17 empty] | 120 | 2025-07-26 | 341 | 0 | 0 | 733514.0544 | 887763.1334
[17 empty] | 120 | 2025-07-27 | 342 | 0 | 0 | 733514.0544 | 887763.1334
[17 empty] | 120 | 2025-07-28 | 343 | 2323.8013 | 2933.985 | 735837.8557 | 890697.1184
[17 empty] | 120 | 2025-07-29 | 344 | 2323.8013 | 2933.985 | 738161.657 | 893631.1034
[17 empty] | 120 | 2025-07-30 | 345 | 2323.8013 | 2933.985 | 740485.4583 | 896565.0883
[17 empty] | 120 | 2025-07-31 | 346 | 2323.8013 | 2933.985 | 742809.2596 | 899499.0733
[17 empty] | 120 | 2025-08-01 | 347 | 2323.8013 | 2933.985 | 745133.0609 | 902433.0583
[17 empty] | 120 | 2025-08-02 | 348 | 0 | 0 | 745133.0609 | 902433.0583
[17 empty] | 120 | 2025-08-03 | 349 | 0 | 0 | 745133.0609 | 902433.0583
[17 empty] | 120 | 2025-08-04 | 350 | 2323.8013 | 2933.985 | 747456.8623 | 905367.0432
[17 empty] | 120 | 2025-08-05 | 351 | 2323.8013 | 2933.985 | 749780.6636 | 908301.0282
[17 empty] | 120 | 2025-08-06 | 352 | 2323.8013 | 2933.985 | 752104.4649 | 911235.0132
[17 empty] | 120 | 2025-08-07 | 353 | 215.5336 | 256.485 | 752319.9985 | 911491.4982
[17 empty] | 120 | 2025-08-08 | 354 | 215.5336 | 256.485 | 752535.532 | 911747.9831
[17 empty] | 120 | 2025-08-09 | 355 | 0 | 0 | 752535.532 | 911747.9831
[17 empty] | 120 | 2025-08-10 | 356 | 0 | 0 | 752535.532 | 911747.9831
[17 empty] | 120 | 2025-08-11 | 357 | 215.5336 | 256.485 | 752751.0656 | 912004.4681
[17 empty] | 120 | 2025-08-12 | 358 | 215.5336 | 256.485 | 752966.5992 | 912260.9531
[17 empty] | 120 | 2025-08-13 | 359 | 215.5336 | 256.485 | 753182.1328 | 912517.4381
[17 empty] | 120 | 2025-08-14 | 360 | 215.5336 | 256.485 | 753397.6664 | 912773.923
[17 empty] | 120 | 2025-08-15 | 361 | 215.5336 | 256.485 | 753613.2 | 913030.408
[17 empty] | 120 | 2025-08-16 | 362 | 0 | 0 | 753613.2 | 913030.408
[17 empty] | 121 | 2024-09-05 | 1 | 220.5053 | 280.0418 | 220.5053 | 280.0418
[17 empty] | 121 | 2024-09-06 | 2 | 220.5053 | 280.0418 | 441.0106 | 560.0835
[17 empty] | 121 | 2024-09-07 | 3 | 0 | 0 | 441.0106 | 560.0835
[17 empty] | 121 | 2024-09-08 | 4 | 0 | 0 | 441.0106 | 560.0835
[17 empty] | 121 | 2024-09-09 | 5 | 220.5053 | 280.0418 | 661.5159 | 840.1253
[17 empty] | 121 | 2024-09-10 | 6 | 1511.4144 | 1816.2236 | 2172.9304 | 2656.3488
[17 empty] | 121 | 2024-09-11 | 7 | 1511.4144 | 1816.2236 | 3684.3448 | 4472.5724
[17 empty] | 121 | 2024-09-12 | 8 | 1511.4144 | 1816.2236 | 5195.7592 | 6288.796
[17 empty] | 121 | 2024-09-13 | 9 | 1511.4144 | 1816.2236 | 6707.1736 | 8105.0195
[17 empty] | 121 | 2024-09-14 | 10 | 0 | 0 | 6707.1736 | 8105.0195
[17 empty] | 121 | 2024-09-15 | 11 | 0 | 0 | 6707.1736 | 8105.0195
[17 empty] | 121 | 2024-09-16 | 12 | 1754.5173 | 2110.378 | 8461.6908 | 10215.3976
[17 empty] | 121 | 2024-09-17 | 13 | 1754.5173 | 2110.378 | 10216.2081 | 12325.7756
[17 empty] | 121 | 2024-09-18 | 14 | 1754.5173 | 2110.378 | 11970.7254 | 14436.1536
[17 empty] | 121 | 2024-09-19 | 15 | 1754.5173 | 2110.378 | 13725.2426 | 16546.5316
[17 empty] | 121 | 2024-09-20 | 16 | 3308.6636 | 4068.6024 | 17033.9062 | 20615.1341
[17 empty] | 121 | 2024-09-21 | 17 | 0 | 0 | 17033.9062 | 20615.1341
[17 empty] | 121 | 2024-09-22 | 18 | 0 | 0 | 17033.9062 | 20615.1341
[17 empty] | 121 | 2024-09-23 | 19 | 3308.6636 | 4068.6024 | 20342.5698 | 24683.7365
[17 empty] | 121 | 2024-09-24 | 20 | 5690.6346 | 6855.5085 | 26033.2045 | 31539.245
[17 empty] | 121 | 2024-09-25 | 21 | 4399.7255 | 5319.3267 | 30432.93 | 36858.5717
[17 empty] | 121 | 2024-09-26 | 22 | 4399.7255 | 5319.3267 | 34832.6555 | 42177.8984
[17 empty] | 121 | 2024-09-27 | 23 | 4399.7255 | 5319.3267 | 39232.3811 | 47497.225
[17 empty] | 121 | 2024-09-28 | 24 | 0 | 0 | 39232.3811 | 47497.225
[17 empty] | 121 | 2024-09-29 | 25 | 0 | 0 | 39232.3811 | 47497.225
[17 empty] | 121 | 2024-09-30 | 26 | 4399.7255 | 5319.3267 | 43632.1066 | 52816.5517
[17 empty] | 121 | 2024-10-01 | 27 | 4399.7255 | 5319.3267 | 48031.8321 | 58135.8784
[17 empty] | 121 | 2024-10-02 | 28 | 4399.7255 | 5319.3267 | 52431.5576 | 63455.2051
[17 empty] | 121 | 2024-10-03 | 29 | 4399.7255 | 5319.3267 | 56831.2832 | 68774.5318
[17 empty] | 121 | 2024-10-04 | 30 | 4399.7255 | 5319.3267 | 61231.0087 | 74093.8585
[17 empty] | 121 | 2024-10-05 | 31 | 0 | 0 | 61231.0087 | 74093.8585
[17 empty] | 121 | 2024-10-06 | 32 | 0 | 0 | 61231.0087 | 74093.8585
[17 empty] | 121 | 2024-10-07 | 33 | 4399.7255 | 5319.3267 | 65630.7342 | 79413.1852
[17 empty] | 121 | 2024-10-08 | 34 | 4399.7255 | 5319.3267 | 70030.4598 | 84732.5118
[17 empty] | 121 | 2024-10-09 | 35 | 4399.7255 | 5319.3267 | 74430.1853 | 90051.8385
[17 empty] | 121 | 2024-10-10 | 36 | 4399.7255 | 5319.3267 | 78829.9108 | 95371.1652
[17 empty] | 121 | 2024-10-11 | 37 | 4399.7255 | 5319.3267 | 83229.6364 | 100690.4919
[17 empty] | 121 | 2024-10-12 | 38 | 0 | 0 | 83229.6364 | 100690.4919
[17 empty] | 121 | 2024-10-13 | 39 | 0 | 0 | 83229.6364 | 100690.4919
[17 empty] | 121 | 2024-10-14 | 40 | 4399.7255 | 5319.3267 | 87629.3619 | 106009.8186
[17 empty] | 121 | 2024-10-15 | 41 | 4399.7255 | 5319.3267 | 92029.0874 | 111329.1453
[17 empty] | 121 | 2024-10-16 | 42 | 4399.7255 | 5319.3267 | 96428.8129 | 116648.472
[17 empty] | 121 | 2024-10-17 | 43 | 4399.7255 | 5319.3267 | 100828.5385 | 121967.7987
[17 empty] | 121 | 2024-10-18 | 44 | 4399.7255 | 5319.3267 | 105228.264 | 127287.1253
[17 empty] | 121 | 2024-10-19 | 45 | 0 | 0 | 105228.264 | 127287.1253
[17 empty] | 121 | 2024-10-20 | 46 | 0 | 0 | 105228.264 | 127287.1253
[17 empty] | 121 | 2024-10-21 | 47 | 4399.7255 | 5319.3267 | 109627.9895 | 132606.452
[17 empty] | 121 | 2024-10-22 | 48 | 4399.7255 | 5319.3267 | 114027.7151 | 137925.7787
[17 empty] | 121 | 2024-10-23 | 49 | 4399.7255 | 5319.3267 | 118427.4406 | 143245.1054
[17 empty] | 121 | 2024-10-24 | 50 | 4399.7255 | 5319.3267 | 122827.1661 | 148564.4321
[17 empty] | 121 | 2024-10-25 | 51 | 4399.7255 | 5319.3267 | 127226.8916 | 153883.7588
[17 empty] | 121 | 2024-10-26 | 52 | 0 | 0 | 127226.8916 | 153883.7588
[17 empty] | 121 | 2024-10-27 | 53 | 0 | 0 | 127226.8916 | 153883.7588
[17 empty] | 121 | 2024-10-28 | 54 | 4399.7255 | 5319.3267 | 131626.6172 | 159203.0855
[17 empty] | 121 | 2024-10-29 | 55 | 4399.7255 | 5319.3267 | 136026.3427 | 164522.4121
[17 empty] | 121 | 2024-10-30 | 56 | 4399.7255 | 5319.3267 | 140426.0682 | 169841.7388
[17 empty] | 121 | 2024-10-31 | 57 | 4399.7255 | 5319.3267 | 144825.7938 | 175161.0655
[17 empty] | 121 | 2024-11-01 | 58 | 4399.7255 | 5319.3267 | 149225.5193 | 180480.3922
[17 empty] | 121 | 2024-11-02 | 59 | 0 | 0 | 149225.5193 | 180480.3922
[17 empty] | 121 | 2024-11-03 | 60 | 0 | 0 | 149225.5193 | 180480.3922
[17 empty] | 121 | 2024-11-04 | 61 | 4399.7255 | 5319.3267 | 153625.2448 | 185799.7189
[17 empty] | 121 | 2024-11-05 | 62 | 4399.7255 | 5319.3267 | 158024.9704 | 191119.0456
[17 empty] | 121 | 2024-11-06 | 63 | 4399.7255 | 5319.3267 | 162424.6959 | 196438.3723
[17 empty] | 121 | 2024-11-07 | 64 | 4399.7255 | 5319.3267 | 166824.4214 | 201757.6989
[17 empty] | 121 | 2024-11-08 | 65 | 4399.7255 | 5319.3267 | 171224.1469 | 207077.0256
[17 empty] | 121 | 2024-11-09 | 66 | 0 | 0 | 171224.1469 | 207077.0256
[17 empty] | 121 | 2024-11-10 | 67 | 0 | 0 | 171224.1469 | 207077.0256
[17 empty] | 121 | 2024-11-11 | 68 | 4399.7255 | 5319.3267 | 175623.8725 | 212396.3523
[17 empty] | 121 | 2024-11-12 | 69 | 4399.7255 | 5319.3267 | 180023.598 | 217715.679
[17 empty] | 121 | 2024-11-13 | 70 | 4399.7255 | 5319.3267 | 184423.3235 | 223035.0057
[17 empty] | 121 | 2024-11-14 | 71 | 4399.7255 | 5319.3267 | 188823.0491 | 228354.3324
[17 empty] | 121 | 2024-11-15 | 72 | 6526.4647 | 7743.8093 | 195349.5137 | 236098.1417
[17 empty] | 121 | 2024-11-16 | 73 | 0 | 0 | 195349.5137 | 236098.1417
[17 empty] | 121 | 2024-11-17 | 74 | 0 | 0 | 195349.5137 | 236098.1417
[17 empty] | 121 | 2024-11-18 | 75 | 4972.3183 | 5785.5849 | 200321.832 | 241883.7266
[17 empty] | 121 | 2024-11-19 | 76 | 4972.3183 | 5785.5849 | 205294.1504 | 247669.3115
[17 empty] | 121 | 2024-11-20 | 77 | 4972.3183 | 5785.5849 | 210266.4687 | 253454.8964
[17 empty] | 121 | 2024-11-21 | 78 | 4972.3183 | 5785.5849 | 215238.787 | 259240.4813
[17 empty] | 121 | 2024-11-22 | 79 | 4972.3183 | 5785.5849 | 220211.1053 | 265026.0662
[17 empty] | 121 | 2024-11-23 | 80 | 0 | 0 | 220211.1053 | 265026.0662
[17 empty] | 121 | 2024-11-24 | 81 | 0 | 0 | 220211.1053 | 265026.0662
[17 empty] | 121 | 2024-11-25 | 82 | 4972.3183 | 5785.5849 | 225183.4236 | 270811.6511
[17 empty] | 121 | 2024-11-26 | 83 | 4972.3183 | 5785.5849 | 230155.742 | 276597.236
[17 empty] | 121 | 2024-11-27 | 84 | 4972.3183 | 5785.5849 | 235128.0603 | 282382.8209
[17 empty] | 121 | 2024-11-28 | 85 | 4972.3183 | 5785.5849 | 240100.3786 | 288168.4058
[17 empty] | 121 | 2024-11-29 | 86 | 4972.3183 | 5785.5849 | 245072.6969 | 293953.9907
[17 empty] | 121 | 2024-11-30 | 87 | 0 | 0 | 245072.6969 | 293953.9907
[17 empty] | 121 | 2024-12-01 | 88 | 0 | 0 | 245072.6969 | 293953.9907
[17 empty] | 121 | 2024-12-02 | 89 | 4972.3183 | 5785.5849 | 250045.0152 | 299739.5756
[17 empty] | 121 | 2024-12-03 | 90 | 4972.3183 | 5785.5849 | 255017.3335 | 305525.1605
[17 empty] | 121 | 2024-12-04 | 91 | 4972.3183 | 5785.5849 | 259989.6519 | 311310.7454
[17 empty] | 121 | 2024-12-05 | 92 | 4972.3183 | 5785.5849 | 264961.9702 | 317096.3303
[17 empty] | 121 | 2024-12-06 | 93 | 4972.3183 | 5785.5849 | 269934.2885 | 322881.9152
[17 empty] | 121 | 2024-12-07 | 94 | 0 | 0 | 269934.2885 | 322881.9152
[17 empty] | 121 | 2024-12-08 | 95 | 0 | 0 | 269934.2885 | 322881.9152
[17 empty] | 121 | 2024-12-09 | 96 | 8121.3183 | 9280.9749 | 278055.6068 | 332162.8901
[17 empty] | 121 | 2024-12-10 | 97 | 8121.3183 | 9280.9749 | 286176.9251 | 341443.865
[17 empty] | 121 | 2024-12-11 | 98 | 8121.3183 | 9280.9749 | 294298.2435 | 350724.84
[17 empty] | 121 | 2024-12-12 | 99 | 8121.3183 | 9280.9749 | 302419.5618 | 360005.8149
[17 empty] | 121 | 2024-12-13 | 100 | 8121.3183 | 9280.9749 | 310540.8801 | 369286.7898
[17 empty] | 121 | 2024-12-14 | 101 | 0 | 0 | 310540.8801 | 369286.7898
[17 empty] | 121 | 2024-12-15 | 102 | 0 | 0 | 310540.8801 | 369286.7898
[17 empty] | 121 | 2024-12-16 | 103 | 8121.3183 | 9280.9749 | 318662.1984 | 378567.7647
[17 empty] | 121 | 2024-12-17 | 104 | 9859.0398 | 11470.504 | 328521.2382 | 390038.2687
[17 empty] | 121 | 2024-12-18 | 105 | 9859.0398 | 11470.504 | 338380.2781 | 401508.7727
[17 empty] | 121 | 2024-12-19 | 106 | 9859.0398 | 11470.504 | 348239.3179 | 412979.2767
[17 empty] | 121 | 2024-12-20 | 107 | 9859.0398 | 11470.504 | 358098.3578 | 424449.7807
[17 empty] | 121 | 2024-12-21 | 108 | 0 | 0 | 358098.3578 | 424449.7807
[17 empty] | 121 | 2024-12-22 | 109 | 0 | 0 | 358098.3578 | 424449.7807
[17 empty] | 121 | 2024-12-23 | 110 | 9859.0398 | 11470.504 | 367957.3976 | 435920.2848
[17 empty] | 121 | 2024-12-24 | 111 | 9859.0398 | 11470.504 | 377816.4374 | 447390.7888
[17 empty] | 121 | 2024-12-25 | 112 | 9859.0398 | 11470.504 | 387675.4773 | 458861.2928
[17 empty] | 121 | 2024-12-26 | 113 | 9859.0398 | 11470.504 | 397534.5171 | 470331.7968
[17 empty] | 121 | 2024-12-27 | 114 | 9859.0398 | 11470.504 | 407393.5569 | 481802.3008
[17 empty] | 121 | 2024-12-28 | 115 | 0 | 0 | 407393.5569 | 481802.3008
[17 empty] | 121 | 2024-12-29 | 116 | 0 | 0 | 407393.5569 | 481802.3008
[17 empty] | 121 | 2024-12-30 | 117 | 9715.0688 | 11525.8579 | 417108.6258 | 493328.1588
[17 empty] | 121 | 2024-12-31 | 118 | 9715.0688 | 11525.8579 | 426823.6946 | 504854.0167
[17 empty] | 121 | 2025-01-01 | 119 | 9715.0688 | 11525.8579 | 436538.7634 | 516379.8746
[17 empty] | 121 | 2025-01-02 | 120 | 9715.0688 | 11525.8579 | 446253.8322 | 527905.7326
[17 empty] | 121 | 2025-01-03 | 121 | 9715.0688 | 11525.8579 | 455968.9011 | 539431.5905
[17 empty] | 121 | 2025-01-04 | 122 | 0 | 0 | 455968.9011 | 539431.5905
[17 empty] | 121 | 2025-01-05 | 123 | 0 | 0 | 455968.9011 | 539431.5905
[17 empty] | 121 | 2025-01-06 | 124 | 9715.0688 | 11525.8579 | 465683.9699 | 550957.4484
[17 empty] | 121 | 2025-01-07 | 125 | 12077.9097 | 14526.6659 | 477761.8796 | 565484.1143
[17 empty] | 121 | 2025-01-08 | 126 | 12077.9097 | 14526.6659 | 489839.7894 | 580010.7802
[17 empty] | 121 | 2025-01-09 | 127 | 12077.9097 | 14526.6659 | 501917.6991 | 594537.4461
[17 empty] | 121 | 2025-01-10 | 128 | 12077.9097 | 14526.6659 | 513995.6088 | 609064.112
[17 empty] | 121 | 2025-01-11 | 129 | 0 | 0 | 513995.6088 | 609064.112
[17 empty] | 121 | 2025-01-12 | 130 | 0 | 0 | 513995.6088 | 609064.112
[17 empty] | 121 | 2025-01-13 | 131 | 12077.9097 | 14526.6659 | 526073.5185 | 623590.7779
[17 empty] | 121 | 2025-01-14 | 132 | 12077.9097 | 14526.6659 | 538151.4283 | 638117.4437
[17 empty] | 121 | 2025-01-15 | 133 | 12077.9097 | 14526.6659 | 550229.338 | 652644.1096
[17 empty] | 121 | 2025-01-16 | 134 | 12077.9097 | 14526.6659 | 562307.2477 | 667170.7755
[17 empty] | 121 | 2025-01-17 | 135 | 12077.9097 | 14526.6659 | 574385.1575 | 681697.4414
[17 empty] | 121 | 2025-01-18 | 136 | 0 | 0 | 574385.1575 | 681697.4414
[17 empty] | 121 | 2025-01-19 | 137 | 0 | 0 | 574385.1575 | 681697.4414
[17 empty] | 121 | 2025-01-20 | 138 | 9951.1706 | 12102.1833 | 584336.3281 | 693799.6247
[17 empty] | 121 | 2025-01-21 | 139 | 9951.1706 | 12102.1833 | 594287.4987 | 705901.808
[17 empty] | 121 | 2025-01-22 | 140 | 9951.1706 | 12102.1833 | 604238.6693 | 718003.9912
[17 empty] | 121 | 2025-01-23 | 141 | 9951.1706 | 12102.1833 | 614189.8399 | 730106.1745
[17 empty] | 121 | 2025-01-24 | 142 | 9951.1706 | 12102.1833 | 624141.0105 | 742208.3578
[17 empty] | 121 | 2025-01-25 | 143 | 0 | 0 | 624141.0105 | 742208.3578
[17 empty] | 121 | 2025-01-26 | 144 | 0 | 0 | 624141.0105 | 742208.3578
[17 empty] | 121 | 2025-01-27 | 145 | 9951.1706 | 12102.1833 | 634092.1811 | 754310.5411
[17 empty] | 121 | 2025-01-28 | 146 | 9951.1706 | 12102.1833 | 644043.3517 | 766412.7243
[17 empty] | 121 | 2025-01-29 | 147 | 9951.1706 | 12102.1833 | 653994.5223 | 778514.9076
[17 empty] | 121 | 2025-01-30 | 148 | 6802.1706 | 8606.7933 | 660796.6929 | 787121.7009
[17 empty] | 121 | 2025-01-31 | 149 | 6802.1706 | 8606.7933 | 667598.8635 | 795728.4942
[17 empty] | 121 | 2025-02-01 | 150 | 0 | 0 | 667598.8635 | 795728.4942
[17 empty] | 121 | 2025-02-02 | 151 | 0 | 0 | 667598.8635 | 795728.4942
[17 empty] | 121 | 2025-02-03 | 152 | 4564.1706 | 5764.5333 | 672163.0341 | 801493.0275
[17 empty] | 121 | 2025-02-04 | 153 | 4564.1706 | 5764.5333 | 676727.2047 | 807257.5607
[17 empty] | 121 | 2025-02-05 | 154 | 4564.1706 | 5764.5333 | 681291.3753 | 813022.094
[17 empty] | 121 | 2025-02-06 | 155 | 4564.1706 | 5764.5333 | 685855.5459 | 818786.6273
[17 empty] | 121 | 2025-02-07 | 156 | 4564.1706 | 5764.5333 | 690419.7165 | 824551.1606
[17 empty] | 121 | 2025-02-08 | 157 | 0 | 0 | 690419.7165 | 824551.1606
[17 empty] | 121 | 2025-02-09 | 158 | 0 | 0 | 690419.7165 | 824551.1606
[17 empty] | 121 | 2025-02-10 | 159 | 4564.1706 | 5764.5333 | 694983.8871 | 830315.6938
[17 empty] | 121 | 2025-02-11 | 160 | 4564.1706 | 5764.5333 | 699548.0577 | 836080.2271
[17 empty] | 121 | 2025-02-12 | 161 | 4564.1706 | 5764.5333 | 704112.2283 | 841844.7604
[17 empty] | 121 | 2025-02-13 | 162 | 4564.1706 | 5764.5333 | 708676.3989 | 847609.2937
[17 empty] | 121 | 2025-02-14 | 163 | 4564.1706 | 5764.5333 | 713240.5695 | 853373.827
[17 empty] | 121 | 2025-02-15 | 164 | 0 | 0 | 713240.5695 | 853373.827
[17 empty] | 121 | 2025-02-16 | 165 | 0 | 0 | 713240.5695 | 853373.827
[17 empty] | 121 | 2025-02-17 | 166 | 4564.1706 | 5764.5333 | 717804.7401 | 859138.3602
[17 empty] | 121 | 2025-02-18 | 167 | 4564.1706 | 5764.5333 | 722368.9107 | 864902.8935
[17 empty] | 121 | 2025-02-19 | 168 | 4564.1706 | 5764.5333 | 726933.0813 | 870667.4268
[17 empty] | 121 | 2025-02-20 | 169 | 4564.1706 | 5764.5333 | 731497.2519 | 876431.9601
[17 empty] | 121 | 2025-02-21 | 170 | 4564.1706 | 5764.5333 | 736061.4225 | 882196.4933
[17 empty] | 121 | 2025-02-22 | 171 | 0 | 0 | 736061.4225 | 882196.4933
[17 empty] | 121 | 2025-02-23 | 172 | 0 | 0 | 736061.4225 | 882196.4933
[17 empty] | 121 | 2025-02-24 | 173 | 4564.1706 | 5764.5333 | 740625.5931 | 887961.0266
[17 empty] | 121 | 2025-02-25 | 174 | 4564.1706 | 5764.5333 | 745189.7637 | 893725.5599
[17 empty] | 121 | 2025-02-26 | 175 | 4564.1706 | 5764.5333 | 749753.9343 | 899490.0932
[17 empty] | 121 | 2025-02-27 | 176 | 4564.1706 | 5764.5333 | 754318.1049 | 905254.6264
[17 empty] | 121 | 2025-02-28 | 177 | 4564.1706 | 5764.5333 | 758882.2755 | 911019.1597
[17 empty] | 121 | 2025-03-01 | 178 | 0 | 0 | 758882.2755 | 911019.1597
[17 empty] | 121 | 2025-03-02 | 179 | 0 | 0 | 758882.2755 | 911019.1597
[17 empty] | 121 | 2025-03-03 | 180 | 4564.1706 | 5764.5333 | 763446.4461 | 916783.693
[17 empty] | 121 | 2025-03-04 | 181 | 4564.1706 | 5764.5333 | 768010.6167 | 922548.2263
[17 empty] | 121 | 2025-03-05 | 182 | 4564.1706 | 5764.5333 | 772574.7873 | 928312.7596
[17 empty] | 121 | 2025-03-06 | 183 | 4564.1706 | 5764.5333 | 777138.9579 | 934077.2928
[17 empty] | 121 | 2025-03-07 | 184 | 4564.1706 | 5764.5333 | 781703.1285 | 939841.8261
[17 empty] | 121 | 2025-03-08 | 185 | 0 | 0 | 781703.1285 | 939841.8261
[17 empty] | 121 | 2025-03-09 | 186 | 0 | 0 | 781703.1285 | 939841.8261
[17 empty] | 121 | 2025-03-10 | 187 | 4564.1706 | 5764.5333 | 786267.2991 | 945606.3594
[17 empty] | 121 | 2025-03-11 | 188 | 4564.1706 | 5764.5333 | 790831.4697 | 951370.8927
[17 empty] | 121 | 2025-03-12 | 189 | 4564.1706 | 5764.5333 | 795395.6403 | 957135.4259
[17 empty] | 121 | 2025-03-13 | 190 | 4564.1706 | 5764.5333 | 799959.8109 | 962899.9592
[17 empty] | 121 | 2025-03-14 | 191 | 4564.1706 | 5764.5333 | 804523.9815 | 968664.4925
[17 empty] | 121 | 2025-03-15 | 192 | 0 | 0 | 804523.9815 | 968664.4925
[17 empty] | 121 | 2025-03-16 | 193 | 0 | 0 | 804523.9815 | 968664.4925
[17 empty] | 121 | 2025-03-17 | 194 | 4564.1706 | 5764.5333 | 809088.1521 | 974429.0258
[17 empty] | 121 | 2025-03-18 | 195 | 4564.1706 | 5764.5333 | 813652.3227 | 980193.5591
[17 empty] | 121 | 2025-03-19 | 196 | 4564.1706 | 5764.5333 | 818216.4933 | 985958.0923
[17 empty] | 121 | 2025-03-20 | 197 | 4564.1706 | 5764.5333 | 822780.664 | 991722.6256
[17 empty] | 121 | 2025-03-21 | 198 | 4564.1706 | 5764.5333 | 827344.8346 | 997487.1589
[17 empty] | 121 | 2025-03-22 | 199 | 0 | 0 | 827344.8346 | 997487.1589
[17 empty] | 121 | 2025-03-23 | 200 | 0 | 0 | 827344.8346 | 997487.1589
[17 empty] | 121 | 2025-03-24 | 201 | 4564.1706 | 5764.5333 | 831909.0052 | 1003251.6922
[17 empty] | 121 | 2025-03-25 | 202 | 4564.1706 | 5764.5333 | 836473.1758 | 1009016.2254
[17 empty] | 121 | 2025-03-26 | 203 | 4564.1706 | 5764.5333 | 841037.3464 | 1014780.7587
[17 empty] | 121 | 2025-03-27 | 204 | 4564.1706 | 5764.5333 | 845601.517 | 1020545.292
[17 empty] | 121 | 2025-03-28 | 205 | 4564.1706 | 5764.5333 | 850165.6876 | 1026309.8253
[17 empty] | 121 | 2025-03-29 | 206 | 0 | 0 | 850165.6876 | 1026309.8253
[17 empty] | 121 | 2025-03-30 | 207 | 0 | 0 | 850165.6876 | 1026309.8253
[17 empty] | 121 | 2025-03-31 | 208 | 4564.1706 | 5764.5333 | 854729.8582 | 1032074.3586
[17 empty] | 121 | 2025-04-01 | 209 | 4564.1706 | 5764.5333 | 859294.0288 | 1037838.8918
[17 empty] | 121 | 2025-04-02 | 210 | 4564.1706 | 5764.5333 | 863858.1994 | 1043603.4251
[17 empty] | 121 | 2025-04-03 | 211 | 4564.1706 | 5764.5333 | 868422.37 | 1049367.9584
[17 empty] | 121 | 2025-04-04 | 212 | 4564.1706 | 5764.5333 | 872986.5406 | 1055132.4917
[17 empty] | 121 | 2025-04-05 | 213 | 0 | 0 | 872986.5406 | 1055132.4917
[17 empty] | 121 | 2025-04-06 | 214 | 0 | 0 | 872986.5406 | 1055132.4917
[17 empty] | 121 | 2025-04-07 | 215 | 2826.4491 | 3575.0042 | 875812.9897 | 1058707.4958
[17 empty] | 121 | 2025-04-08 | 216 | 2826.4491 | 3575.0042 | 878639.4387 | 1062282.5
[17 empty] | 121 | 2025-04-09 | 217 | 2826.4491 | 3575.0042 | 881465.8878 | 1065857.5042
[17 empty] | 121 | 2025-04-10 | 218 | 2826.4491 | 3575.0042 | 884292.3369 | 1069432.5083
[17 empty] | 121 | 2025-04-11 | 219 | 2826.4491 | 3575.0042 | 887118.786 | 1073007.5125
[17 empty] | 121 | 2025-04-12 | 220 | 0 | 0 | 887118.786 | 1073007.5125
[17 empty] | 121 | 2025-04-13 | 221 | 0 | 0 | 887118.786 | 1073007.5125
[17 empty] | 121 | 2025-04-14 | 222 | 2826.4491 | 3575.0042 | 889945.2351 | 1076582.5166
[17 empty] | 121 | 2025-04-15 | 223 | 2605.9438 | 3294.9624 | 892551.1788 | 1079877.4791
[17 empty] | 121 | 2025-04-16 | 224 | 2605.9438 | 3294.9624 | 895157.1226 | 1083172.4415
[17 empty] | 121 | 2025-04-17 | 225 | 2605.9438 | 3294.9624 | 897763.0664 | 1086467.4039
[17 empty] | 121 | 2025-04-18 | 226 | 2605.9438 | 3294.9624 | 900369.0101 | 1089762.3663
[17 empty] | 121 | 2025-04-19 | 227 | 0 | 0 | 900369.0101 | 1089762.3663
[17 empty] | 121 | 2025-04-20 | 228 | 0 | 0 | 900369.0101 | 1089762.3663
[17 empty] | 121 | 2025-04-21 | 229 | 2605.9438 | 3294.9624 | 902974.9539 | 1093057.3287
[17 empty] | 121 | 2025-04-22 | 230 | 2605.9438 | 3294.9624 | 905580.8977 | 1096352.2911
[17 empty] | 121 | 2025-04-23 | 231 | 2605.9438 | 3294.9624 | 908186.8414 | 1099647.2535
[17 empty] | 121 | 2025-04-24 | 232 | 2605.9438 | 3294.9624 | 910792.7852 | 1102942.2159
[17 empty] | 121 | 2025-04-25 | 233 | 2605.9438 | 3294.9624 | 913398.729 | 1106237.1784
[17 empty] | 121 | 2025-04-26 | 234 | 0 | 0 | 913398.729 | 1106237.1784
[17 empty] | 121 | 2025-04-27 | 235 | 0 | 0 | 913398.729 | 1106237.1784
[17 empty] | 121 | 2025-04-28 | 236 | 2605.9438 | 3294.9624 | 916004.6727 | 1109532.1408
[17 empty] | 121 | 2025-04-29 | 237 | 2605.9438 | 3294.9624 | 918610.6165 | 1112827.1032
[17 empty] | 121 | 2025-04-30 | 238 | 2605.9438 | 3294.9624 | 921216.5603 | 1116122.0656
[17 empty] | 121 | 2025-05-01 | 239 | 2605.9438 | 3294.9624 | 923822.504 | 1119417.028
[17 empty] | 121 | 2025-05-02 | 240 | 2605.9438 | 3294.9624 | 926428.4478 | 1122711.9904
[17 empty] | 121 | 2025-05-03 | 241 | 0 | 0 | 926428.4478 | 1122711.9904
[17 empty] | 121 | 2025-05-04 | 242 | 0 | 0 | 926428.4478 | 1122711.9904
[17 empty] | 121 | 2025-05-05 | 243 | 2605.9438 | 3294.9624 | 929034.3916 | 1126006.9528
[17 empty] | 121 | 2025-05-06 | 244 | 2605.9438 | 3294.9624 | 931640.3353 | 1129301.9152
[17 empty] | 121 | 2025-05-07 | 245 | 2605.9438 | 3294.9624 | 934246.2791 | 1132596.8776
[17 empty] | 121 | 2025-05-08 | 246 | 2605.9438 | 3294.9624 | 936852.2229 | 1135891.8401
[17 empty] | 121 | 2025-05-09 | 247 | 243.1029 | 294.1545 | 937095.3257 | 1136185.9945
[17 empty] | 121 | 2025-05-10 | 248 | 0 | 0 | 937095.3257 | 1136185.9945
[17 empty] | 121 | 2025-05-11 | 249 | 0 | 0 | 937095.3257 | 1136185.9945
[17 empty] | 121 | 2025-05-12 | 250 | 243.1029 | 294.1545 | 937338.4286 | 1136480.149
[17 empty] | 121 | 2025-05-13 | 251 | 243.1029 | 294.1545 | 937581.5314 | 1136774.3034
[17 empty] | 121 | 2025-05-14 | 252 | 243.1029 | 294.1545 | 937824.6343 | 1137068.4579
[17 empty] | 121 | 2025-05-15 | 253 | 243.1029 | 294.1545 | 938067.7371 | 1137362.6123
[17 empty] | 121 | 2025-05-16 | 254 | 243.1029 | 294.1545 | 938310.84 | 1137656.7668
[17 empty] | 121 | 2025-05-17 | 255 | 0 | 0 | 938310.84 | 1137656.7668
[17 empty] | 121 | 2025-05-18 | 256 | 0 | 0 | 938310.84 | 1137656.7668
[17 empty] | 122 | 2024-10-24 | 1 | 367.9566 | 430.5092 | 367.9566 | 430.5092
[17 empty] | 122 | 2024-10-25 | 2 | 367.9566 | 430.5092 | 735.9132 | 861.0184
[17 empty] | 122 | 2024-10-26 | 3 | 0 | 0 | 735.9132 | 861.0184
[17 empty] | 122 | 2024-10-27 | 4 | 0 | 0 | 735.9132 | 861.0184
[17 empty] | 122 | 2024-10-28 | 5 | 367.9566 | 430.5092 | 1103.8698 | 1291.5276
[17 empty] | 122 | 2024-10-29 | 6 | 2474.0137 | 3126.2624 | 3577.8835 | 4417.79
[17 empty] | 122 | 2024-10-30 | 7 | 2474.0137 | 3126.2624 | 6051.8972 | 7544.0523
[17 empty] | 122 | 2024-10-31 | 8 | 2474.0137 | 3126.2624 | 8525.911 | 10670.3147
[17 empty] | 122 | 2024-11-01 | 9 | 2474.0137 | 3126.2624 | 10999.9247 | 13796.577
[17 empty] | 122 | 2024-11-02 | 10 | 0 | 0 | 10999.9247 | 13796.577
[17 empty] | 122 | 2024-11-03 | 11 | 0 | 0 | 10999.9247 | 13796.577
[17 empty] | 122 | 2024-11-04 | 12 | 2474.0137 | 3126.2624 | 13473.9384 | 16922.8394
[17 empty] | 122 | 2024-11-05 | 13 | 2474.0137 | 3126.2624 | 15947.9522 | 20049.1017
[17 empty] | 122 | 2024-11-06 | 14 | 2474.0137 | 3126.2624 | 18421.9659 | 23175.3641
[17 empty] | 122 | 2024-11-07 | 15 | 2474.0137 | 3126.2624 | 20895.9796 | 26301.6265
[17 empty] | 122 | 2024-11-08 | 16 | 2474.0137 | 3126.2624 | 23369.9934 | 29427.8888
[17 empty] | 122 | 2024-11-09 | 17 | 0 | 0 | 23369.9934 | 29427.8888
[17 empty] | 122 | 2024-11-10 | 18 | 0 | 0 | 23369.9934 | 29427.8888
[17 empty] | 122 | 2024-11-11 | 19 | 2474.0137 | 3126.2624 | 25844.0071 | 32554.1512
[17 empty] | 122 | 2024-11-12 | 20 | 2474.0137 | 3126.2624 | 28318.0208 | 35680.4135
[17 empty] | 122 | 2024-11-13 | 21 | 2474.0137 | 3126.2624 | 30792.0346 | 38806.6759
[17 empty] | 122 | 2024-11-14 | 22 | 2474.0137 | 3126.2624 | 33266.0483 | 41932.9382
[17 empty] | 122 | 2024-11-15 | 23 | 2474.0137 | 3126.2624 | 35740.062 | 45059.2006
[17 empty] | 122 | 2024-11-16 | 24 | 0 | 0 | 35740.062 | 45059.2006
[17 empty] | 122 | 2024-11-17 | 25 | 0 | 0 | 35740.062 | 45059.2006
[17 empty] | 122 | 2024-11-18 | 26 | 2474.0137 | 3126.2624 | 38214.0758 | 48185.4629
[17 empty] | 122 | 2024-11-19 | 27 | 2474.0137 | 3126.2624 | 40688.0895 | 51311.7253
[17 empty] | 122 | 2024-11-20 | 28 | 2474.0137 | 3126.2624 | 43162.1032 | 54437.9876
[17 empty] | 122 | 2024-11-21 | 29 | 2474.0137 | 3126.2624 | 45636.117 | 57564.25
[17 empty] | 122 | 2024-11-22 | 30 | 2474.0137 | 3126.2624 | 48110.1307 | 60690.5123
[17 empty] | 122 | 2024-11-23 | 31 | 0 | 0 | 48110.1307 | 60690.5123
[17 empty] | 122 | 2024-11-24 | 32 | 0 | 0 | 48110.1307 | 60690.5123
[17 empty] | 122 | 2024-11-25 | 33 | 2474.0137 | 3126.2624 | 50584.1444 | 63816.7747
[17 empty] | 122 | 2024-11-26 | 34 | 2474.0137 | 3126.2624 | 53058.1582 | 66943.037
[17 empty] | 122 | 2024-11-27 | 35 | 2474.0137 | 3126.2624 | 55532.1719 | 70069.2994
[17 empty] | 122 | 2024-11-28 | 36 | 2474.0137 | 3126.2624 | 58006.1856 | 73195.5617
[17 empty] | 122 | 2024-11-29 | 37 | 2474.0137 | 3126.2624 | 60480.1994 | 76321.8241
[17 empty] | 122 | 2024-11-30 | 38 | 0 | 0 | 60480.1994 | 76321.8241
[17 empty] | 122 | 2024-12-01 | 39 | 0 | 0 | 60480.1994 | 76321.8241
[17 empty] | 122 | 2024-12-02 | 40 | 2474.0137 | 3126.2624 | 62954.2131 | 79448.0865
[17 empty] | 122 | 2024-12-03 | 41 | 2474.0137 | 3126.2624 | 65428.2268 | 82574.3488
[17 empty] | 122 | 2024-12-04 | 42 | 2474.0137 | 3126.2624 | 67902.2406 | 85700.6112
[17 empty] | 122 | 2024-12-05 | 43 | 2474.0137 | 3126.2624 | 70376.2543 | 88826.8735
[17 empty] | 122 | 2024-12-06 | 44 | 2474.0137 | 3126.2624 | 72850.268 | 91953.1359
[17 empty] | 122 | 2024-12-07 | 45 | 0 | 0 | 72850.268 | 91953.1359
[17 empty] | 122 | 2024-12-08 | 46 | 0 | 0 | 72850.268 | 91953.1359
[17 empty] | 122 | 2024-12-09 | 47 | 2474.0137 | 3126.2624 | 75324.2818 | 95079.3982
[17 empty] | 122 | 2024-12-10 | 48 | 2474.0137 | 3126.2624 | 77798.2955 | 98205.6606
[17 empty] | 122 | 2024-12-11 | 49 | 2474.0137 | 3126.2624 | 80272.3092 | 101331.9229
[17 empty] | 122 | 2024-12-12 | 50 | 2474.0137 | 3126.2624 | 82746.3229 | 104458.1853
[17 empty] | 122 | 2024-12-13 | 51 | 2474.0137 | 3126.2624 | 85220.3367 | 107584.4476
[17 empty] | 122 | 2024-12-14 | 52 | 0 | 0 | 85220.3367 | 107584.4476
[17 empty] | 122 | 2024-12-15 | 53 | 0 | 0 | 85220.3367 | 107584.4476
[17 empty] | 122 | 2024-12-16 | 54 | 4147.4443 | 5218.0505 | 89367.781 | 112802.4982
[17 empty] | 122 | 2024-12-17 | 55 | 2041.3871 | 2522.2974 | 91409.1681 | 115324.7956
[17 empty] | 122 | 2024-12-18 | 56 | 2041.3871 | 2522.2974 | 93450.5553 | 117847.093
[17 empty] | 122 | 2024-12-19 | 57 | 2041.3871 | 2522.2974 | 95491.9424 | 120369.3904
[17 empty] | 122 | 2024-12-20 | 58 | 2041.3871 | 2522.2974 | 97533.3296 | 122891.6878
[17 empty] | 122 | 2024-12-21 | 59 | 0 | 0 | 97533.3296 | 122891.6878
[17 empty] | 122 | 2024-12-22 | 60 | 0 | 0 | 97533.3296 | 122891.6878
[17 empty] | 122 | 2024-12-23 | 61 | 2041.3871 | 2522.2974 | 99574.7167 | 125413.9852
[17 empty] | 122 | 2024-12-24 | 62 | 2041.3871 | 2522.2974 | 101616.1038 | 127936.2826
[17 empty] | 122 | 2024-12-25 | 63 | 2041.3871 | 2522.2974 | 103657.491 | 130458.58
[17 empty] | 122 | 2024-12-26 | 64 | 2041.3871 | 2522.2974 | 105698.8781 | 132980.8774
[17 empty] | 122 | 2024-12-27 | 65 | 2041.3871 | 2522.2974 | 107740.2653 | 135503.1748
[17 empty] | 122 | 2024-12-28 | 66 | 0 | 0 | 107740.2653 | 135503.1748
[17 empty] | 122 | 2024-12-29 | 67 | 0 | 0 | 107740.2653 | 135503.1748
[17 empty] | 122 | 2024-12-30 | 68 | 2041.3871 | 2522.2974 | 109781.6524 | 138025.4722
[17 empty] | 122 | 2024-12-31 | 69 | 2041.3871 | 2522.2974 | 111823.0396 | 140547.7696
[17 empty] | 122 | 2025-01-01 | 70 | 2041.3871 | 2522.2974 | 113864.4267 | 143070.067
[17 empty] | 122 | 2025-01-02 | 71 | 2041.3871 | 2522.2974 | 115905.8139 | 145592.3644
[17 empty] | 122 | 2025-01-03 | 72 | 2041.3871 | 2522.2974 | 117947.201 | 148114.6618
[17 empty] | 122 | 2025-01-04 | 73 | 0 | 0 | 117947.201 | 148114.6618
[17 empty] | 122 | 2025-01-05 | 74 | 0 | 0 | 117947.201 | 148114.6618
[17 empty] | 122 | 2025-01-06 | 75 | 2041.3871 | 2522.2974 | 119988.5882 | 150636.9592
[17 empty] | 122 | 2025-01-07 | 76 | 2041.3871 | 2522.2974 | 122029.9753 | 153159.2567
[17 empty] | 122 | 2025-01-08 | 77 | 2041.3871 | 2522.2974 | 124071.3624 | 155681.5541
[17 empty] | 122 | 2025-01-09 | 78 | 2041.3871 | 2522.2974 | 126112.7496 | 158203.8515
[17 empty] | 122 | 2025-01-10 | 79 | 2041.3871 | 2522.2974 | 128154.1367 | 160726.1489
[17 empty] | 122 | 2025-01-11 | 80 | 0 | 0 | 128154.1367 | 160726.1489
[17 empty] | 122 | 2025-01-12 | 81 | 0 | 0 | 128154.1367 | 160726.1489
[17 empty] | 122 | 2025-01-13 | 82 | 2041.3871 | 2522.2974 | 130195.5239 | 163248.4463
[17 empty] | 122 | 2025-01-14 | 83 | 2041.3871 | 2522.2974 | 132236.911 | 165770.7437
[17 empty] | 122 | 2025-01-15 | 84 | 2041.3871 | 2522.2974 | 134278.2982 | 168293.0411
[17 empty] | 122 | 2025-01-16 | 85 | 2041.3871 | 2522.2974 | 136319.6853 | 170815.3385
[17 empty] | 122 | 2025-01-17 | 86 | 2041.3871 | 2522.2974 | 138361.0725 | 173337.6359
[17 empty] | 122 | 2025-01-18 | 87 | 0 | 0 | 138361.0725 | 173337.6359
[17 empty] | 122 | 2025-01-19 | 88 | 0 | 0 | 138361.0725 | 173337.6359
[17 empty] | 122 | 2025-01-20 | 89 | 2041.3871 | 2522.2974 | 140402.4596 | 175859.9333
[17 empty] | 122 | 2025-01-21 | 90 | 2041.3871 | 2522.2974 | 142443.8468 | 178382.2307
[17 empty] | 122 | 2025-01-22 | 91 | 2041.3871 | 2522.2974 | 144485.2339 | 180904.5281
[17 empty] | 122 | 2025-01-23 | 92 | 2041.3871 | 2522.2974 | 146526.621 | 183426.8255
[17 empty] | 122 | 2025-01-24 | 93 | 2041.3871 | 2522.2974 | 148568.0082 | 185949.1229
[17 empty] | 122 | 2025-01-25 | 94 | 0 | 0 | 148568.0082 | 185949.1229
[17 empty] | 122 | 2025-01-26 | 95 | 0 | 0 | 148568.0082 | 185949.1229
[17 empty] | 122 | 2025-01-27 | 96 | 2041.3871 | 2522.2974 | 150609.3953 | 188471.4203
[17 empty] | 122 | 2025-01-28 | 97 | 2041.3871 | 2522.2974 | 152650.7825 | 190993.7177
[17 empty] | 122 | 2025-01-29 | 98 | 2041.3871 | 2522.2974 | 154692.1696 | 193516.0151
[17 empty] | 122 | 2025-01-30 | 99 | 2041.3871 | 2522.2974 | 156733.5568 | 196038.3125
[17 empty] | 122 | 2025-01-31 | 100 | 2041.3871 | 2522.2974 | 158774.9439 | 198560.6099
[17 empty] | 122 | 2025-02-01 | 101 | 0 | 0 | 158774.9439 | 198560.6099
[17 empty] | 122 | 2025-02-02 | 102 | 0 | 0 | 158774.9439 | 198560.6099
[17 empty] | 122 | 2025-02-03 | 103 | 2041.3871 | 2522.2974 | 160816.3311 | 201082.9073
[17 empty] | 122 | 2025-02-04 | 104 | 2041.3871 | 2522.2974 | 162857.7182 | 203605.2047
[17 empty] | 122 | 2025-02-05 | 105 | 2041.3871 | 2522.2974 | 164899.1054 | 206127.5021
[17 empty] | 122 | 2025-02-06 | 106 | 2041.3871 | 2522.2974 | 166940.4925 | 208649.7996
[17 empty] | 122 | 2025-02-07 | 107 | 2041.3871 | 2522.2974 | 168981.8796 | 211172.097
[17 empty] | 122 | 2025-02-08 | 108 | 0 | 0 | 168981.8796 | 211172.097
[17 empty] | 122 | 2025-02-09 | 109 | 0 | 0 | 168981.8796 | 211172.097
[17 empty] | 122 | 2025-02-10 | 110 | 2041.3871 | 2522.2974 | 171023.2668 | 213694.3944
[17 empty] | 122 | 2025-02-11 | 111 | 2041.3871 | 2522.2974 | 173064.6539 | 216216.6918
[17 empty] | 122 | 2025-02-12 | 112 | 2041.3871 | 2522.2974 | 175106.0411 | 218738.9892
[17 empty] | 122 | 2025-02-13 | 113 | 2041.3871 | 2522.2974 | 177147.4282 | 221261.2866
[17 empty] | 122 | 2025-02-14 | 114 | 2041.3871 | 2522.2974 | 179188.8154 | 223783.584
[17 empty] | 122 | 2025-02-15 | 115 | 0 | 0 | 179188.8154 | 223783.584
[17 empty] | 122 | 2025-02-16 | 116 | 0 | 0 | 179188.8154 | 223783.584
[17 empty] | 122 | 2025-02-17 | 117 | 2041.3871 | 2522.2974 | 181230.2025 | 226305.8814
[17 empty] | 122 | 2025-02-18 | 118 | 2041.3871 | 2522.2974 | 183271.5897 | 228828.1788
[17 empty] | 122 | 2025-02-19 | 119 | 2041.3871 | 2522.2974 | 185312.9768 | 231350.4762
[17 empty] | 122 | 2025-02-20 | 120 | 2041.3871 | 2522.2974 | 187354.364 | 233872.7736
[17 empty] | 122 | 2025-02-21 | 121 | 2041.3871 | 2522.2974 | 189395.7511 | 236395.071
[17 empty] | 122 | 2025-02-22 | 122 | 0 | 0 | 189395.7511 | 236395.071
[17 empty] | 122 | 2025-02-23 | 123 | 0 | 0 | 189395.7511 | 236395.071
[17 empty] | 122 | 2025-02-24 | 124 | 2041.3871 | 2522.2974 | 191437.1382 | 238917.3684
[17 empty] | 122 | 2025-02-25 | 125 | 2041.3871 | 2522.2974 | 193478.5254 | 241439.6658
[17 empty] | 122 | 2025-02-26 | 126 | 2041.3871 | 2522.2974 | 195519.9125 | 243961.9632
[17 empty] | 122 | 2025-02-27 | 127 | 2041.3871 | 2522.2974 | 197561.2997 | 246484.2606
[17 empty] | 122 | 2025-02-28 | 128 | 2041.3871 | 2522.2974 | 199602.6868 | 249006.558
[17 empty] | 122 | 2025-03-01 | 129 | 0 | 0 | 199602.6868 | 249006.558
[17 empty] | 122 | 2025-03-02 | 130 | 0 | 0 | 199602.6868 | 249006.558
[17 empty] | 122 | 2025-03-03 | 131 | 2041.3871 | 2522.2974 | 201644.074 | 251528.8554
[17 empty] | 122 | 2025-03-04 | 132 | 2041.3871 | 2522.2974 | 203685.4611 | 254051.1528
[17 empty] | 122 | 2025-03-05 | 133 | 5474.1371 | 6813.2349 | 209159.5983 | 260864.3877
[17 empty] | 122 | 2025-03-06 | 134 | 5474.1371 | 6813.2349 | 214633.7354 | 267677.6226
[17 empty] | 122 | 2025-03-07 | 135 | 5474.1371 | 6813.2349 | 220107.8725 | 274490.8576
[17 empty] | 122 | 2025-03-08 | 136 | 0 | 0 | 220107.8725 | 274490.8576
[17 empty] | 122 | 2025-03-09 | 137 | 0 | 0 | 220107.8725 | 274490.8576
[17 empty] | 122 | 2025-03-10 | 138 | 5474.1371 | 6813.2349 | 225582.0097 | 281304.0925
[17 empty] | 122 | 2025-03-11 | 139 | 5474.1371 | 6813.2349 | 231056.1468 | 288117.3274
[17 empty] | 122 | 2025-03-12 | 140 | 5474.1371 | 6813.2349 | 236530.284 | 294930.5623
[17 empty] | 122 | 2025-03-13 | 141 | 5474.1371 | 6813.2349 | 242004.4211 | 301743.7972
[17 empty] | 122 | 2025-03-14 | 142 | 5474.1371 | 6813.2349 | 247478.5583 | 308557.0321
[17 empty] | 122 | 2025-03-15 | 143 | 0 | 0 | 247478.5583 | 308557.0321
[17 empty] | 122 | 2025-03-16 | 144 | 0 | 0 | 247478.5583 | 308557.0321
[17 empty] | 122 | 2025-03-17 | 145 | 9673.1371 | 11978.0049 | 257151.6954 | 320535.037
[17 empty] | 122 | 2025-03-18 | 146 | 9673.1371 | 11978.0049 | 266824.8326 | 332513.0419
[17 empty] | 122 | 2025-03-19 | 147 | 9673.1371 | 11978.0049 | 276497.9697 | 344491.0468
[17 empty] | 122 | 2025-03-20 | 148 | 9673.1371 | 11978.0049 | 286171.1069 | 356469.0517
[17 empty] | 122 | 2025-03-21 | 149 | 9673.1371 | 11978.0049 | 295844.244 | 368447.0566
[17 empty] | 122 | 2025-03-22 | 150 | 0 | 0 | 295844.244 | 368447.0566
[17 empty] | 122 | 2025-03-23 | 151 | 0 | 0 | 295844.244 | 368447.0566
[17 empty] | 122 | 2025-03-24 | 152 | 9673.1371 | 11978.0049 | 305517.3811 | 380425.0615
[17 empty] | 122 | 2025-03-25 | 153 | 9673.1371 | 11978.0049 | 315190.5183 | 392403.0664
[17 empty] | 122 | 2025-03-26 | 154 | 7999.7066 | 9886.2167 | 323190.2249 | 402289.2831
[17 empty] | 122 | 2025-03-27 | 155 | 7999.7066 | 9886.2167 | 331189.9315 | 412175.4998
[17 empty] | 122 | 2025-03-28 | 156 | 7999.7066 | 9886.2167 | 339189.6381 | 422061.7165
[17 empty] | 122 | 2025-03-29 | 157 | 0 | 0 | 339189.6381 | 422061.7165
[17 empty] | 122 | 2025-03-30 | 158 | 0 | 0 | 339189.6381 | 422061.7165
[17 empty] | 122 | 2025-03-31 | 159 | 7999.7066 | 9886.2167 | 347189.3447 | 431947.9332
[17 empty] | 122 | 2025-04-01 | 160 | 7999.7066 | 9886.2167 | 355189.0512 | 441834.15
[17 empty] | 122 | 2025-04-02 | 161 | 7999.7066 | 9886.2167 | 363188.7578 | 451720.3667
[17 empty] | 122 | 2025-04-03 | 162 | 7999.7066 | 9886.2167 | 371188.4644 | 461606.5834
[17 empty] | 122 | 2025-04-04 | 163 | 7999.7066 | 9886.2167 | 379188.171 | 471492.8001
[17 empty] | 122 | 2025-04-05 | 164 | 0 | 0 | 379188.171 | 471492.8001
[17 empty] | 122 | 2025-04-06 | 165 | 0 | 0 | 379188.171 | 471492.8001
[17 empty] | 122 | 2025-04-07 | 166 | 7999.7066 | 9886.2167 | 387187.8776 | 481379.0168
[17 empty] | 122 | 2025-04-08 | 167 | 4566.9566 | 5595.2792 | 391754.8342 | 486974.296
[17 empty] | 122 | 2025-04-09 | 168 | 4566.9566 | 5595.2792 | 396321.7908 | 492569.5752
[17 empty] | 122 | 2025-04-10 | 169 | 4566.9566 | 5595.2792 | 400888.7474 | 498164.8544
[17 empty] | 122 | 2025-04-11 | 170 | 4566.9566 | 5595.2792 | 405455.704 | 503760.1336
[17 empty] | 122 | 2025-04-12 | 171 | 0 | 0 | 405455.704 | 503760.1336
[17 empty] | 122 | 2025-04-13 | 172 | 0 | 0 | 405455.704 | 503760.1336
[17 empty] | 122 | 2025-04-14 | 173 | 4566.9566 | 5595.2792 | 410022.6606 | 509355.4128
[17 empty] | 122 | 2025-04-15 | 174 | 4566.9566 | 5595.2792 | 414589.6171 | 514950.6921
[17 empty] | 122 | 2025-04-16 | 175 | 4566.9566 | 5595.2792 | 419156.5737 | 520545.9713
[17 empty] | 122 | 2025-04-17 | 176 | 4566.9566 | 5595.2792 | 423723.5303 | 526141.2505
[17 empty] | 122 | 2025-04-18 | 177 | 4566.9566 | 5595.2792 | 428290.4869 | 531736.5297
[17 empty] | 122 | 2025-04-19 | 178 | 0 | 0 | 428290.4869 | 531736.5297
[17 empty] | 122 | 2025-04-20 | 179 | 0 | 0 | 428290.4869 | 531736.5297
[17 empty] | 122 | 2025-04-21 | 180 | 4566.9566 | 5595.2792 | 432857.4435 | 537331.8089
[17 empty] | 122 | 2025-04-22 | 181 | 4566.9566 | 5595.2792 | 437424.4001 | 542927.0881
[17 empty] | 122 | 2025-04-23 | 182 | 4566.9566 | 5595.2792 | 441991.3567 | 548522.3673
[17 empty] | 122 | 2025-04-24 | 183 | 4566.9566 | 5595.2792 | 446558.3133 | 554117.6465
[17 empty] | 122 | 2025-04-25 | 184 | 4566.9566 | 5595.2792 | 451125.2699 | 559712.9257
[17 empty] | 122 | 2025-04-26 | 185 | 0 | 0 | 451125.2699 | 559712.9257
[17 empty] | 122 | 2025-04-27 | 186 | 0 | 0 | 451125.2699 | 559712.9257
[17 empty] | 122 | 2025-04-28 | 187 | 4566.9566 | 5595.2792 | 455692.2265 | 565308.2049
[17 empty] | 122 | 2025-04-29 | 188 | 4566.9566 | 5595.2792 | 460259.183 | 570903.4842
[17 empty] | 122 | 2025-04-30 | 189 | 4566.9566 | 5595.2792 | 464826.1396 | 576498.7634
[17 empty] | 122 | 2025-05-01 | 190 | 4566.9566 | 5595.2792 | 469393.0962 | 582094.0426
[17 empty] | 122 | 2025-05-02 | 191 | 4566.9566 | 5595.2792 | 473960.0528 | 587689.3218
[17 empty] | 122 | 2025-05-03 | 192 | 0 | 0 | 473960.0528 | 587689.3218
[17 empty] | 122 | 2025-05-04 | 193 | 0 | 0 | 473960.0528 | 587689.3218
[17 empty] | 122 | 2025-05-05 | 194 | 4566.9566 | 5595.2792 | 478527.0094 | 593284.601
[17 empty] | 122 | 2025-05-06 | 195 | 4566.9566 | 5595.2792 | 483093.966 | 598879.8802
[17 empty] | 122 | 2025-05-07 | 196 | 4566.9566 | 5595.2792 | 487660.9226 | 604475.1594
[17 empty] | 122 | 2025-05-08 | 197 | 4566.9566 | 5595.2792 | 492227.8792 | 610070.4386
[17 empty] | 122 | 2025-05-09 | 198 | 4566.9566 | 5595.2792 | 496794.8358 | 615665.7178
[17 empty] | 122 | 2025-05-10 | 199 | 0 | 0 | 496794.8358 | 615665.7178
[17 empty] | 122 | 2025-05-11 | 200 | 0 | 0 | 496794.8358 | 615665.7178
[17 empty] | 122 | 2025-05-12 | 201 | 4566.9566 | 5595.2792 | 501361.7924 | 621260.997
[17 empty] | 122 | 2025-05-13 | 202 | 4566.9566 | 5595.2792 | 505928.7489 | 626856.2763
[17 empty] | 122 | 2025-05-14 | 203 | 4566.9566 | 5595.2792 | 510495.7055 | 632451.5555
[17 empty] | 122 | 2025-05-15 | 204 | 4566.9566 | 5595.2792 | 515062.6621 | 638046.8347
[17 empty] | 122 | 2025-05-16 | 205 | 4566.9566 | 5595.2792 | 519629.6187 | 643642.1139
[17 empty] | 122 | 2025-05-17 | 206 | 0 | 0 | 519629.6187 | 643642.1139
[17 empty] | 122 | 2025-05-18 | 207 | 0 | 0 | 519629.6187 | 643642.1139
[17 empty] | 122 | 2025-05-19 | 208 | 4566.9566 | 5595.2792 | 524196.5753 | 649237.3931
[17 empty] | 122 | 2025-05-20 | 209 | 4566.9566 | 5595.2792 | 528763.5319 | 654832.6723
[17 empty] | 122 | 2025-05-21 | 210 | 4566.9566 | 5595.2792 | 533330.4885 | 660427.9515
[17 empty] | 122 | 2025-05-22 | 211 | 4566.9566 | 5595.2792 | 537897.4451 | 666023.2307
[17 empty] | 122 | 2025-05-23 | 212 | 4566.9566 | 5595.2792 | 542464.4017 | 671618.5099
[17 empty] | 122 | 2025-05-24 | 213 | 0 | 0 | 542464.4017 | 671618.5099
[17 empty] | 122 | 2025-05-25 | 214 | 0 | 0 | 542464.4017 | 671618.5099
[17 empty] | 122 | 2025-05-26 | 215 | 4566.9566 | 5595.2792 | 547031.3582 | 677213.7892
[17 empty] | 122 | 2025-05-27 | 216 | 4566.9566 | 5595.2792 | 551598.3148 | 682809.0684
[17 empty] | 122 | 2025-05-28 | 217 | 4566.9566 | 5595.2792 | 556165.2714 | 688404.3476
[17 empty] | 122 | 2025-05-29 | 218 | 4566.9566 | 5595.2792 | 560732.228 | 693999.6268
[17 empty] | 122 | 2025-05-30 | 219 | 4566.9566 | 5595.2792 | 565299.1846 | 699594.906
[17 empty] | 122 | 2025-05-31 | 220 | 0 | 0 | 565299.1846 | 699594.906
[17 empty] | 122 | 2025-06-01 | 221 | 0 | 0 | 565299.1846 | 699594.906
[17 empty] | 122 | 2025-06-02 | 222 | 4566.9566 | 5595.2792 | 569866.1412 | 705190.1852
[17 empty] | 122 | 2025-06-03 | 223 | 4566.9566 | 5595.2792 | 574433.0978 | 710785.4644
[17 empty] | 122 | 2025-06-04 | 224 | 4566.9566 | 5595.2792 | 579000.0544 | 716380.7436
[17 empty] | 122 | 2025-06-05 | 225 | 4566.9566 | 5595.2792 | 583567.011 | 721976.0228
[17 empty] | 122 | 2025-06-06 | 226 | 4566.9566 | 5595.2792 | 588133.9676 | 727571.302
[17 empty] | 122 | 2025-06-07 | 227 | 0 | 0 | 588133.9676 | 727571.302
[17 empty] | 122 | 2025-06-08 | 228 | 0 | 0 | 588133.9676 | 727571.302
[17 empty] | 122 | 2025-06-09 | 229 | 4566.9566 | 5595.2792 | 592700.9241 | 733166.5813
[17 empty] | 122 | 2025-06-10 | 230 | 4566.9566 | 5595.2792 | 597267.8807 | 738761.8605
[17 empty] | 122 | 2025-06-11 | 231 | 4566.9566 | 5595.2792 | 601834.8373 | 744357.1397
[17 empty] | 122 | 2025-06-12 | 232 | 4566.9566 | 5595.2792 | 606401.7939 | 749952.4189
[17 empty] | 122 | 2025-06-13 | 233 | 4566.9566 | 5595.2792 | 610968.7505 | 755547.6981
[17 empty] | 122 | 2025-06-14 | 234 | 0 | 0 | 610968.7505 | 755547.6981
[17 empty] | 122 | 2025-06-15 | 235 | 0 | 0 | 610968.7505 | 755547.6981
[17 empty] | 122 | 2025-06-16 | 236 | 4566.9566 | 5595.2792 | 615535.7071 | 761142.9773
[17 empty] | 122 | 2025-06-17 | 237 | 4566.9566 | 5595.2792 | 620102.6637 | 766738.2565
[17 empty] | 122 | 2025-06-18 | 238 | 4566.9566 | 5595.2792 | 624669.6203 | 772333.5357
[17 empty] | 122 | 2025-06-19 | 239 | 4566.9566 | 5595.2792 | 629236.5769 | 777928.8149
[17 empty] | 122 | 2025-06-20 | 240 | 4566.9566 | 5595.2792 | 633803.5335 | 783524.0941
[17 empty] | 122 | 2025-06-21 | 241 | 0 | 0 | 633803.5335 | 783524.0941
[17 empty] | 122 | 2025-06-22 | 242 | 0 | 0 | 633803.5335 | 783524.0941
[17 empty] | 122 | 2025-06-23 | 243 | 4566.9566 | 5595.2792 | 638370.49 | 789119.3734
[17 empty] | 122 | 2025-06-24 | 244 | 4566.9566 | 5595.2792 | 642937.4466 | 794714.6526
[17 empty] | 122 | 2025-06-25 | 245 | 4566.9566 | 5595.2792 | 647504.4032 | 800309.9318
[17 empty] | 122 | 2025-06-26 | 246 | 4566.9566 | 5595.2792 | 652071.3598 | 805905.211
[17 empty] | 122 | 2025-06-27 | 247 | 4566.9566 | 5595.2792 | 656638.3164 | 811500.4902
[17 empty] | 122 | 2025-06-28 | 248 | 0 | 0 | 656638.3164 | 811500.4902
[17 empty] | 122 | 2025-06-29 | 249 | 0 | 0 | 656638.3164 | 811500.4902
[17 empty] | 122 | 2025-06-30 | 250 | 4566.9566 | 5595.2792 | 661205.273 | 817095.7694
[17 empty] | 122 | 2025-07-01 | 251 | 4566.9566 | 5595.2792 | 665772.2296 | 822691.0486
[17 empty] | 122 | 2025-07-02 | 252 | 4566.9566 | 5595.2792 | 670339.1862 | 828286.3278
[17 empty] | 122 | 2025-07-03 | 253 | 4566.9566 | 5595.2792 | 674906.1428 | 833881.607
[17 empty] | 122 | 2025-07-04 | 254 | 4566.9566 | 5595.2792 | 679473.0994 | 839476.8862
[17 empty] | 122 | 2025-07-05 | 255 | 0 | 0 | 679473.0994 | 839476.8862
[17 empty] | 122 | 2025-07-06 | 256 | 0 | 0 | 679473.0994 | 839476.8862
[17 empty] | 122 | 2025-07-07 | 257 | 4566.9566 | 5595.2792 | 684040.0559 | 845072.1655
[17 empty] | 122 | 2025-07-08 | 258 | 4566.9566 | 5595.2792 | 688607.0125 | 850667.4447
[17 empty] | 122 | 2025-07-09 | 259 | 4566.9566 | 5595.2792 | 693173.9691 | 856262.7239
[17 empty] | 122 | 2025-07-10 | 260 | 4566.9566 | 5595.2792 | 697740.9257 | 861858.0031
[17 empty] | 122 | 2025-07-11 | 261 | 4566.9566 | 5595.2792 | 702307.8823 | 867453.2823
[17 empty] | 122 | 2025-07-12 | 262 | 0 | 0 | 702307.8823 | 867453.2823
[17 empty] | 122 | 2025-07-13 | 263 | 0 | 0 | 702307.8823 | 867453.2823
[17 empty] | 122 | 2025-07-14 | 264 | 4566.9566 | 5595.2792 | 706874.8389 | 873048.5615
[17 empty] | 122 | 2025-07-15 | 265 | 4566.9566 | 5595.2792 | 711441.7955 | 878643.8407
[17 empty] | 122 | 2025-07-16 | 266 | 4566.9566 | 5595.2792 | 716008.7521 | 884239.1199
[17 empty] | 122 | 2025-07-17 | 267 | 4566.9566 | 5595.2792 | 720575.7087 | 889834.3991
[17 empty] | 122 | 2025-07-18 | 268 | 4566.9566 | 5595.2792 | 725142.6653 | 895429.6783
[17 empty] | 122 | 2025-07-19 | 269 | 0 | 0 | 725142.6653 | 895429.6783
[17 empty] | 122 | 2025-07-20 | 270 | 0 | 0 | 725142.6653 | 895429.6783
[17 empty] | 122 | 2025-07-21 | 271 | 4566.9566 | 5595.2792 | 729709.6218 | 901024.9576
[17 empty] | 122 | 2025-07-22 | 272 | 4566.9566 | 5595.2792 | 734276.5784 | 906620.2368
[17 empty] | 122 | 2025-07-23 | 273 | 4566.9566 | 5595.2792 | 738843.535 | 912215.516
[17 empty] | 122 | 2025-07-24 | 274 | 4566.9566 | 5595.2792 | 743410.4916 | 917810.7952
[17 empty] | 122 | 2025-07-25 | 275 | 4566.9566 | 5595.2792 | 747977.4482 | 923406.0744
[17 empty] | 122 | 2025-07-26 | 276 | 0 | 0 | 747977.4482 | 923406.0744
[17 empty] | 122 | 2025-07-27 | 277 | 0 | 0 | 747977.4482 | 923406.0744
[17 empty] | 122 | 2025-07-28 | 278 | 4566.9566 | 5595.2792 | 752544.4048 | 929001.3536
[17 empty] | 122 | 2025-07-29 | 279 | 4566.9566 | 5595.2792 | 757111.3614 | 934596.6328
[17 empty] | 122 | 2025-07-30 | 280 | 4566.9566 | 5595.2792 | 761678.318 | 940191.912
[17 empty] | 122 | 2025-07-31 | 281 | 4566.9566 | 5595.2792 | 766245.2746 | 945787.1912
[17 empty] | 122 | 2025-08-01 | 282 | 4566.9566 | 5595.2792 | 770812.2312 | 951382.4704
[17 empty] | 122 | 2025-08-02 | 283 | 0 | 0 | 770812.2312 | 951382.4704
[17 empty] | 122 | 2025-08-03 | 284 | 0 | 0 | 770812.2312 | 951382.4704
[17 empty] | 122 | 2025-08-04 | 285 | 4566.9566 | 5595.2792 | 775379.1877 | 956977.7497
[17 empty] | 122 | 2025-08-05 | 286 | 4566.9566 | 5595.2792 | 779946.1443 | 962573.0289
[17 empty] | 122 | 2025-08-06 | 287 | 4566.9566 | 5595.2792 | 784513.1009 | 968168.3081
[17 empty] | 122 | 2025-08-07 | 288 | 4566.9566 | 5595.2792 | 789080.0575 | 973763.5873
[17 empty] | 122 | 2025-08-08 | 289 | 4566.9566 | 5595.2792 | 793647.0141 | 979358.8665
[17 empty] | 122 | 2025-08-09 | 290 | 0 | 0 | 793647.0141 | 979358.8665
[17 empty] | 122 | 2025-08-10 | 291 | 0 | 0 | 793647.0141 | 979358.8665
[17 empty] | 122 | 2025-08-11 | 292 | 4566.9566 | 5595.2792 | 798213.9707 | 984954.1457
[17 empty] | 122 | 2025-08-12 | 293 | 4566.9566 | 5595.2792 | 802780.9273 | 990549.4249
[17 empty] | 122 | 2025-08-13 | 294 | 367.9566 | 430.5092 | 803148.8839 | 990979.9341
[17 empty] | 122 | 2025-08-14 | 295 | 367.9566 | 430.5092 | 803516.8405 | 991410.4433
[17 empty] | 122 | 2025-08-15 | 296 | 367.9566 | 430.5092 | 803884.7971 | 991840.9525
[17 empty] | 122 | 2025-08-16 | 297 | 0 | 0 | 803884.7971 | 991840.9525
[17 empty] | 122 | 2025-08-17 | 298 | 0 | 0 | 803884.7971 | 991840.9525
[17 empty] | 122 | 2025-08-18 | 299 | 367.9566 | 430.5092 | 804252.7536 | 992271.4618
[17 empty] | 122 | 2025-08-19 | 300 | 367.9566 | 430.5092 | 804620.7102 | 992701.971
[17 empty] | 122 | 2025-08-20 | 301 | 367.9566 | 430.5092 | 804988.6668 | 993132.4802
[17 empty] | 122 | 2025-08-21 | 302 | 367.9566 | 430.5092 | 805356.6234 | 993562.9894
[17 empty] | 122 | 2025-08-22 | 303 | 367.9566 | 430.5092 | 805724.58 | 993993.4986
[17 empty] | 123 | 2024-11-05 | 1 | 462.7886 | 513.6953 | 462.7886 | 513.6953
[17 empty] | 123 | 2024-11-06 | 2 | 462.7886 | 513.6953 | 925.5771 | 1027.3906
[17 empty] | 123 | 2024-11-07 | 3 | 462.7886 | 513.6953 | 1388.3657 | 1541.0859
[17 empty] | 123 | 2024-11-08 | 4 | 462.7886 | 513.6953 | 1851.1543 | 2054.7813
[17 empty] | 123 | 2024-11-09 | 5 | 0 | 0 | 1851.1543 | 2054.7813
[17 empty] | 123 | 2024-11-10 | 6 | 0 | 0 | 1851.1543 | 2054.7813
[17 empty] | 123 | 2024-11-11 | 7 | 3585.7886 | 3980.2253 | 5436.9429 | 6035.0066
[17 empty] | 123 | 2024-11-12 | 8 | 3585.7886 | 3980.2253 | 9022.7314 | 10015.2319
[17 empty] | 123 | 2024-11-13 | 9 | 3585.7886 | 3980.2253 | 12608.52 | 13995.4572
[17 empty] | 123 | 2024-11-14 | 10 | 3585.7886 | 3980.2253 | 16194.3086 | 17975.6825
[17 empty] | 123 | 2024-11-15 | 11 | 3585.7886 | 3980.2253 | 19780.0971 | 21955.9078
[17 empty] | 123 | 2024-11-16 | 12 | 0 | 0 | 19780.0971 | 21955.9078
[17 empty] | 123 | 2024-11-17 | 13 | 0 | 0 | 19780.0971 | 21955.9078
[17 empty] | 123 | 2024-11-18 | 14 | 3585.7886 | 3980.2253 | 23365.8857 | 25936.1331
[17 empty] | 123 | 2024-11-19 | 15 | 3585.7886 | 3980.2253 | 26951.6743 | 29916.3585
[17 empty] | 123 | 2024-11-20 | 16 | 3585.7886 | 3980.2253 | 30537.4629 | 33896.5838
[17 empty] | 123 | 2024-11-21 | 17 | 3585.7886 | 3980.2253 | 34123.2514 | 37876.8091
[17 empty] | 123 | 2024-11-22 | 18 | 3585.7886 | 3980.2253 | 37709.04 | 41857.0344
[17 empty] | 123 | 2024-11-23 | 19 | 0 | 0 | 37709.04 | 41857.0344
[17 empty] | 123 | 2024-11-24 | 20 | 0 | 0 | 37709.04 | 41857.0344
[17 empty] | 123 | 2024-11-25 | 21 | 3585.7886 | 3980.2253 | 41294.8286 | 45837.2597
[17 empty] | 123 | 2024-11-26 | 22 | 3585.7886 | 3980.2253 | 44880.6171 | 49817.485
[17 empty] | 123 | 2024-11-27 | 23 | 3585.7886 | 3980.2253 | 48466.4057 | 53797.7103
[17 empty] | 123 | 2024-11-28 | 24 | 3585.7886 | 3980.2253 | 52052.1943 | 57777.9357
[17 empty] | 123 | 2024-11-29 | 25 | 3585.7886 | 3980.2253 | 55637.9829 | 61758.161
[17 empty] | 123 | 2024-11-30 | 26 | 0 | 0 | 55637.9829 | 61758.161
[17 empty] | 123 | 2024-12-01 | 27 | 0 | 0 | 55637.9829 | 61758.161
[17 empty] | 123 | 2024-12-02 | 28 | 3585.7886 | 3980.2253 | 59223.7714 | 65738.3863
[17 empty] | 123 | 2024-12-03 | 29 | 3585.7886 | 3980.2253 | 62809.56 | 69718.6116
[17 empty] | 123 | 2024-12-04 | 30 | 3585.7886 | 3980.2253 | 66395.3486 | 73698.8369
[17 empty] | 123 | 2024-12-05 | 31 | 3585.7886 | 3980.2253 | 69981.1371 | 77679.0622
[17 empty] | 123 | 2024-12-06 | 32 | 3585.7886 | 3980.2253 | 73566.9257 | 81659.2875
[17 empty] | 123 | 2024-12-07 | 33 | 0 | 0 | 73566.9257 | 81659.2875
[17 empty] | 123 | 2024-12-08 | 34 | 0 | 0 | 73566.9257 | 81659.2875
[17 empty] | 123 | 2024-12-09 | 35 | 3585.7886 | 3980.2253 | 77152.7143 | 85639.5129
[17 empty] | 123 | 2024-12-10 | 36 | 3585.7886 | 3980.2253 | 80738.5029 | 89619.7382
[17 empty] | 123 | 2024-12-11 | 37 | 3585.7886 | 3980.2253 | 84324.2914 | 93599.9635
[17 empty] | 123 | 2024-12-12 | 38 | 5412.0358 | 6171.7219 | 89736.3272 | 99771.6854
[17 empty] | 123 | 2024-12-13 | 39 | 2289.0358 | 2705.1919 | 92025.363 | 102476.8774
[17 empty] | 123 | 2024-12-14 | 40 | 0 | 0 | 92025.363 | 102476.8774
[17 empty] | 123 | 2024-12-15 | 41 | 0 | 0 | 92025.363 | 102476.8774
[17 empty] | 123 | 2024-12-16 | 42 | 2289.0358 | 2705.1919 | 94314.3987 | 105182.0693
[17 empty] | 123 | 2024-12-17 | 43 | 2289.0358 | 2705.1919 | 96603.4345 | 107887.2613
[17 empty] | 123 | 2024-12-18 | 44 | 2289.0358 | 2705.1919 | 98892.4702 | 110592.4532
[17 empty] | 123 | 2024-12-19 | 45 | 2289.0358 | 2705.1919 | 101181.506 | 113297.6451
[17 empty] | 123 | 2024-12-20 | 46 | 2289.0358 | 2705.1919 | 103470.5418 | 116002.8371
[17 empty] | 123 | 2024-12-21 | 47 | 0 | 0 | 103470.5418 | 116002.8371
[17 empty] | 123 | 2024-12-22 | 48 | 0 | 0 | 103470.5418 | 116002.8371
[17 empty] | 123 | 2024-12-23 | 49 | 2289.0358 | 2705.1919 | 105759.5775 | 118708.029
[17 empty] | 123 | 2024-12-24 | 50 | 2289.0358 | 2705.1919 | 108048.6133 | 121413.221
[17 empty] | 123 | 2024-12-25 | 51 | 2289.0358 | 2705.1919 | 110337.6491 | 124118.4129
[17 empty] | 123 | 2024-12-26 | 52 | 2289.0358 | 2705.1919 | 112626.6848 | 126823.6049
[17 empty] | 123 | 2024-12-27 | 53 | 2289.0358 | 2705.1919 | 114915.7206 | 129528.7968
[17 empty] | 123 | 2024-12-28 | 54 | 0 | 0 | 114915.7206 | 129528.7968
[17 empty] | 123 | 2024-12-29 | 55 | 0 | 0 | 114915.7206 | 129528.7968
[17 empty] | 123 | 2024-12-30 | 56 | 2289.0358 | 2705.1919 | 117204.7563 | 132233.9888
[17 empty] | 123 | 2024-12-31 | 57 | 2289.0358 | 2705.1919 | 119493.7921 | 134939.1807
[17 empty] | 123 | 2025-01-01 | 58 | 2289.0358 | 2705.1919 | 121782.8279 | 137644.3726
[17 empty] | 123 | 2025-01-02 | 59 | 2289.0358 | 2705.1919 | 124071.8636 | 140349.5646
[17 empty] | 123 | 2025-01-03 | 60 | 2289.0358 | 2705.1919 | 126360.8994 | 143054.7565
[17 empty] | 123 | 2025-01-04 | 61 | 0 | 0 | 126360.8994 | 143054.7565
[17 empty] | 123 | 2025-01-05 | 62 | 0 | 0 | 126360.8994 | 143054.7565
[17 empty] | 123 | 2025-01-06 | 63 | 2289.0358 | 2705.1919 | 128649.9352 | 145759.9485
[17 empty] | 123 | 2025-01-07 | 64 | 2289.0358 | 2705.1919 | 130938.9709 | 148465.1404
[17 empty] | 123 | 2025-01-08 | 65 | 2289.0358 | 2705.1919 | 133228.0067 | 151170.3324
[17 empty] | 123 | 2025-01-09 | 66 | 2289.0358 | 2705.1919 | 135517.0424 | 153875.5243
[17 empty] | 123 | 2025-01-10 | 67 | 2289.0358 | 2705.1919 | 137806.0782 | 156580.7162
[17 empty] | 123 | 2025-01-11 | 68 | 0 | 0 | 137806.0782 | 156580.7162
[17 empty] | 123 | 2025-01-12 | 69 | 0 | 0 | 137806.0782 | 156580.7162
[17 empty] | 123 | 2025-01-13 | 70 | 2289.0358 | 2705.1919 | 140095.114 | 159285.9082
[17 empty] | 123 | 2025-01-14 | 71 | 2289.0358 | 2705.1919 | 142384.1497 | 161991.1001
[17 empty] | 123 | 2025-01-15 | 72 | 2289.0358 | 2705.1919 | 144673.1855 | 164696.2921
[17 empty] | 123 | 2025-01-16 | 73 | 2289.0358 | 2705.1919 | 146962.2213 | 167401.484
[17 empty] | 123 | 2025-01-17 | 74 | 2289.0358 | 2705.1919 | 149251.257 | 170106.676
[17 empty] | 123 | 2025-01-18 | 75 | 0 | 0 | 149251.257 | 170106.676
[17 empty] | 123 | 2025-01-19 | 76 | 0 | 0 | 149251.257 | 170106.676
[17 empty] | 123 | 2025-01-20 | 77 | 2289.0358 | 2705.1919 | 151540.2928 | 172811.8679
[17 empty] | 123 | 2025-01-21 | 78 | 2289.0358 | 2705.1919 | 153829.3285 | 175517.0598
[17 empty] | 123 | 2025-01-22 | 79 | 2289.0358 | 2705.1919 | 156118.3643 | 178222.2518
[17 empty] | 123 | 2025-01-23 | 80 | 2289.0358 | 2705.1919 | 158407.4001 | 180927.4437
[17 empty] | 123 | 2025-01-24 | 81 | 2289.0358 | 2705.1919 | 160696.4358 | 183632.6357
[17 empty] | 123 | 2025-01-25 | 82 | 0 | 0 | 160696.4358 | 183632.6357
[17 empty] | 123 | 2025-01-26 | 83 | 0 | 0 | 160696.4358 | 183632.6357
[17 empty] | 123 | 2025-01-27 | 84 | 2289.0358 | 2705.1919 | 162985.4716 | 186337.8276
[17 empty] | 123 | 2025-01-28 | 85 | 2289.0358 | 2705.1919 | 165274.5074 | 189043.0196
[17 empty] | 123 | 2025-01-29 | 86 | 2289.0358 | 2705.1919 | 167563.5431 | 191748.2115
[17 empty] | 123 | 2025-01-30 | 87 | 2289.0358 | 2705.1919 | 169852.5789 | 194453.4035
[17 empty] | 123 | 2025-01-31 | 88 | 2289.0358 | 2705.1919 | 172141.6146 | 197158.5954
[17 empty] | 123 | 2025-02-01 | 89 | 0 | 0 | 172141.6146 | 197158.5954
[17 empty] | 123 | 2025-02-02 | 90 | 0 | 0 | 172141.6146 | 197158.5954
[17 empty] | 123 | 2025-02-03 | 91 | 2289.0358 | 2705.1919 | 174430.6504 | 199863.7873
[17 empty] | 123 | 2025-02-04 | 92 | 2289.0358 | 2705.1919 | 176719.6862 | 202568.9793
[17 empty] | 123 | 2025-02-05 | 93 | 2289.0358 | 2705.1919 | 179008.7219 | 205274.1712
[17 empty] | 123 | 2025-02-06 | 94 | 2289.0358 | 2705.1919 | 181297.7577 | 207979.3632
[17 empty] | 123 | 2025-02-07 | 95 | 2289.0358 | 2705.1919 | 183586.7935 | 210684.5551
[17 empty] | 123 | 2025-02-08 | 96 | 0 | 0 | 183586.7935 | 210684.5551
[17 empty] | 123 | 2025-02-09 | 97 | 0 | 0 | 183586.7935 | 210684.5551
[17 empty] | 123 | 2025-02-10 | 98 | 2289.0358 | 2705.1919 | 185875.8292 | 213389.7471
[17 empty] | 123 | 2025-02-11 | 99 | 2289.0358 | 2705.1919 | 188164.865 | 216094.939
[17 empty] | 123 | 2025-02-12 | 100 | 2289.0358 | 2705.1919 | 190453.9007 | 218800.1309
[17 empty] | 123 | 2025-02-13 | 101 | 2289.0358 | 2705.1919 | 192742.9365 | 221505.3229
[17 empty] | 123 | 2025-02-14 | 102 | 2289.0358 | 2705.1919 | 195031.9723 | 224210.5148
[17 empty] | 123 | 2025-02-15 | 103 | 0 | 0 | 195031.9723 | 224210.5148
[17 empty] | 123 | 2025-02-16 | 104 | 0 | 0 | 195031.9723 | 224210.5148
[17 empty] | 123 | 2025-02-17 | 105 | 2289.0358 | 2705.1919 | 197321.008 | 226915.7068
[17 empty] | 123 | 2025-02-18 | 106 | 2289.0358 | 2705.1919 | 199610.0438 | 229620.8987
[17 empty] | 123 | 2025-02-19 | 107 | 2289.0358 | 2705.1919 | 201899.0796 | 232326.0907
[17 empty] | 123 | 2025-02-20 | 108 | 2289.0358 | 2705.1919 | 204188.1153 | 235031.2826
[17 empty] | 123 | 2025-02-21 | 109 | 2289.0358 | 2705.1919 | 206477.1511 | 237736.4745
[17 empty] | 123 | 2025-02-22 | 110 | 0 | 0 | 206477.1511 | 237736.4745
[17 empty] | 123 | 2025-02-23 | 111 | 0 | 0 | 206477.1511 | 237736.4745
[17 empty] | 123 | 2025-02-24 | 112 | 2289.0358 | 2705.1919 | 208766.1868 | 240441.6665
[17 empty] | 123 | 2025-02-25 | 113 | 2289.0358 | 2705.1919 | 211055.2226 | 243146.8584
[17 empty] | 123 | 2025-02-26 | 114 | 2289.0358 | 2705.1919 | 213344.2584 | 245852.0504
[17 empty] | 123 | 2025-02-27 | 115 | 2289.0358 | 2705.1919 | 215633.2941 | 248557.2423
[17 empty] | 123 | 2025-02-28 | 116 | 2289.0358 | 2705.1919 | 217922.3299 | 251262.4343
[17 empty] | 123 | 2025-03-01 | 117 | 0 | 0 | 217922.3299 | 251262.4343
[17 empty] | 123 | 2025-03-02 | 118 | 0 | 0 | 217922.3299 | 251262.4343
[17 empty] | 123 | 2025-03-03 | 119 | 2289.0358 | 2705.1919 | 220211.3657 | 253967.6262
[17 empty] | 123 | 2025-03-04 | 120 | 2289.0358 | 2705.1919 | 222500.4014 | 256672.8182
[17 empty] | 123 | 2025-03-05 | 121 | 2289.0358 | 2705.1919 | 224789.4372 | 259378.0101
[17 empty] | 123 | 2025-03-06 | 122 | 2289.0358 | 2705.1919 | 227078.4729 | 262083.202
[17 empty] | 123 | 2025-03-07 | 123 | 2289.0358 | 2705.1919 | 229367.5087 | 264788.394
[17 empty] | 123 | 2025-03-08 | 124 | 0 | 0 | 229367.5087 | 264788.394
[17 empty] | 123 | 2025-03-09 | 125 | 0 | 0 | 229367.5087 | 264788.394
[17 empty] | 123 | 2025-03-10 | 126 | 2289.0358 | 2705.1919 | 231656.5445 | 267493.5859
[17 empty] | 123 | 2025-03-11 | 127 | 2289.0358 | 2705.1919 | 233945.5802 | 270198.7779
[17 empty] | 123 | 2025-03-12 | 128 | 2289.0358 | 2705.1919 | 236234.616 | 272903.9698
[17 empty] | 123 | 2025-03-13 | 129 | 2289.0358 | 2705.1919 | 238523.6517 | 275609.1618
[17 empty] | 123 | 2025-03-14 | 130 | 2289.0358 | 2705.1919 | 240812.6875 | 278314.3537
[17 empty] | 123 | 2025-03-15 | 131 | 0 | 0 | 240812.6875 | 278314.3537
[17 empty] | 123 | 2025-03-16 | 132 | 0 | 0 | 240812.6875 | 278314.3537
[17 empty] | 123 | 2025-03-17 | 133 | 2289.0358 | 2705.1919 | 243101.7233 | 281019.5456
[17 empty] | 123 | 2025-03-18 | 134 | 2289.0358 | 2705.1919 | 245390.759 | 283724.7376
[17 empty] | 123 | 2025-03-19 | 135 | 2289.0358 | 2705.1919 | 247679.7948 | 286429.9295
[17 empty] | 123 | 2025-03-20 | 136 | 2289.0358 | 2705.1919 | 249968.8306 | 289135.1215
[17 empty] | 123 | 2025-03-21 | 137 | 2289.0358 | 2705.1919 | 252257.8663 | 291840.3134
[17 empty] | 123 | 2025-03-22 | 138 | 0 | 0 | 252257.8663 | 291840.3134
[17 empty] | 123 | 2025-03-23 | 139 | 0 | 0 | 252257.8663 | 291840.3134
[17 empty] | 123 | 2025-03-24 | 140 | 2289.0358 | 2705.1919 | 254546.9021 | 294545.5054
[17 empty] | 123 | 2025-03-25 | 141 | 2289.0358 | 2705.1919 | 256835.9378 | 297250.6973
[17 empty] | 123 | 2025-03-26 | 142 | 6275.8108 | 7848.1317 | 263111.7486 | 305098.829
[17 empty] | 123 | 2025-03-27 | 143 | 6275.8108 | 7848.1317 | 269387.5594 | 312946.9607
[17 empty] | 123 | 2025-03-28 | 144 | 6275.8108 | 7848.1317 | 275663.3701 | 320795.0924
[17 empty] | 123 | 2025-03-29 | 145 | 0 | 0 | 275663.3701 | 320795.0924
[17 empty] | 123 | 2025-03-30 | 146 | 0 | 0 | 275663.3701 | 320795.0924
[17 empty] | 123 | 2025-03-31 | 147 | 6275.8108 | 7848.1317 | 281939.1809 | 328643.2241
[17 empty] | 123 | 2025-04-01 | 148 | 6275.8108 | 7848.1317 | 288214.9917 | 336491.3558
[17 empty] | 123 | 2025-04-02 | 149 | 6275.8108 | 7848.1317 | 294490.8024 | 344339.4875
[17 empty] | 123 | 2025-04-03 | 150 | 6275.8108 | 7848.1317 | 300766.6132 | 352187.6192
[17 empty] | 123 | 2025-04-04 | 151 | 6275.8108 | 7848.1317 | 307042.4239 | 360035.7509
[17 empty] | 123 | 2025-04-05 | 152 | 0 | 0 | 307042.4239 | 360035.7509
[17 empty] | 123 | 2025-04-06 | 153 | 0 | 0 | 307042.4239 | 360035.7509
[17 empty] | 123 | 2025-04-07 | 154 | 10580.8108 | 13444.6317 | 317623.2347 | 373480.3825
[17 empty] | 123 | 2025-04-08 | 155 | 10580.8108 | 13444.6317 | 328204.0455 | 386925.0142
[17 empty] | 123 | 2025-04-09 | 156 | 10580.8108 | 13444.6317 | 338784.8562 | 400369.6459
[17 empty] | 123 | 2025-04-10 | 157 | 10580.8108 | 13444.6317 | 349365.667 | 413814.2776
[17 empty] | 123 | 2025-04-11 | 158 | 10580.8108 | 13444.6317 | 359946.4778 | 427258.9093
[17 empty] | 123 | 2025-04-12 | 159 | 0 | 0 | 359946.4778 | 427258.9093
[17 empty] | 123 | 2025-04-13 | 160 | 0 | 0 | 359946.4778 | 427258.9093
[17 empty] | 123 | 2025-04-14 | 161 | 10580.8108 | 13444.6317 | 370527.2885 | 440703.541
[17 empty] | 123 | 2025-04-15 | 162 | 10580.8108 | 13444.6317 | 381108.0993 | 454148.1727
[17 empty] | 123 | 2025-04-16 | 163 | 8754.5636 | 11253.1351 | 389862.6629 | 465401.3078
[17 empty] | 123 | 2025-04-17 | 164 | 8754.5636 | 11253.1351 | 398617.2264 | 476654.4428
[17 empty] | 123 | 2025-04-18 | 165 | 8754.5636 | 11253.1351 | 407371.79 | 487907.5779
[17 empty] | 123 | 2025-04-19 | 166 | 0 | 0 | 407371.79 | 487907.5779
[17 empty] | 123 | 2025-04-20 | 167 | 0 | 0 | 407371.79 | 487907.5779
[17 empty] | 123 | 2025-04-21 | 168 | 8754.5636 | 11253.1351 | 416126.3536 | 499160.713
[17 empty] | 123 | 2025-04-22 | 169 | 8754.5636 | 11253.1351 | 424880.9171 | 510413.848
[17 empty] | 123 | 2025-04-23 | 170 | 8754.5636 | 11253.1351 | 433635.4807 | 521666.9831
[17 empty] | 123 | 2025-04-24 | 171 | 8754.5636 | 11253.1351 | 442390.0443 | 532920.1182
[17 empty] | 123 | 2025-04-25 | 172 | 8754.5636 | 11253.1351 | 451144.6079 | 544173.2532
[17 empty] | 123 | 2025-04-26 | 173 | 0 | 0 | 451144.6079 | 544173.2532
[17 empty] | 123 | 2025-04-27 | 174 | 0 | 0 | 451144.6079 | 544173.2532
[17 empty] | 123 | 2025-04-28 | 175 | 8754.5636 | 11253.1351 | 459899.1714 | 555426.3883
[17 empty] | 123 | 2025-04-29 | 176 | 8754.5636 | 11253.1351 | 468653.735 | 566679.5234
[17 empty] | 123 | 2025-04-30 | 177 | 8754.5636 | 11253.1351 | 477408.2986 | 577932.6584
[17 empty] | 123 | 2025-05-01 | 178 | 8754.5636 | 11253.1351 | 486162.8621 | 589185.7935
[17 empty] | 123 | 2025-05-02 | 179 | 8754.5636 | 11253.1351 | 494917.4257 | 600438.9285
[17 empty] | 123 | 2025-05-03 | 180 | 0 | 0 | 494917.4257 | 600438.9285
[17 empty] | 123 | 2025-05-04 | 181 | 0 | 0 | 494917.4257 | 600438.9285
[17 empty] | 123 | 2025-05-05 | 182 | 8754.5636 | 11253.1351 | 503671.9893 | 611692.0636
[17 empty] | 123 | 2025-05-06 | 183 | 8754.5636 | 11253.1351 | 512426.5529 | 622945.1987
[17 empty] | 123 | 2025-05-07 | 184 | 8754.5636 | 11253.1351 | 521181.1164 | 634198.3337
[17 empty] | 123 | 2025-05-08 | 185 | 8754.5636 | 11253.1351 | 529935.68 | 645451.4688
[17 empty] | 123 | 2025-05-09 | 186 | 8754.5636 | 11253.1351 | 538690.2436 | 656704.6039
[17 empty] | 123 | 2025-05-10 | 187 | 0 | 0 | 538690.2436 | 656704.6039
[17 empty] | 123 | 2025-05-11 | 188 | 0 | 0 | 538690.2436 | 656704.6039
[17 empty] | 123 | 2025-05-12 | 189 | 8754.5636 | 11253.1351 | 547444.8071 | 667957.7389
[17 empty] | 123 | 2025-05-13 | 190 | 8754.5636 | 11253.1351 | 556199.3707 | 679210.874
[17 empty] | 123 | 2025-05-14 | 191 | 8754.5636 | 11253.1351 | 564953.9343 | 690464.0091
[17 empty] | 123 | 2025-05-15 | 192 | 8754.5636 | 11253.1351 | 573708.4979 | 701717.1441
[17 empty] | 123 | 2025-05-16 | 193 | 8754.5636 | 11253.1351 | 582463.0614 | 712970.2792
[17 empty] | 123 | 2025-05-17 | 194 | 0 | 0 | 582463.0614 | 712970.2792
[17 empty] | 123 | 2025-05-18 | 195 | 0 | 0 | 582463.0614 | 712970.2792
[17 empty] | 123 | 2025-05-19 | 196 | 8754.5636 | 11253.1351 | 591217.625 | 724223.4143
[17 empty] | 123 | 2025-05-20 | 197 | 8754.5636 | 11253.1351 | 599972.1886 | 735476.5493
[17 empty] | 123 | 2025-05-21 | 198 | 4767.7886 | 6110.1953 | 604739.9771 | 741586.7446
[17 empty] | 123 | 2025-05-22 | 199 | 4767.7886 | 6110.1953 | 609507.7657 | 747696.9399
[17 empty] | 123 | 2025-05-23 | 200 | 4767.7886 | 6110.1953 | 614275.5543 | 753807.1353
[17 empty] | 123 | 2025-05-24 | 201 | 0 | 0 | 614275.5543 | 753807.1353
[17 empty] | 123 | 2025-05-25 | 202 | 0 | 0 | 614275.5543 | 753807.1353
[17 empty] | 123 | 2025-05-26 | 203 | 4767.7886 | 6110.1953 | 619043.3429 | 759917.3306
[17 empty] | 123 | 2025-05-27 | 204 | 4767.7886 | 6110.1953 | 623811.1314 | 766027.5259
[17 empty] | 123 | 2025-05-28 | 205 | 4767.7886 | 6110.1953 | 628578.92 | 772137.7212
[17 empty] | 123 | 2025-05-29 | 206 | 4767.7886 | 6110.1953 | 633346.7086 | 778247.9165
[17 empty] | 123 | 2025-05-30 | 207 | 4767.7886 | 6110.1953 | 638114.4971 | 784358.1118
[17 empty] | 123 | 2025-05-31 | 208 | 0 | 0 | 638114.4971 | 784358.1118
[17 empty] | 123 | 2025-06-01 | 209 | 0 | 0 | 638114.4971 | 784358.1118
[17 empty] | 123 | 2025-06-02 | 210 | 4767.7886 | 6110.1953 | 642882.2857 | 790468.3071
[17 empty] | 123 | 2025-06-03 | 211 | 4767.7886 | 6110.1953 | 647650.0743 | 796578.5025
[17 empty] | 123 | 2025-06-04 | 212 | 4767.7886 | 6110.1953 | 652417.8629 | 802688.6978
[17 empty] | 123 | 2025-06-05 | 213 | 4767.7886 | 6110.1953 | 657185.6514 | 808798.8931
[17 empty] | 123 | 2025-06-06 | 214 | 4767.7886 | 6110.1953 | 661953.44 | 814909.0884
[17 empty] | 123 | 2025-06-07 | 215 | 0 | 0 | 661953.44 | 814909.0884
[17 empty] | 123 | 2025-06-08 | 216 | 0 | 0 | 661953.44 | 814909.0884
[17 empty] | 123 | 2025-06-09 | 217 | 4767.7886 | 6110.1953 | 666721.2286 | 821019.2837
[17 empty] | 123 | 2025-06-10 | 218 | 4767.7886 | 6110.1953 | 671489.0171 | 827129.479
[17 empty] | 123 | 2025-06-11 | 219 | 4767.7886 | 6110.1953 | 676256.8057 | 833239.6743
[17 empty] | 123 | 2025-06-12 | 220 | 4767.7886 | 6110.1953 | 681024.5943 | 839349.8697
[17 empty] | 123 | 2025-06-13 | 221 | 4767.7886 | 6110.1953 | 685792.3829 | 845460.065
[17 empty] | 123 | 2025-06-14 | 222 | 0 | 0 | 685792.3829 | 845460.065
[17 empty] | 123 | 2025-06-15 | 223 | 0 | 0 | 685792.3829 | 845460.065
[17 empty] | 123 | 2025-06-16 | 224 | 4767.7886 | 6110.1953 | 690560.1714 | 851570.2603
[17 empty] | 123 | 2025-06-17 | 225 | 4767.7886 | 6110.1953 | 695327.96 | 857680.4556
[17 empty] | 123 | 2025-06-18 | 226 | 4767.7886 | 6110.1953 | 700095.7486 | 863790.6509
[17 empty] | 123 | 2025-06-19 | 227 | 4767.7886 | 6110.1953 | 704863.5371 | 869900.8462
[17 empty] | 123 | 2025-06-20 | 228 | 4767.7886 | 6110.1953 | 709631.3257 | 876011.0415
[17 empty] | 123 | 2025-06-21 | 229 | 0 | 0 | 709631.3257 | 876011.0415
[17 empty] | 123 | 2025-06-22 | 230 | 0 | 0 | 709631.3257 | 876011.0415
[17 empty] | 123 | 2025-06-23 | 231 | 4767.7886 | 6110.1953 | 714399.1143 | 882121.2369
[17 empty] | 123 | 2025-06-24 | 232 | 4767.7886 | 6110.1953 | 719166.9029 | 888231.4322
[17 empty] | 123 | 2025-06-25 | 233 | 4767.7886 | 6110.1953 | 723934.6914 | 894341.6275
[17 empty] | 123 | 2025-06-26 | 234 | 4767.7886 | 6110.1953 | 728702.48 | 900451.8228
[17 empty] | 123 | 2025-06-27 | 235 | 4767.7886 | 6110.1953 | 733470.2686 | 906562.0181
[17 empty] | 123 | 2025-06-28 | 236 | 0 | 0 | 733470.2686 | 906562.0181
[17 empty] | 123 | 2025-06-29 | 237 | 0 | 0 | 733470.2686 | 906562.0181
[17 empty] | 123 | 2025-06-30 | 238 | 4767.7886 | 6110.1953 | 738238.0571 | 912672.2134
[17 empty] | 123 | 2025-07-01 | 239 | 4767.7886 | 6110.1953 | 743005.8457 | 918782.4087
[17 empty] | 123 | 2025-07-02 | 240 | 4767.7886 | 6110.1953 | 747773.6343 | 924892.6041
[17 empty] | 123 | 2025-07-03 | 241 | 4767.7886 | 6110.1953 | 752541.4229 | 931002.7994
[17 empty] | 123 | 2025-07-04 | 242 | 4767.7886 | 6110.1953 | 757309.2114 | 937112.9947
[17 empty] | 123 | 2025-07-05 | 243 | 0 | 0 | 757309.2114 | 937112.9947
[17 empty] | 123 | 2025-07-06 | 244 | 0 | 0 | 757309.2114 | 937112.9947
[17 empty] | 123 | 2025-07-07 | 245 | 4767.7886 | 6110.1953 | 762077 | 943223.19
[17 empty] | 123 | 2025-07-08 | 246 | 4767.7886 | 6110.1953 | 766844.7886 | 949333.3853
[17 empty] | 123 | 2025-07-09 | 247 | 4767.7886 | 6110.1953 | 771612.5771 | 955443.5806
[17 empty] | 123 | 2025-07-10 | 248 | 4767.7886 | 6110.1953 | 776380.3657 | 961553.7759
[17 empty] | 123 | 2025-07-11 | 249 | 4767.7886 | 6110.1953 | 781148.1543 | 967663.9713
[17 empty] | 123 | 2025-07-12 | 250 | 0 | 0 | 781148.1543 | 967663.9713
[17 empty] | 123 | 2025-07-13 | 251 | 0 | 0 | 781148.1543 | 967663.9713
[17 empty] | 123 | 2025-07-14 | 252 | 4767.7886 | 6110.1953 | 785915.9429 | 973774.1666
[17 empty] | 123 | 2025-07-15 | 253 | 4767.7886 | 6110.1953 | 790683.7314 | 979884.3619
[17 empty] | 123 | 2025-07-16 | 254 | 4767.7886 | 6110.1953 | 795451.52 | 985994.5572
[17 empty] | 123 | 2025-07-17 | 255 | 4767.7886 | 6110.1953 | 800219.3086 | 992104.7525
[17 empty] | 123 | 2025-07-18 | 256 | 4767.7886 | 6110.1953 | 804987.0971 | 998214.9478
[17 empty] | 123 | 2025-07-19 | 257 | 0 | 0 | 804987.0971 | 998214.9478
[17 empty] | 123 | 2025-07-20 | 258 | 0 | 0 | 804987.0971 | 998214.9478
[17 empty] | 123 | 2025-07-21 | 259 | 4767.7886 | 6110.1953 | 809754.8857 | 1004325.1431
[17 empty] | 123 | 2025-07-22 | 260 | 4767.7886 | 6110.1953 | 814522.6743 | 1010435.3385
[17 empty] | 123 | 2025-07-23 | 261 | 4767.7886 | 6110.1953 | 819290.4629 | 1016545.5338
[17 empty] | 123 | 2025-07-24 | 262 | 4767.7886 | 6110.1953 | 824058.2514 | 1022655.7291
[17 empty] | 123 | 2025-07-25 | 263 | 4767.7886 | 6110.1953 | 828826.04 | 1028765.9244
[17 empty] | 123 | 2025-07-26 | 264 | 0 | 0 | 828826.04 | 1028765.9244
[17 empty] | 123 | 2025-07-27 | 265 | 0 | 0 | 828826.04 | 1028765.9244
[17 empty] | 123 | 2025-07-28 | 266 | 4767.7886 | 6110.1953 | 833593.8286 | 1034876.1197
[17 empty] | 123 | 2025-07-29 | 267 | 4767.7886 | 6110.1953 | 838361.6171 | 1040986.315
[17 empty] | 123 | 2025-07-30 | 268 | 4767.7886 | 6110.1953 | 843129.4057 | 1047096.5103
[17 empty] | 123 | 2025-07-31 | 269 | 4767.7886 | 6110.1953 | 847897.1943 | 1053206.7057
[17 empty] | 123 | 2025-08-01 | 270 | 4767.7886 | 6110.1953 | 852664.9829 | 1059316.901
[17 empty] | 123 | 2025-08-02 | 271 | 0 | 0 | 852664.9829 | 1059316.901
[17 empty] | 123 | 2025-08-03 | 272 | 0 | 0 | 852664.9829 | 1059316.901
[17 empty] | 123 | 2025-08-04 | 273 | 4767.7886 | 6110.1953 | 857432.7714 | 1065427.0963
[17 empty] | 123 | 2025-08-05 | 274 | 4767.7886 | 6110.1953 | 862200.56 | 1071537.2916
[17 empty] | 123 | 2025-08-06 | 275 | 4767.7886 | 6110.1953 | 866968.3486 | 1077647.4869
[17 empty] | 123 | 2025-08-07 | 276 | 4767.7886 | 6110.1953 | 871736.1371 | 1083757.6822
[17 empty] | 123 | 2025-08-08 | 277 | 4767.7886 | 6110.1953 | 876503.9257 | 1089867.8775
[17 empty] | 123 | 2025-08-09 | 278 | 0 | 0 | 876503.9257 | 1089867.8775
[17 empty] | 123 | 2025-08-10 | 279 | 0 | 0 | 876503.9257 | 1089867.8775
[17 empty] | 123 | 2025-08-11 | 280 | 4767.7886 | 6110.1953 | 881271.7143 | 1095978.0729
[17 empty] | 123 | 2025-08-12 | 281 | 4767.7886 | 6110.1953 | 886039.5029 | 1102088.2682
[17 empty] | 123 | 2025-08-13 | 282 | 4767.7886 | 6110.1953 | 890807.2914 | 1108198.4635
[17 empty] | 123 | 2025-08-14 | 283 | 4767.7886 | 6110.1953 | 895575.08 | 1114308.6588
[17 empty] | 123 | 2025-08-15 | 284 | 4767.7886 | 6110.1953 | 900342.8686 | 1120418.8541
[17 empty] | 123 | 2025-08-16 | 285 | 0 | 0 | 900342.8686 | 1120418.8541
[17 empty] | 123 | 2025-08-17 | 286 | 0 | 0 | 900342.8686 | 1120418.8541
[17 empty] | 123 | 2025-08-18 | 287 | 4767.7886 | 6110.1953 | 905110.6571 | 1126529.0494
[17 empty] | 123 | 2025-08-19 | 288 | 4767.7886 | 6110.1953 | 909878.4457 | 1132639.2447
[17 empty] | 123 | 2025-08-20 | 289 | 4767.7886 | 6110.1953 | 914646.2343 | 1138749.4401
[17 empty] | 123 | 2025-08-21 | 290 | 4767.7886 | 6110.1953 | 919414.0229 | 1144859.6354
[17 empty] | 123 | 2025-08-22 | 291 | 4767.7886 | 6110.1953 | 924181.8114 | 1150969.8307
[17 empty] | 123 | 2025-08-23 | 292 | 0 | 0 | 924181.8114 | 1150969.8307
[17 empty] | 123 | 2025-08-24 | 293 | 0 | 0 | 924181.8114 | 1150969.8307
[17 empty] | 123 | 2025-08-25 | 294 | 4767.7886 | 6110.1953 | 928949.6 | 1157080.026
[17 empty] | 123 | 2025-08-26 | 295 | 4767.7886 | 6110.1953 | 933717.3886 | 1163190.2213
[17 empty] | 123 | 2025-08-27 | 296 | 4767.7886 | 6110.1953 | 938485.1771 | 1169300.4166
[17 empty] | 123 | 2025-08-28 | 297 | 4767.7886 | 6110.1953 | 943252.9657 | 1175410.6119
[17 empty] | 123 | 2025-08-29 | 298 | 4767.7886 | 6110.1953 | 948020.7543 | 1181520.8073
[17 empty] | 123 | 2025-08-30 | 299 | 0 | 0 | 948020.7543 | 1181520.8073
[17 empty] | 123 | 2025-08-31 | 300 | 0 | 0 | 948020.7543 | 1181520.8073
[17 empty] | 123 | 2025-09-01 | 301 | 4767.7886 | 6110.1953 | 952788.5429 | 1187631.0026
[17 empty] | 123 | 2025-09-02 | 302 | 4767.7886 | 6110.1953 | 957556.3314 | 1193741.1979
[17 empty] | 123 | 2025-09-03 | 303 | 4767.7886 | 6110.1953 | 962324.12 | 1199851.3932
[17 empty] | 123 | 2025-09-04 | 304 | 4767.7886 | 6110.1953 | 967091.9086 | 1205961.5885
[17 empty] | 123 | 2025-09-05 | 305 | 4767.7886 | 6110.1953 | 971859.6971 | 1212071.7838
[17 empty] | 123 | 2025-09-06 | 306 | 0 | 0 | 971859.6971 | 1212071.7838
[17 empty] | 123 | 2025-09-07 | 307 | 0 | 0 | 971859.6971 | 1212071.7838
[17 empty] | 123 | 2025-09-08 | 308 | 4767.7886 | 6110.1953 | 976627.4857 | 1218181.9791
[17 empty] | 123 | 2025-09-09 | 309 | 4767.7886 | 6110.1953 | 981395.2743 | 1224292.1745
[17 empty] | 123 | 2025-09-10 | 310 | 4767.7886 | 6110.1953 | 986163.0629 | 1230402.3698
[17 empty] | 123 | 2025-09-11 | 311 | 4767.7886 | 6110.1953 | 990930.8514 | 1236512.5651
[17 empty] | 123 | 2025-09-12 | 312 | 4767.7886 | 6110.1953 | 995698.64 | 1242622.7604
[17 empty] | 123 | 2025-09-13 | 313 | 0 | 0 | 995698.64 | 1242622.7604
[17 empty] | 123 | 2025-09-14 | 314 | 0 | 0 | 995698.64 | 1242622.7604
[17 empty] | 123 | 2025-09-15 | 315 | 4767.7886 | 6110.1953 | 1000466.4286 | 1248732.9557
[17 empty] | 123 | 2025-09-16 | 316 | 4767.7886 | 6110.1953 | 1005234.2171 | 1254843.151
[17 empty] | 123 | 2025-09-17 | 317 | 4767.7886 | 6110.1953 | 1010002.0057 | 1260953.3463
[17 empty] | 123 | 2025-09-18 | 318 | 4767.7886 | 6110.1953 | 1014769.7943 | 1267063.5417
[17 empty] | 123 | 2025-09-19 | 319 | 4767.7886 | 6110.1953 | 1019537.5829 | 1273173.737
[17 empty] | 123 | 2025-09-20 | 320 | 0 | 0 | 1019537.5829 | 1273173.737
[17 empty] | 123 | 2025-09-21 | 321 | 0 | 0 | 1019537.5829 | 1273173.737
[17 empty] | 123 | 2025-09-22 | 322 | 4767.7886 | 6110.1953 | 1024305.3714 | 1279283.9323
[17 empty] | 123 | 2025-09-23 | 323 | 462.7886 | 513.6953 | 1024768.16 | 1279797.6276
[17 empty] | 123 | 2025-09-24 | 324 | 462.7886 | 513.6953 | 1025230.9486 | 1280311.3229
[17 empty] | 123 | 2025-09-25 | 325 | 462.7886 | 513.6953 | 1025693.7371 | 1280825.0182
[17 empty] | 123 | 2025-09-26 | 326 | 462.7886 | 513.6953 | 1026156.5257 | 1281338.7135
[17 empty] | 123 | 2025-09-27 | 327 | 0 | 0 | 1026156.5257 | 1281338.7135
[17 empty] | 123 | 2025-09-28 | 328 | 0 | 0 | 1026156.5257 | 1281338.7135
[17 empty] | 123 | 2025-09-29 | 329 | 462.7886 | 513.6953 | 1026619.3143 | 1281852.4089
[17 empty] | 123 | 2025-09-30 | 330 | 462.7886 | 513.6953 | 1027082.1029 | 1282366.1042
[17 empty] | 123 | 2025-10-01 | 331 | 462.7886 | 513.6953 | 1027544.8914 | 1282879.7995
[17 empty] | 123 | 2025-10-02 | 332 | 462.7886 | 513.6953 | 1028007.68 | 1283393.4948
[17 empty] | 124 | 2024-12-18 | 1 | 575.2259 | 730.5369 | 575.2259 | 730.5369
[17 empty] | 124 | 2024-12-19 | 2 | 575.2259 | 730.5369 | 1150.4518 | 1461.0738
[17 empty] | 124 | 2024-12-20 | 3 | 575.2259 | 730.5369 | 1725.6777 | 2191.6107
[17 empty] | 124 | 2024-12-21 | 4 | 0 | 0 | 1725.6777 | 2191.6107
[17 empty] | 124 | 2024-12-22 | 5 | 0 | 0 | 1725.6777 | 2191.6107
[17 empty] | 124 | 2024-12-23 | 6 | 3401.4659 | 4263.3369 | 5127.1437 | 6454.9477
[17 empty] | 124 | 2024-12-24 | 7 | 3401.4659 | 4263.3369 | 8528.6096 | 10718.2846
[17 empty] | 124 | 2024-12-25 | 8 | 3401.4659 | 4263.3369 | 11930.0755 | 14981.6215
[17 empty] | 124 | 2024-12-26 | 9 | 3401.4659 | 4263.3369 | 15331.5414 | 19244.9584
[17 empty] | 124 | 2024-12-27 | 10 | 3401.4659 | 4263.3369 | 18733.0073 | 23508.2953
[17 empty] | 124 | 2024-12-28 | 11 | 0 | 0 | 18733.0073 | 23508.2953
[17 empty] | 124 | 2024-12-29 | 12 | 0 | 0 | 18733.0073 | 23508.2953
[17 empty] | 124 | 2024-12-30 | 13 | 3401.4659 | 4263.3369 | 22134.4732 | 27771.6322
[17 empty] | 124 | 2024-12-31 | 14 | 3401.4659 | 4263.3369 | 25535.9392 | 32034.9691
[17 empty] | 124 | 2025-01-01 | 15 | 3401.4659 | 4263.3369 | 28937.4051 | 36298.306
[17 empty] | 124 | 2025-01-02 | 16 | 3401.4659 | 4263.3369 | 32338.871 | 40561.643
[17 empty] | 124 | 2025-01-03 | 17 | 3401.4659 | 4263.3369 | 35740.3369 | 44824.9799
[17 empty] | 124 | 2025-01-04 | 18 | 0 | 0 | 35740.3369 | 44824.9799
[17 empty] | 124 | 2025-01-05 | 19 | 0 | 0 | 35740.3369 | 44824.9799
[17 empty] | 124 | 2025-01-06 | 20 | 3401.4659 | 4263.3369 | 39141.8028 | 49088.3168
[17 empty] | 124 | 2025-01-07 | 21 | 3401.4659 | 4263.3369 | 42543.2687 | 53351.6537
[17 empty] | 124 | 2025-01-08 | 22 | 3401.4659 | 4263.3369 | 45944.7346 | 57614.9906
[17 empty] | 124 | 2025-01-09 | 23 | 3401.4659 | 4263.3369 | 49346.2006 | 61878.3275
[17 empty] | 124 | 2025-01-10 | 24 | 3401.4659 | 4263.3369 | 52747.6665 | 66141.6644
[17 empty] | 124 | 2025-01-11 | 25 | 0 | 0 | 52747.6665 | 66141.6644
[17 empty] | 124 | 2025-01-12 | 26 | 0 | 0 | 52747.6665 | 66141.6644
[17 empty] | 124 | 2025-01-13 | 27 | 3401.4659 | 4263.3369 | 56149.1324 | 70405.0013
[17 empty] | 124 | 2025-01-14 | 28 | 3401.4659 | 4263.3369 | 59550.5983 | 74668.3383
[17 empty] | 124 | 2025-01-15 | 29 | 3401.4659 | 4263.3369 | 62952.0642 | 78931.6752
[17 empty] | 124 | 2025-01-16 | 30 | 3401.4659 | 4263.3369 | 66353.5301 | 83195.0121
[17 empty] | 124 | 2025-01-17 | 31 | 3401.4659 | 4263.3369 | 69754.9961 | 87458.349
[17 empty] | 124 | 2025-01-18 | 32 | 0 | 0 | 69754.9961 | 87458.349
[17 empty] | 124 | 2025-01-19 | 33 | 0 | 0 | 69754.9961 | 87458.349
[17 empty] | 124 | 2025-01-20 | 34 | 3401.4659 | 4263.3369 | 73156.462 | 91721.6859
[17 empty] | 124 | 2025-01-21 | 35 | 3401.4659 | 4263.3369 | 76557.9279 | 95985.0228
[17 empty] | 124 | 2025-01-22 | 36 | 3401.4659 | 4263.3369 | 79959.3938 | 100248.3597
[17 empty] | 124 | 2025-01-23 | 37 | 3401.4659 | 4263.3369 | 83360.8597 | 104511.6966
[17 empty] | 124 | 2025-01-24 | 38 | 5974.5185 | 7531.1138 | 89335.3783 | 112042.8104
[17 empty] | 124 | 2025-01-25 | 39 | 0 | 0 | 89335.3783 | 112042.8104
[17 empty] | 124 | 2025-01-26 | 40 | 0 | 0 | 89335.3783 | 112042.8104
[17 empty] | 124 | 2025-01-27 | 41 | 3148.2785 | 3998.3138 | 92483.6568 | 116041.1242
[17 empty] | 124 | 2025-01-28 | 42 | 3148.2785 | 3998.3138 | 95631.9354 | 120039.4379
[17 empty] | 124 | 2025-01-29 | 43 | 3148.2785 | 3998.3138 | 98780.2139 | 124037.7517
[17 empty] | 124 | 2025-01-30 | 44 | 3148.2785 | 3998.3138 | 101928.4925 | 128036.0654
[17 empty] | 124 | 2025-01-31 | 45 | 3148.2785 | 3998.3138 | 105076.771 | 132034.3792
[17 empty] | 124 | 2025-02-01 | 46 | 0 | 0 | 105076.771 | 132034.3792
[17 empty] | 124 | 2025-02-02 | 47 | 0 | 0 | 105076.771 | 132034.3792
[17 empty] | 124 | 2025-02-03 | 48 | 3148.2785 | 3998.3138 | 108225.0495 | 136032.6929
[17 empty] | 124 | 2025-02-04 | 49 | 3148.2785 | 3998.3138 | 111373.3281 | 140031.0067
[17 empty] | 124 | 2025-02-05 | 50 | 3148.2785 | 3998.3138 | 114521.6066 | 144029.3204
[17 empty] | 124 | 2025-02-06 | 51 | 3148.2785 | 3998.3138 | 117669.8852 | 148027.6342
[17 empty] | 124 | 2025-02-07 | 52 | 3148.2785 | 3998.3138 | 120818.1637 | 152025.9479
[17 empty] | 124 | 2025-02-08 | 53 | 0 | 0 | 120818.1637 | 152025.9479
[17 empty] | 124 | 2025-02-09 | 54 | 0 | 0 | 120818.1637 | 152025.9479
[17 empty] | 124 | 2025-02-10 | 55 | 3148.2785 | 3998.3138 | 123966.4423 | 156024.2617
[17 empty] | 124 | 2025-02-11 | 56 | 3148.2785 | 3998.3138 | 127114.7208 | 160022.5755
[17 empty] | 124 | 2025-02-12 | 57 | 3148.2785 | 3998.3138 | 130262.9994 | 164020.8892
[17 empty] | 124 | 2025-02-13 | 58 | 3148.2785 | 3998.3138 | 133411.2779 | 168019.203
[17 empty] | 124 | 2025-02-14 | 59 | 3148.2785 | 3998.3138 | 136559.5565 | 172017.5167
[17 empty] | 124 | 2025-02-15 | 60 | 0 | 0 | 136559.5565 | 172017.5167
[17 empty] | 124 | 2025-02-16 | 61 | 0 | 0 | 136559.5565 | 172017.5167
[17 empty] | 124 | 2025-02-17 | 62 | 3148.2785 | 3998.3138 | 139707.835 | 176015.8305
[17 empty] | 124 | 2025-02-18 | 63 | 3148.2785 | 3998.3138 | 142856.1136 | 180014.1442
[17 empty] | 124 | 2025-02-19 | 64 | 3148.2785 | 3998.3138 | 146004.3921 | 184012.458
[17 empty] | 124 | 2025-02-20 | 65 | 3148.2785 | 3998.3138 | 149152.6707 | 188010.7717
[17 empty] | 124 | 2025-02-21 | 66 | 3148.2785 | 3998.3138 | 152300.9492 | 192009.0855
[17 empty] | 124 | 2025-02-22 | 67 | 0 | 0 | 152300.9492 | 192009.0855
[17 empty] | 124 | 2025-02-23 | 68 | 0 | 0 | 152300.9492 | 192009.0855
[17 empty] | 124 | 2025-02-24 | 69 | 3148.2785 | 3998.3138 | 155449.2278 | 196007.3992
[17 empty] | 124 | 2025-02-25 | 70 | 3148.2785 | 3998.3138 | 158597.5063 | 200005.713
[17 empty] | 124 | 2025-02-26 | 71 | 3148.2785 | 3998.3138 | 161745.7848 | 204004.0268
[17 empty] | 124 | 2025-02-27 | 72 | 3148.2785 | 3998.3138 | 164894.0634 | 208002.3405
[17 empty] | 124 | 2025-02-28 | 73 | 3148.2785 | 3998.3138 | 168042.3419 | 212000.6543
[17 empty] | 124 | 2025-03-01 | 74 | 0 | 0 | 168042.3419 | 212000.6543
[17 empty] | 124 | 2025-03-02 | 75 | 0 | 0 | 168042.3419 | 212000.6543
[17 empty] | 124 | 2025-03-03 | 76 | 3148.2785 | 3998.3138 | 171190.6205 | 215998.968
[17 empty] | 124 | 2025-03-04 | 77 | 3148.2785 | 3998.3138 | 174338.899 | 219997.2818
[17 empty] | 124 | 2025-03-05 | 78 | 3148.2785 | 3998.3138 | 177487.1776 | 223995.5955
[17 empty] | 124 | 2025-03-06 | 79 | 3148.2785 | 3998.3138 | 180635.4561 | 227993.9093
[17 empty] | 124 | 2025-03-07 | 80 | 3148.2785 | 3998.3138 | 183783.7347 | 231992.223
[17 empty] | 124 | 2025-03-08 | 81 | 0 | 0 | 183783.7347 | 231992.223
[17 empty] | 124 | 2025-03-09 | 82 | 0 | 0 | 183783.7347 | 231992.223
[17 empty] | 124 | 2025-03-10 | 83 | 3148.2785 | 3998.3138 | 186932.0132 | 235990.5368
[17 empty] | 124 | 2025-03-11 | 84 | 3148.2785 | 3998.3138 | 190080.2918 | 239988.8506
[17 empty] | 124 | 2025-03-12 | 85 | 3148.2785 | 3998.3138 | 193228.5703 | 243987.1643
[17 empty] | 124 | 2025-03-13 | 86 | 3148.2785 | 3998.3138 | 196376.8489 | 247985.4781
[17 empty] | 124 | 2025-03-14 | 87 | 3148.2785 | 3998.3138 | 199525.1274 | 251983.7918
[17 empty] | 124 | 2025-03-15 | 88 | 0 | 0 | 199525.1274 | 251983.7918
[17 empty] | 124 | 2025-03-16 | 89 | 0 | 0 | 199525.1274 | 251983.7918
[17 empty] | 124 | 2025-03-17 | 90 | 3148.2785 | 3998.3138 | 202673.406 | 255982.1056
[17 empty] | 124 | 2025-03-18 | 91 | 3148.2785 | 3998.3138 | 205821.6845 | 259980.4193
[17 empty] | 124 | 2025-03-19 | 92 | 3148.2785 | 3998.3138 | 208969.9631 | 263978.7331
[17 empty] | 124 | 2025-03-20 | 93 | 3148.2785 | 3998.3138 | 212118.2416 | 267977.0468
[17 empty] | 124 | 2025-03-21 | 94 | 3148.2785 | 3998.3138 | 215266.5201 | 271975.3606
[17 empty] | 124 | 2025-03-22 | 95 | 0 | 0 | 215266.5201 | 271975.3606
[17 empty] | 124 | 2025-03-23 | 96 | 0 | 0 | 215266.5201 | 271975.3606
[17 empty] | 124 | 2025-03-24 | 97 | 3148.2785 | 3998.3138 | 218414.7987 | 275973.6743
[17 empty] | 124 | 2025-03-25 | 98 | 7745.4035 | 9055.1513 | 226160.2022 | 285028.8256
[17 empty] | 124 | 2025-03-26 | 99 | 7745.4035 | 9055.1513 | 233905.6058 | 294083.9769
[17 empty] | 124 | 2025-03-27 | 100 | 7745.4035 | 9055.1513 | 241651.0093 | 303139.1281
[17 empty] | 124 | 2025-03-28 | 101 | 7745.4035 | 9055.1513 | 249396.4129 | 312194.2794
[17 empty] | 124 | 2025-03-29 | 102 | 0 | 0 | 249396.4129 | 312194.2794
[17 empty] | 124 | 2025-03-30 | 103 | 0 | 0 | 249396.4129 | 312194.2794
[17 empty] | 124 | 2025-03-31 | 104 | 7745.4035 | 9055.1513 | 257141.8164 | 321249.4306
[17 empty] | 124 | 2025-04-01 | 105 | 7745.4035 | 9055.1513 | 264887.22 | 330304.5819
[17 empty] | 124 | 2025-04-02 | 106 | 7745.4035 | 9055.1513 | 272632.6235 | 339359.7331
[17 empty] | 124 | 2025-04-03 | 107 | 7745.4035 | 9055.1513 | 280378.0271 | 348414.8844
[17 empty] | 124 | 2025-04-04 | 108 | 13079.0574 | 15242.1897 | 293457.0845 | 363657.0741
[17 empty] | 124 | 2025-04-05 | 109 | 0 | 0 | 293457.0845 | 363657.0741
[17 empty] | 124 | 2025-04-06 | 110 | 0 | 0 | 293457.0845 | 363657.0741
[17 empty] | 124 | 2025-04-07 | 111 | 13079.0574 | 15242.1897 | 306536.1419 | 378899.2638
[17 empty] | 124 | 2025-04-08 | 112 | 13079.0574 | 15242.1897 | 319615.1993 | 394141.4535
[17 empty] | 124 | 2025-04-09 | 113 | 13079.0574 | 15242.1897 | 332694.2566 | 409383.6432
[17 empty] | 124 | 2025-04-10 | 114 | 13079.0574 | 15242.1897 | 345773.314 | 424625.833
[17 empty] | 124 | 2025-04-11 | 115 | 13079.0574 | 15242.1897 | 358852.3714 | 439868.0227
[17 empty] | 124 | 2025-04-12 | 116 | 0 | 0 | 358852.3714 | 439868.0227
[17 empty] | 124 | 2025-04-13 | 117 | 0 | 0 | 358852.3714 | 439868.0227
[17 empty] | 124 | 2025-04-14 | 118 | 13079.0574 | 15242.1897 | 371931.4288 | 455110.2124
[17 empty] | 124 | 2025-04-15 | 119 | 10506.0048 | 11974.4129 | 382437.4336 | 467084.6253
[17 empty] | 124 | 2025-04-16 | 120 | 10506.0048 | 11974.4129 | 392943.4383 | 479059.0381
[17 empty] | 124 | 2025-04-17 | 121 | 10506.0048 | 11974.4129 | 403449.4431 | 491033.451
[17 empty] | 124 | 2025-04-18 | 122 | 10506.0048 | 11974.4129 | 413955.4479 | 503007.8639
[17 empty] | 124 | 2025-04-19 | 123 | 0 | 0 | 413955.4479 | 503007.8639
[17 empty] | 124 | 2025-04-20 | 124 | 0 | 0 | 413955.4479 | 503007.8639
[17 empty] | 124 | 2025-04-21 | 125 | 10506.0048 | 11974.4129 | 424461.4526 | 514982.2768
[17 empty] | 124 | 2025-04-22 | 126 | 10506.0048 | 11974.4129 | 434967.4574 | 526956.6896
[17 empty] | 124 | 2025-04-23 | 127 | 10506.0048 | 11974.4129 | 445473.4622 | 538931.1025
[17 empty] | 124 | 2025-04-24 | 128 | 10506.0048 | 11974.4129 | 455979.4669 | 550905.5154
[17 empty] | 124 | 2025-04-25 | 129 | 10506.0048 | 11974.4129 | 466485.4717 | 562879.9283
[17 empty] | 124 | 2025-04-26 | 130 | 0 | 0 | 466485.4717 | 562879.9283
[17 empty] | 124 | 2025-04-27 | 131 | 0 | 0 | 466485.4717 | 562879.9283
[17 empty] | 124 | 2025-04-28 | 132 | 5908.8798 | 6917.5754 | 472394.3514 | 569797.5036
[17 empty] | 124 | 2025-04-29 | 133 | 5908.8798 | 6917.5754 | 478303.2312 | 576715.079
[17 empty] | 124 | 2025-04-30 | 134 | 5908.8798 | 6917.5754 | 484212.111 | 583632.6544
[17 empty] | 124 | 2025-05-01 | 135 | 5908.8798 | 6917.5754 | 490120.9907 | 590550.2298
[17 empty] | 124 | 2025-05-02 | 136 | 5908.8798 | 6917.5754 | 496029.8705 | 597467.8051
[17 empty] | 124 | 2025-05-03 | 137 | 0 | 0 | 496029.8705 | 597467.8051
[17 empty] | 124 | 2025-05-04 | 138 | 0 | 0 | 496029.8705 | 597467.8051
[17 empty] | 124 | 2025-05-05 | 139 | 5908.8798 | 6917.5754 | 501938.7502 | 604385.3805
[17 empty] | 124 | 2025-05-06 | 140 | 5908.8798 | 6917.5754 | 507847.63 | 611302.9559
[17 empty] | 124 | 2025-05-07 | 141 | 5908.8798 | 6917.5754 | 513756.5098 | 618220.5313
[17 empty] | 124 | 2025-05-08 | 142 | 5908.8798 | 6917.5754 | 519665.3895 | 625138.1066
[17 empty] | 124 | 2025-05-09 | 143 | 5908.8798 | 6917.5754 | 525574.2693 | 632055.682
[17 empty] | 124 | 2025-05-10 | 144 | 0 | 0 | 525574.2693 | 632055.682
[17 empty] | 124 | 2025-05-11 | 145 | 0 | 0 | 525574.2693 | 632055.682
[17 empty] | 124 | 2025-05-12 | 146 | 5908.8798 | 6917.5754 | 531483.1491 | 638973.2574
[17 empty] | 124 | 2025-05-13 | 147 | 5908.8798 | 6917.5754 | 537392.0288 | 645890.8328
[17 empty] | 124 | 2025-05-14 | 148 | 5908.8798 | 6917.5754 | 543300.9086 | 652808.4081
[17 empty] | 124 | 2025-05-15 | 149 | 5908.8798 | 6917.5754 | 549209.7883 | 659725.9835
[17 empty] | 124 | 2025-05-16 | 150 | 5908.8798 | 6917.5754 | 555118.6681 | 666643.5589
[17 empty] | 124 | 2025-05-17 | 151 | 0 | 0 | 555118.6681 | 666643.5589
[17 empty] | 124 | 2025-05-18 | 152 | 0 | 0 | 555118.6681 | 666643.5589
[17 empty] | 124 | 2025-05-19 | 153 | 5908.8798 | 6917.5754 | 561027.5479 | 673561.1343
[17 empty] | 124 | 2025-05-20 | 154 | 5908.8798 | 6917.5754 | 566936.4276 | 680478.7096
[17 empty] | 124 | 2025-05-21 | 155 | 5908.8798 | 6917.5754 | 572845.3074 | 687396.285
[17 empty] | 124 | 2025-05-22 | 156 | 5908.8798 | 6917.5754 | 578754.1872 | 694313.8604
[17 empty] | 124 | 2025-05-23 | 157 | 5908.8798 | 6917.5754 | 584663.0669 | 701231.4357
[17 empty] | 124 | 2025-05-24 | 158 | 0 | 0 | 584663.0669 | 701231.4357
[17 empty] | 124 | 2025-05-25 | 159 | 0 | 0 | 584663.0669 | 701231.4357
[17 empty] | 124 | 2025-05-26 | 160 | 5908.8798 | 6917.5754 | 590571.9467 | 708149.0111
[17 empty] | 124 | 2025-05-27 | 161 | 5908.8798 | 6917.5754 | 596480.8264 | 715066.5865
[17 empty] | 124 | 2025-05-28 | 162 | 5908.8798 | 6917.5754 | 602389.7062 | 721984.1619
[17 empty] | 124 | 2025-05-29 | 163 | 5908.8798 | 6917.5754 | 608298.586 | 728901.7372
[17 empty] | 124 | 2025-05-30 | 164 | 5908.8798 | 6917.5754 | 614207.4657 | 735819.3126
[17 empty] | 124 | 2025-05-31 | 165 | 0 | 0 | 614207.4657 | 735819.3126
[17 empty] | 124 | 2025-06-01 | 166 | 0 | 0 | 614207.4657 | 735819.3126
[17 empty] | 124 | 2025-06-02 | 167 | 5908.8798 | 6917.5754 | 620116.3455 | 742736.888
[17 empty] | 124 | 2025-06-03 | 168 | 5908.8798 | 6917.5754 | 626025.2252 | 749654.4634
[17 empty] | 124 | 2025-06-04 | 169 | 5908.8798 | 6917.5754 | 631934.105 | 756572.0387
[17 empty] | 124 | 2025-06-05 | 170 | 5908.8798 | 6917.5754 | 637842.9848 | 763489.6141
[17 empty] | 124 | 2025-06-06 | 171 | 5908.8798 | 6917.5754 | 643751.8645 | 770407.1895
[17 empty] | 124 | 2025-06-07 | 172 | 0 | 0 | 643751.8645 | 770407.1895
[17 empty] | 124 | 2025-06-08 | 173 | 0 | 0 | 643751.8645 | 770407.1895
[17 empty] | 124 | 2025-06-09 | 174 | 5908.8798 | 6917.5754 | 649660.7443 | 777324.7649
[17 empty] | 124 | 2025-06-10 | 175 | 5908.8798 | 6917.5754 | 655569.6241 | 784242.3402
[17 empty] | 124 | 2025-06-11 | 176 | 5908.8798 | 6917.5754 | 661478.5038 | 791159.9156
[17 empty] | 124 | 2025-06-12 | 177 | 5908.8798 | 6917.5754 | 667387.3836 | 798077.491
[17 empty] | 124 | 2025-06-13 | 178 | 5908.8798 | 6917.5754 | 673296.2633 | 804995.0664
[17 empty] | 124 | 2025-06-14 | 179 | 0 | 0 | 673296.2633 | 804995.0664
[17 empty] | 124 | 2025-06-15 | 180 | 0 | 0 | 673296.2633 | 804995.0664
[17 empty] | 124 | 2025-06-16 | 181 | 5908.8798 | 6917.5754 | 679205.1431 | 811912.6417
[17 empty] | 124 | 2025-06-17 | 182 | 5908.8798 | 6917.5754 | 685114.0229 | 818830.2171
[17 empty] | 124 | 2025-06-18 | 183 | 5908.8798 | 6917.5754 | 691022.9026 | 825747.7925
[17 empty] | 124 | 2025-06-19 | 184 | 5908.8798 | 6917.5754 | 696931.7824 | 832665.3679
[17 empty] | 124 | 2025-06-20 | 185 | 5908.8798 | 6917.5754 | 702840.6621 | 839582.9432
[17 empty] | 124 | 2025-06-21 | 186 | 0 | 0 | 702840.6621 | 839582.9432
[17 empty] | 124 | 2025-06-22 | 187 | 0 | 0 | 702840.6621 | 839582.9432
[17 empty] | 124 | 2025-06-23 | 188 | 5908.8798 | 6917.5754 | 708749.5419 | 846500.5186
[17 empty] | 124 | 2025-06-24 | 189 | 5908.8798 | 6917.5754 | 714658.4217 | 853418.094
[17 empty] | 124 | 2025-06-25 | 190 | 5908.8798 | 6917.5754 | 720567.3014 | 860335.6694
[17 empty] | 124 | 2025-06-26 | 191 | 5908.8798 | 6917.5754 | 726476.1812 | 867253.2447
[17 empty] | 124 | 2025-06-27 | 192 | 5908.8798 | 6917.5754 | 732385.061 | 874170.8201
[17 empty] | 124 | 2025-06-28 | 193 | 0 | 0 | 732385.061 | 874170.8201
[17 empty] | 124 | 2025-06-29 | 194 | 0 | 0 | 732385.061 | 874170.8201
[17 empty] | 124 | 2025-06-30 | 195 | 5908.8798 | 6917.5754 | 738293.9407 | 881088.3955
[17 empty] | 124 | 2025-07-01 | 196 | 5908.8798 | 6917.5754 | 744202.8205 | 888005.9709
[17 empty] | 124 | 2025-07-02 | 197 | 5908.8798 | 6917.5754 | 750111.7002 | 894923.5462
[17 empty] | 124 | 2025-07-03 | 198 | 5908.8798 | 6917.5754 | 756020.58 | 901841.1216
[17 empty] | 124 | 2025-07-04 | 199 | 5908.8798 | 6917.5754 | 761929.4598 | 908758.697
[17 empty] | 124 | 2025-07-05 | 200 | 0 | 0 | 761929.4598 | 908758.697
[17 empty] | 124 | 2025-07-06 | 201 | 0 | 0 | 761929.4598 | 908758.697
[17 empty] | 124 | 2025-07-07 | 202 | 5908.8798 | 6917.5754 | 767838.3395 | 915676.2723
[17 empty] | 124 | 2025-07-08 | 203 | 5908.8798 | 6917.5754 | 773747.2193 | 922593.8477
[17 empty] | 124 | 2025-07-09 | 204 | 5908.8798 | 6917.5754 | 779656.099 | 929511.4231
[17 empty] | 124 | 2025-07-10 | 205 | 5908.8798 | 6917.5754 | 785564.9788 | 936428.9985
[17 empty] | 124 | 2025-07-11 | 206 | 5908.8798 | 6917.5754 | 791473.8586 | 943346.5738
[17 empty] | 124 | 2025-07-12 | 207 | 0 | 0 | 791473.8586 | 943346.5738
[17 empty] | 124 | 2025-07-13 | 208 | 0 | 0 | 791473.8586 | 943346.5738
[17 empty] | 124 | 2025-07-14 | 209 | 5908.8798 | 6917.5754 | 797382.7383 | 950264.1492
[17 empty] | 124 | 2025-07-15 | 210 | 5908.8798 | 6917.5754 | 803291.6181 | 957181.7246
[17 empty] | 124 | 2025-07-16 | 211 | 5908.8798 | 6917.5754 | 809200.4979 | 964099.3
[17 empty] | 124 | 2025-07-17 | 212 | 5908.8798 | 6917.5754 | 815109.3776 | 971016.8753
[17 empty] | 124 | 2025-07-18 | 213 | 5908.8798 | 6917.5754 | 821018.2574 | 977934.4507
[17 empty] | 124 | 2025-07-19 | 214 | 0 | 0 | 821018.2574 | 977934.4507
[17 empty] | 124 | 2025-07-20 | 215 | 0 | 0 | 821018.2574 | 977934.4507
[17 empty] | 124 | 2025-07-21 | 216 | 5908.8798 | 6917.5754 | 826927.1371 | 984852.0261
[17 empty] | 124 | 2025-07-22 | 217 | 5908.8798 | 6917.5754 | 832836.0169 | 991769.6015
[17 empty] | 124 | 2025-07-23 | 218 | 5908.8798 | 6917.5754 | 838744.8967 | 998687.1768
[17 empty] | 124 | 2025-07-24 | 219 | 5908.8798 | 6917.5754 | 844653.7764 | 1005604.7522
[17 empty] | 124 | 2025-07-25 | 220 | 5908.8798 | 6917.5754 | 850562.6562 | 1012522.3276
[17 empty] | 124 | 2025-07-26 | 221 | 0 | 0 | 850562.6562 | 1012522.3276
[17 empty] | 124 | 2025-07-27 | 222 | 0 | 0 | 850562.6562 | 1012522.3276
[17 empty] | 124 | 2025-07-28 | 223 | 5908.8798 | 6917.5754 | 856471.5359 | 1019439.903
[17 empty] | 124 | 2025-07-29 | 224 | 5908.8798 | 6917.5754 | 862380.4157 | 1026357.4783
[17 empty] | 124 | 2025-07-30 | 225 | 5908.8798 | 6917.5754 | 868289.2955 | 1033275.0537
[17 empty] | 124 | 2025-07-31 | 226 | 5908.8798 | 6917.5754 | 874198.1752 | 1040192.6291
[17 empty] | 124 | 2025-08-01 | 227 | 5908.8798 | 6917.5754 | 880107.055 | 1047110.2045
[17 empty] | 124 | 2025-08-02 | 228 | 0 | 0 | 880107.055 | 1047110.2045
[17 empty] | 124 | 2025-08-03 | 229 | 0 | 0 | 880107.055 | 1047110.2045
[17 empty] | 124 | 2025-08-04 | 230 | 5908.8798 | 6917.5754 | 886015.9348 | 1054027.7798
[17 empty] | 124 | 2025-08-05 | 231 | 5908.8798 | 6917.5754 | 891924.8145 | 1060945.3552
[17 empty] | 124 | 2025-08-06 | 232 | 5908.8798 | 6917.5754 | 897833.6943 | 1067862.9306
[17 empty] | 124 | 2025-08-07 | 233 | 5908.8798 | 6917.5754 | 903742.574 | 1074780.506
[17 empty] | 124 | 2025-08-08 | 234 | 5908.8798 | 6917.5754 | 909651.4538 | 1081698.0813
[17 empty] | 124 | 2025-08-09 | 235 | 0 | 0 | 909651.4538 | 1081698.0813
[17 empty] | 124 | 2025-08-10 | 236 | 0 | 0 | 909651.4538 | 1081698.0813
[17 empty] | 124 | 2025-08-11 | 237 | 5908.8798 | 6917.5754 | 915560.3336 | 1088615.6567
[17 empty] | 124 | 2025-08-12 | 238 | 5908.8798 | 6917.5754 | 921469.2133 | 1095533.2321
[17 empty] | 124 | 2025-08-13 | 239 | 5908.8798 | 6917.5754 | 927378.0931 | 1102450.8075
[17 empty] | 124 | 2025-08-14 | 240 | 5908.8798 | 6917.5754 | 933286.9728 | 1109368.3828
[17 empty] | 124 | 2025-08-15 | 241 | 5908.8798 | 6917.5754 | 939195.8526 | 1116285.9582
[17 empty] | 124 | 2025-08-16 | 242 | 0 | 0 | 939195.8526 | 1116285.9582
[17 empty] | 124 | 2025-08-17 | 243 | 0 | 0 | 939195.8526 | 1116285.9582
[17 empty] | 124 | 2025-08-18 | 244 | 5908.8798 | 6917.5754 | 945104.7324 | 1123203.5336
[17 empty] | 124 | 2025-08-19 | 245 | 5908.8798 | 6917.5754 | 951013.6121 | 1130121.1089
[17 empty] | 124 | 2025-08-20 | 246 | 5908.8798 | 6917.5754 | 956922.4919 | 1137038.6843
[17 empty] | 124 | 2025-08-21 | 247 | 5908.8798 | 6917.5754 | 962831.3717 | 1143956.2597
[17 empty] | 124 | 2025-08-22 | 248 | 5908.8798 | 6917.5754 | 968740.2514 | 1150873.8351
[17 empty] | 124 | 2025-08-23 | 249 | 0 | 0 | 968740.2514 | 1150873.8351
[17 empty] | 124 | 2025-08-24 | 250 | 0 | 0 | 968740.2514 | 1150873.8351
[17 empty] | 124 | 2025-08-25 | 251 | 5908.8798 | 6917.5754 | 974649.1312 | 1157791.4104
[17 empty] | 124 | 2025-08-26 | 252 | 5908.8798 | 6917.5754 | 980558.0109 | 1164708.9858
[17 empty] | 124 | 2025-08-27 | 253 | 5908.8798 | 6917.5754 | 986466.8907 | 1171626.5612
[17 empty] | 124 | 2025-08-28 | 254 | 5908.8798 | 6917.5754 | 992375.7705 | 1178544.1366
[17 empty] | 124 | 2025-08-29 | 255 | 5908.8798 | 6917.5754 | 998284.6502 | 1185461.7119
[17 empty] | 124 | 2025-08-30 | 256 | 0 | 0 | 998284.6502 | 1185461.7119
[17 empty] | 124 | 2025-08-31 | 257 | 0 | 0 | 998284.6502 | 1185461.7119
[17 empty] | 124 | 2025-09-01 | 258 | 5908.8798 | 6917.5754 | 1004193.53 | 1192379.2873
[17 empty] | 124 | 2025-09-02 | 259 | 5908.8798 | 6917.5754 | 1010102.4098 | 1199296.8627
[17 empty] | 124 | 2025-09-03 | 260 | 5908.8798 | 6917.5754 | 1016011.2895 | 1206214.4381
[17 empty] | 124 | 2025-09-04 | 261 | 5908.8798 | 6917.5754 | 1021920.1693 | 1213132.0134
[17 empty] | 124 | 2025-09-05 | 262 | 5908.8798 | 6917.5754 | 1027829.049 | 1220049.5888
[17 empty] | 124 | 2025-09-06 | 263 | 0 | 0 | 1027829.049 | 1220049.5888
[17 empty] | 124 | 2025-09-07 | 264 | 0 | 0 | 1027829.049 | 1220049.5888
[17 empty] | 124 | 2025-09-08 | 265 | 5908.8798 | 6917.5754 | 1033737.9288 | 1226967.1642
[17 empty] | 124 | 2025-09-09 | 266 | 5908.8798 | 6917.5754 | 1039646.8086 | 1233884.7396
[17 empty] | 124 | 2025-09-10 | 267 | 5908.8798 | 6917.5754 | 1045555.6883 | 1240802.3149
[17 empty] | 124 | 2025-09-11 | 268 | 5908.8798 | 6917.5754 | 1051464.5681 | 1247719.8903
[17 empty] | 124 | 2025-09-12 | 269 | 5908.8798 | 6917.5754 | 1057373.4478 | 1254637.4657
[17 empty] | 124 | 2025-09-13 | 270 | 0 | 0 | 1057373.4478 | 1254637.4657
[17 empty] | 124 | 2025-09-14 | 271 | 0 | 0 | 1057373.4478 | 1254637.4657
[17 empty] | 124 | 2025-09-15 | 272 | 5908.8798 | 6917.5754 | 1063282.3276 | 1261555.0411
[17 empty] | 124 | 2025-09-16 | 273 | 5908.8798 | 6917.5754 | 1069191.2074 | 1268472.6164
[17 empty] | 124 | 2025-09-17 | 274 | 5908.8798 | 6917.5754 | 1075100.0871 | 1275390.1918
[17 empty] | 124 | 2025-09-18 | 275 | 5908.8798 | 6917.5754 | 1081008.9669 | 1282307.7672
[17 empty] | 124 | 2025-09-19 | 276 | 5908.8798 | 6917.5754 | 1086917.8467 | 1289225.3426
[17 empty] | 124 | 2025-09-20 | 277 | 0 | 0 | 1086917.8467 | 1289225.3426
[17 empty] | 124 | 2025-09-21 | 278 | 0 | 0 | 1086917.8467 | 1289225.3426
[17 empty] | 124 | 2025-09-22 | 279 | 5908.8798 | 6917.5754 | 1092826.7264 | 1296142.9179
[17 empty] | 124 | 2025-09-23 | 280 | 5908.8798 | 6917.5754 | 1098735.6062 | 1303060.4933
[17 empty] | 124 | 2025-09-24 | 281 | 5908.8798 | 6917.5754 | 1104644.4859 | 1309978.0687
[17 empty] | 124 | 2025-09-25 | 282 | 5908.8798 | 6917.5754 | 1110553.3657 | 1316895.6441
[17 empty] | 124 | 2025-09-26 | 283 | 5908.8798 | 6917.5754 | 1116462.2455 | 1323813.2194
[17 empty] | 124 | 2025-09-27 | 284 | 0 | 0 | 1116462.2455 | 1323813.2194
[17 empty] | 124 | 2025-09-28 | 285 | 0 | 0 | 1116462.2455 | 1323813.2194
[17 empty] | 124 | 2025-09-29 | 286 | 5908.8798 | 6917.5754 | 1122371.1252 | 1330730.7948
[17 empty] | 124 | 2025-09-30 | 287 | 5908.8798 | 6917.5754 | 1128280.005 | 1337648.3702
[17 empty] | 124 | 2025-10-01 | 288 | 5908.8798 | 6917.5754 | 1134188.8847 | 1344565.9455
[17 empty] | 124 | 2025-10-02 | 289 | 5908.8798 | 6917.5754 | 1140097.7645 | 1351483.5209
[17 empty] | 124 | 2025-10-03 | 290 | 575.2259 | 730.5369 | 1140672.9904 | 1352214.0578
[17 empty] | 124 | 2025-10-04 | 291 | 0 | 0 | 1140672.9904 | 1352214.0578
[17 empty] | 124 | 2025-10-05 | 292 | 0 | 0 | 1140672.9904 | 1352214.0578
[17 empty] | 124 | 2025-10-06 | 293 | 575.2259 | 730.5369 | 1141248.2163 | 1352944.5947
[17 empty] | 124 | 2025-10-07 | 294 | 575.2259 | 730.5369 | 1141823.4423 | 1353675.1317
[17 empty] | 124 | 2025-10-08 | 295 | 575.2259 | 730.5369 | 1142398.6682 | 1354405.6686
[17 empty] | 124 | 2025-10-09 | 296 | 575.2259 | 730.5369 | 1142973.8941 | 1355136.2055
[17 empty] | 124 | 2025-10-10 | 297 | 575.2259 | 730.5369 | 1143549.12 | 1355866.7424
[17 empty] | 124 | 2025-10-11 | 298 | 0 | 0 | 1143549.12 | 1355866.7424
[17 empty] | 124 | 2025-10-12 | 299 | 0 | 0 | 1143549.12 | 1355866.7424